## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: | Text Humanizer Pro |  | High | 17
Project URL: | Vite + React |  | Medium | 10
Developer: | AI-Hunter |  | Low | 5
OS:
Environment |  |  | Total Test Cases: | 32
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Comment
BR-001 | Account | Profile | Names can be assigned using numbers. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 11224455 | Only characters should be allowed as input in the name text field. | Numbers can be used as names in the input field. | Fail | High | https://jam.dev/c/4e1b9c45-87e4-4ae3-8ad0-ae76185986e5 |  | Fahad
BR-002 | Account | Security | Forget password button in change password | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | The change password page will include fields for the old password, the new password, and a confirmation for the new password. | The "Forgot Password" button appears on the change password page, which seems irrelevant. | Fail | Medium | https://jam.dev/c/b2451410-1448-4214-adbd-fff9ab827ae1 |  | Fahad
BR-003 | Dashboard | Dashboard | Unable to display the user's word count. | User need to be in browser | 1. Open web app | N/A | Users should be able to see how many words they have used. | Unable to display the word used in the dashboard. | Fail | High | https://jam.dev/c/a80ccb95-52d7-4c27-a88d-856ba5635488 |  | Fahad
BR-004 | Dashboard | Dashboard | The AI detection bar malfunctioned. | User need to be in browser | 1. Open web app | N/A | The AI detection bar should be filled based on the level of similarity detected with AI. | Failed to fill the AI bar on the dashboard page. | Fail | High | https://jam.dev/c/bec88c6d-9cac-48d5-a53d-6077b582aba4 |  | Fahad
BR-005 | Dashboard | Dashboard | AI detection failed | User need to be in browser | 1. Open web app | N/A | If a text is generated by AI, it should indicate that it was created using artificial intelligence. | The displayed text appears to be himazine, but it was actually generated by AI. | Fail | High | https://jam.dev/c/a091e244-6fa8-4000-aeab-717f51a5d628 |  | Fahad
BR-006 | Dashboard | Dashboard | Failed to make the text more relatable. | User need to be in browser | 1. Open web app | N/A | When users paste their text, the generation should be done properly based on the category. | Failed to correct the generation. Simply adding "ing" to words doesn't make the text sound humanized by AI. | Fail | High | https://jam.dev/c/83902d8d-9afa-4a55-bcc4-3f7ca8e84a59 |  | Fahad
BR-007 | Dashboard | Dashboard | The copy prompt doesn't show up when clicked. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | When the user clicks the copy button, a prompt should appear with the message "Copied to clipboard." | No message appears when the copy button is clicked. | Fail | High | https://jam.dev/c/a4b1ae10-d607-4098-ac1d-a271c212a4a5 |  | Fahad
BR-008 | Landing Page | Header | The logo appears to be a bit small. | User need to be in web browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been observed in the homepage header section. | Fail | Low | https://jam.dev/c/627db0fc-28db-436f-a1b2-d1b8cc923450 |  | Fahad
BR-009 | Landing Page | Header | Header section size issue | User need to be in browser | 1. Open web app | N/A | The header section size should match the client's requirements exactly. | The header section appears to be smaller than the client's requirements. | Fail | Low | https://jam.dev/c/01c7fc2b-8290-4158-832a-562137b55e28 |  | Fahad
BR-010 | Landing Page | Home | Text font and color issue | User need to be in browser | 1. Open web app | N/A | The font and color should match the client's requirements. | The font size and text color do not match the client's requirements. | Fail | Low | https://jam.dev/c/2637688e-9f2a-4a43-9490-d77286dc7be0 |  | Fahad
BR-011 | Landing Page | Home | The icon size is smaller than the client's requirement. | User need to be in browser | 1. Open web app | N/A | The alignment and font should match the client's requirements. | The icon appears to be smaller than the client's requirement. | Fail | Low | https://jam.dev/c/9f5b1842-a1c3-4bd6-a0f0-b4e3cf772daf |  | Fahad
BR-012 | Landing Page | Home | Content of SEO Agency banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/8f1ec445-48c1-43a2-99a3-8ae5b5b900a3 |  | Fahad
BR-013 | Landing Page | Home | Content of Student banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/12e60943-b415-4bc0-9433-6002453d7a32 |  | Fahad
BR-014 | Landing Page | Home | Content of Marketer banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/adc197c5-b754-498f-932e-33c1eaaccf48 |  | Fahad
BR-015 | Landing Page | Home | Content of Content Creator banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/4099e7d9-2aef-4774-bbbd-84d4ac4e3fb0 |  | Fahad
BR-016 | Landing Page | Home | Content of Resume/CV banner context missing in client requirement | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/b681f39d-9576-4240-9220-348dc31d9092 |  | Fahad
BR-017 | Pricing | Pricing | Banner content missing | User need to be in browser | 1. Open web app | N/A | Pricing content should align exactly with the client's requirements. | The pricing category and banner content don't align with the client's specifications. | Fail | High | https://jam.dev/c/beb7985c-b9ce-4279-966f-8ddb524c65f7 |  | Fahad
BR-018 | Pricing | Pricing | Popular subscription package is not appearing. | User need to be in browser | 1. Open web app | N/A | The popular package should be highlighted on the price banner to help customers find the best deal. | The popular package is not appearing in the price banner as per the client's requirement. | Fail | Medium | https://jam.dev/c/ac834272-815f-4f86-9bc8-5a025791cb6c |  | Fahad
BR-019 | Pricing | Pricing | Design and alignment problem. | User need to be in browser | 1. Open web app | N/A | Design and alignment should match the client's requirements. | A different design has been noticed in the web app. | Fail | Medium | https://jam.dev/c/7b0d1360-907f-477d-aa18-29bfa019046d |  | Fahad
BR-020 | Pricing | Pricing | Delay in the price indicator. | User need to be in browser | 1. Open web app | N/A | A dynamic response in the web app can greatly enhance client attraction. | A delay in the price bar has been observed when the user adjusts the amount by sliding the bar. | Fail | High | https://jam.dev/c/2cd07e41-ee68-4520-8712-f3cbd9183201 |  | Fahad
BR-021 | Pricing | Pricing | The web app failed to load after completing the payment successfully. | User need to be in browser | 1. Open web app 2. Select price range and confirm payment | N/A | The user should be redirected to the home page after successfully purchasing the subscription. | Connection failed after successfully completing the subscription purchase. | Fail | High | https://jam.dev/c/c7d813c8-8ce3-411a-90a6-7d3a34ecabb5 |  | Fahad
BR-022 | Pricing | Pricing | Enterprise banner is missing. | User need to be in browser | 1. Open web app | N/A | Enterprise subscription should be accessible and visible in the web app. | The missing enterprise banner in the web app has been noticed. | Fail | High | https://jam.dev/c/bbef7505-46f7-40b3-9f5e-dafa0ea62449 |  | Fahad
BR-023 | Pricing | Pricing | Design and alignment issue | User need to be in browser | 1. Open web app | N/A | The design and alignment should match the client's requirements. | A different design has been noticed in the web app, which does not align with the client's requirements. | Fail | Medium | https://jam.dev/c/4afe52c8-6143-400d-93e4-ac8532486fb7 |  | Fahad
BR-024 | Pricing | Pricing | Discount percentage missing | User need to be in browser | 1. Open web app | N/A | The subscription banner should display the discount percentage. | The discount price is displayed, but the percentage isn’t shown in the top corner of the banner. | Fail | Medium | https://jam.dev/c/ecb91c2f-c915-4fce-9730-a06d161d0484 |  | Fahad
BR-025 | Signup | Data Policy | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the data policy, and it needs to be accurate. | The content for the data policy is missing. | Fail | High | https://jam.dev/c/98dd060c-576d-4923-a95c-a990d46ecfd6 |  | Fahad
BR-026 | Signup | Signup | Logo seems to be small | User need to be in browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been noticed on the signup page. | Fail | Low | https://jam.dev/c/1c564669-c315-4a2a-a02f-602b9132f7d5 |  | Fahad
BR-027 | Signup | Signup | Missing the option to sign up with Apple ID. | User need to be in browser | 1. Open web app | N/A | The user should be able to signup using two methods as per the client's requirement. | Missing Apple ID signup method on the signup page. | Fail | High | https://jam.dev/c/df41064e-6b9b-4503-907e-1cd628585d14 |  | Fahad
BR-028 | Signup | Signup | Failed to login with google | User need to be in browser | 1. Open web app | N/A | Users should be able to log in or sign up with their Google account. | Unable to log in or sign up with a Google account. | Fail | High | https://jam.dev/c/bcc54832-a96c-43df-a08e-750eab7e0b76 |  | Fahad
BR-029 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | All inputs in the sign-in and sign-up fields should function flawlessly as intended. | Failed to sign up after entering the password, and even after updating it to meet the requirements, the issue persisted. | Fail | High | https://jam.dev/c/507d8b86-ee98-4b3f-9f77-f04863f8ed7e |  | Fahad
BR-030 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | A password should meet the requirements of being at least 8 characters long and including a combination of symbols, letters, and numbers. | Password met the requirements but the signup process failed. | Fail | High | https://jam.dev/c/a003c45b-c55e-42b9-979d-06098fd87c27 |  | Fahad
BR-031 | Signup | Signup | Terms of Use and Privacy Policy button failed | User need to be in browser | 1. Open web app | N/A | After entering the registration credentials, the user needs to click on the Terms of Use and Privacy button. Then, they can proceed by clicking the signup button. | The user can submit the form without selecting the terms of use and privacy policy button. | Fail | High | https://jam.dev/c/7eb55e28-96e5-44bd-9f8b-1d20f5ff389c |  | Fahad
BR-032 | Signup | Terms and use | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the terms and use, and it needs to be accurate. | The content for the terms and use is missing. | Fail | High | https://jam.dev/c/0d7a142d-483b-4d1c-ae79-9696bfda932a |  | Fahad

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Text Humanizer Pro
Developer: | AI - Hunter
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
BR_001 | Landing Page | Header | The logo appears to be a bit small. | User need to be in web browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been observed in the homepage header section. | Fail | Low | https://jam.dev/c/627db0fc-28db-436f-a1b2-d1b8cc923450
BR_002 | Landing Page | Header | Header section size issue | User need to be in browser | 1. Open web app | N/A | The header section size should match the client's requirements exactly. | The header section appears to be smaller than the client's requirements. | Fail | Low | https://jam.dev/c/01c7fc2b-8290-4158-832a-562137b55e28
BR_003 | Landing Page | Home | Text font and color issue | User need to be in browser | 1. Open web app | N/A | The font and color should match the client's requirements. | The font size and text color do not match the client's requirements. | Fail | Low | https://jam.dev/c/2637688e-9f2a-4a43-9490-d77286dc7be0
BR_004 | Landing Page | Home | The icon size is smaller than the client's requirement. | User need to be in browser | 1. Open web app | N/A | The alignment and font should match the client's requirements. | The icon appears to be smaller than the client's requirement. | Fail | Low | https://jam.dev/c/9f5b1842-a1c3-4bd6-a0f0-b4e3cf772daf
BR_005 | Landing Page | Home | Content of SEO Agency banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/8f1ec445-48c1-43a2-99a3-8ae5b5b900a3
BR_006 | Landing Page | Home | Content of Student banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/12e60943-b415-4bc0-9433-6002453d7a32
BR_007 | Landing Page | Home | Content of Marketer banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/adc197c5-b754-498f-932e-33c1eaaccf48
BR_008 | Landing Page | Home | Content of Content Creator banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/4099e7d9-2aef-4774-bbbd-84d4ac4e3fb0
BR_009 | Landing Page | Home | Content of Resume/CV banner context missing in client requirement | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/b681f39d-9576-4240-9220-348dc31d9092
BR_010 | Signup | Signup | Logo seems to be small | User need to be in browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been noticed on the signup page. | Fail | Low | https://jam.dev/c/1c564669-c315-4a2a-a02f-602b9132f7d5
BR_011 | Signup | Signup | Missing the option to sign up with Apple ID. | User need to be in browser | 1. Open web app | N/A | The user should be able to signup using two methods as per the client's requirement. | Missing Apple ID signup method on the signup page. | Fail | High | https://jam.dev/c/df41064e-6b9b-4503-907e-1cd628585d14
BR_012 | Signup | Data Policy | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the data policy, and it needs to be accurate. | The content for the data policy is missing. | Fail | High | https://jam.dev/c/98dd060c-576d-4923-a95c-a990d46ecfd6
BR_013 | Signup | Terms and use | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the terms and use, and it needs to be accurate. | The content for the terms and use is missing. | Fail | High | https://jam.dev/c/0d7a142d-483b-4d1c-ae79-9696bfda932a
BR_014 | Signup | Signup | Failed to login with google | User need to be in browser | 1. Open web app | N/A | Users should be able to log in or sign up with their Google account. | Unable to log in or sign up with a Google account. | Fail | High | https://jam.dev/c/bcc54832-a96c-43df-a08e-750eab7e0b76
BR_015 | Pricing | Pricing | Banner content missing | User need to be in browser | 1. Open web app | N/A | Pricing content should align exactly with the client's requirements. | The pricing category and banner content don't align with the client's specifications. | Fail | High | https://jam.dev/c/beb7985c-b9ce-4279-966f-8ddb524c65f7
BR_016 | Pricing | Pricing | Popular subscription package is not appearing. | User need to be in browser | 1. Open web app | N/A | The popular package should be highlighted on the price banner to help customers find the best deal. | The popular package is not appearing in the price banner as per the client's requirement. | Fail | Medium | https://jam.dev/c/ac834272-815f-4f86-9bc8-5a025791cb6c
BR_017 | Pricing | Pricing | Design and alignment problem. | User need to be in browser | 1. Open web app | N/A | Design and alignment should match the client's requirements. | A different design has been noticed in the web app. | Fail | Medium | https://jam.dev/c/7b0d1360-907f-477d-aa18-29bfa019046d
BR_018 | Pricing | Pricing | Delay in the price indicator. | User need to be in browser | 1. Open web app | N/A | A dynamic response in the web app can greatly enhance client attraction. | A delay in the price bar has been observed when the user adjusts the amount by sliding the bar. | Fail | High | https://jam.dev/c/2cd07e41-ee68-4520-8712-f3cbd9183201
BR_019 | Pricing | Pricing | The web app failed to load after completing the payment successfully. | User need to be in browser | 1. Open web app 2. Select price range and confirm payment | N/A | The user should be redirected to the home page after successfully purchasing the subscription. | Connection failed after successfully completing the subscription purchase. | Fail | High | https://jam.dev/c/c7d813c8-8ce3-411a-90a6-7d3a34ecabb5
BR_020 | Pricing | Pricing | Enterprise banner is missing. | User need to be in browser | 1. Open web app | N/A | Enterprise subscription should be accessible and visible in the web app. | The missing enterprise banner in the web app has been noticed. | Fail | High | https://jam.dev/c/bbef7505-46f7-40b3-9f5e-dafa0ea62449
BR_021 | Pricing | Pricing | Design and alignment issue | User need to be in browser | 1. Open web app | N/A | The design and alignment should match the client's requirements. | A different design has been noticed in the web app, which does not align with the client's requirements. | Fail | Medium | https://jam.dev/c/4afe52c8-6143-400d-93e4-ac8532486fb7
BR_022 | Pricing | Pricing | Discount percentage missing | User need to be in browser | 1. Open web app | N/A | The subscription banner should display the discount percentage. | The discount price is displayed, but the percentage isn’t shown in the top corner of the banner. | Fail | Medium | https://jam.dev/c/ecb91c2f-c915-4fce-9730-a06d161d0484
BR_023 | Dashboard | Dashboard | Unable to display the user's word count. | User need to be in browser | 1. Open web app | N/A | Users should be able to see how many words they have used. | Unable to display the word used in the dashboard. | Fail | High | https://jam.dev/c/a80ccb95-52d7-4c27-a88d-856ba5635488
BR_024 | Dashboard | Dashboard | The AI detection bar malfunctioned. | User need to be in browser | 1. Open web app | N/A | The AI detection bar should be filled based on the level of similarity detected with AI. | Failed to fill the AI bar on the dashboard page. | Fail | High | https://jam.dev/c/bec88c6d-9cac-48d5-a53d-6077b582aba4
BR_025 | Dashboard | Dashboard | AI detection failed | User need to be in browser | 1. Open web app | N/A | If a text is generated by AI, it should indicate that it was created using artificial intelligence. | The displayed text appears to be himazine, but it was actually generated by AI. | Fail | High | https://jam.dev/c/a091e244-6fa8-4000-aeab-717f51a5d628
BR_026 | Dashboard | Dashboard | Failed to make the text more relatable. | User need to be in browser | 1. Open web app | N/A | When users paste their text, the generation should be done properly based on the category. | Failed to correct the generation. Simply adding "ing" to words doesn't make the text sound humanized by AI. | Fail | High | https://jam.dev/c/83902d8d-9afa-4a55-bcc4-3f7ca8e84a59
BR_027 | Account | Profile | Names can be assigned using numbers. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 11224455 | Only characters should be allowed as input in the name text field. | Numbers can be used as names in the input field. | Fail | High | https://jam.dev/c/4e1b9c45-87e4-4ae3-8ad0-ae76185986e5
BR_028 | Account | Security | Forget password button in change password | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | The change password page will include fields for the old password, the new password, and a confirmation for the new password. | The "Forgot Password" button appears on the change password page, which seems irrelevant. | Fail | Medium | https://jam.dev/c/b2451410-1448-4214-adbd-fff9ab827ae1
BR_029 | Dashboard | Dashboard | The copy prompt doesn't show up when clicked. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | When the user clicks the copy button, a prompt should appear with the message "Copied to clipboard." | No message appears when the copy button is clicked. | Fail | High | https://jam.dev/c/a4b1ae10-d607-4098-ac1d-a271c212a4a5
BR_030 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | All inputs in the sign-in and sign-up fields should function flawlessly as intended. | Failed to sign up after entering the password, and even after updating it to meet the requirements, the issue persisted. | Fail | High | https://jam.dev/c/507d8b86-ee98-4b3f-9f77-f04863f8ed7e
BR_031 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | A password should meet the requirements of being at least 8 characters long and including a combination of symbols, letters, and numbers. | Password met the requirements but the signup process failed. | Fail | High | https://jam.dev/c/a003c45b-c55e-42b9-979d-06098fd87c27
BR_032 | Signup | Signup | Terms of Use and Privacy Policy button failed | User need to be in browser | 1. Open web app | N/A | After entering the registration credentials, the user needs to click on the Terms of Use and Privacy button. Then, they can proceed by clicking the signup button. | The user can submit the form without selecting the terms of use and privacy policy button. | Fail | High | https://jam.dev/c/7eb55e28-96e5-44bd-9f8b-1d20f5ff389c
BR_033
BR_034
BR_035
BR_036
BR_037
BR_038

## Tahsin
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Account | Profile | BR-001 | 1 | 3.13% | High: 1 Medium: 0 Low: 0
Account | Security | BR-002 | 1 | 3.13% | High: 0 Medium: 1 Low: 0
Dashboard | Dashboard | BR-003, BR-004, BR-005, BR-006, BR-007 | 5 | 15.63% | High: 5 Medium: 0 Low: 0
Landing Page | Header | BR-008, BR-009 | 2 | 6.25% | High: 0 Medium: 0 Low: 2
Landing Page | Home | BR-010, BR-011, BR-012, BR-013, BR-014, BR-015, BR-016 | 7 | 21.88% | High: 0 Medium: 5 Low: 2
Pricing | Pricing | BR-017, BR-018, BR-019, BR-020, BR-021, BR-022, BR-023, BR-024 | 8 | 25.00% | High: 4 Medium: 4 Low: 0
Signup | Data Policy | BR-025 | 1 | 3.13% | High: 1 Medium: 0 Low: 0
Signup | Signup | BR-026, BR-027, BR-028, BR-029, BR-030, BR-031 | 6 | 18.75% | High: 5 Medium: 0 Low: 1
Signup | Terms and use | BR-032 | 1 | 3.13% | High: 1 Medium: 0 Low: 0