## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Parent Bridge
Developer: | AI Hunter
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127 | [11 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment
BR_001 | Splash Screen | Splash Screen | "Next Button" is not implemented | User need to able to access website using browser | 1. Open website of ParentBridge | N/A | User should be able to change pages by sliding right to left or click button | Unable to change page screen | Fail | Medium | 001.png |  | Solved | Front-End | Splash screen is removed
BR_002 | Splash Screen | Splash Screen | A blank space has been spotted on the splash screen. | User need to able to access website using browser | 1. Open website of ParentBridge | N/A | The screen should be filled with the necessary information. | A blank space has been noticed on the splash screen. | Fail | Medium | 002.png |  | Solved | Front-End | Splash screen is removed
BR_003 | Login | Forget Password | The forgot password section failed to display the correct error message. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on Forget Password | N/A | The error should clearly display the exact problem. | The user was not found in the database, and the system returned a 400 error code, which doesn’t seem accurate from the user’s side. | Fail | High | 003.png |  | Solved | Front-End
BR_004 | Signup | Signup | Failed to signup using google signin | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp | N/A | User should be able to signup through google signup | Unable to sign up using Google. | Fail | High | 004.png |  | Solved | Front-End
BR_005 | Signup | OTP | Able to signup with expired OTP | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp 4. Enter expired OTP and click on verify | USER CREDENTIAL | User shouldn’t be able to verify their login credentials using an expired OTP. | Users can verify their profile using an expired OTP. | Fail | High | 005.mp4 |  | Solved | Front-End
BR_006 | Onboarding | Onboarding | Secure route has not been implemented yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Goto /accout-setup route | USER CREDENTIAL | Users should not be allowed to change the route manually. | User can manually change the route, which could raise security concerns. | Fail | High | 006.mp4 |  | Solved | Front-End
BR_007 | Basic Info | Basic Info | The required mark on basic information should be displayed correctly. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | A required mark should be placed in the input field. | Required field are not mentioned. | Fail | Medium | 007.png |  | Solved | Front-End
BR_008 | Basic Info | Basic Info | Character limit hasn’t been implemented. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | The input field should allow users to enter only a limited number of characters. | Can enter an unlimited number of characters in the input field. | Fail | Low | 008.png |  | Solved | Front-End
BR_009 | Basic Info | Basic Info | Data validation problem in the basic information. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | Character field should only accept letters, while the number field should only accept numeric values. | Data input validation hasn’t been implemented. | Fail | High | 009.png |  | Solved | Front-End
BR_010 | Subscription | Subscription | Calculation error has been noticed in ParentBridge Pro plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information | USER CREDENTIAL | The price plan calculation needs to be accurate on the frontend. | Miscalculation in the monthly and yearly plan has been noticed. | Fail | High | 010.png | Add discount rate | Unsolved | Front-End | The whole pricing is controlled from the backend only.
BR_011 | Subscription | Subscription | Calculation error has been noticed in ParentBridge Pro Plus plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information | USER CREDENTIAL | The price plan calculation needs to be accurate on the frontend. | Miscalculation in the monthly and yearly plan has been noticed. | Fail | High | 011.png | Add discount rate | Unsolved | Front-End | The whole pricing is controlled from the backend only.
BR_012 | Subscription | Subscription | Can't buy the plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | Users should not encounter errors when purchasing a plan. | Unable to complete plan purchase | Fail | High | 012.png | Add discount rate | Solved | Front-End
BR_013 | Subscription | Subscription | Checkout page redirect to localhost url | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | After purchasing a plan, the user should be redirected to either the home page or the payment success page. | After purchasing a plan, the user wasn’t redirected to the home page or the payment success page. | Fail | High | 013.png |  | Solved
BR_014 | Home | Chat | A non-functional button has been noticed. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto chat | USER CREDENTIAL | The settings button and options should be accessible in the chat section. | Chat options are missing in the frontend. | Fail | Medium | 014.png |  | Solved | Front-End
BR_015 | Home | Home | Quick access settings button isn’t working. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto quick access section | USER CREDENTIAL | User should be able to set quick access manually | Quick access setup failed on the user’s side. | Fail | Medium | 015.png |  | Solved | Front-End
BR_016 | Home | Home | Failed to redirect user to calender | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto up comming events section | USER CREDENTIAL | User should be redirected to the desired page when clicking the quick access links | Could not redirect the user to the intended location. | Fail | High | 016.png |  | Solved | Front-End
BR_017 | Home | Calls | Unable to connect with co-parent | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto up comming events section | USER CREDENTIAL | Users should have the option to add co-parents right after creating an account or choose to add them later. | Couldn’t add a co-parent after setting up the account. | Fail | High | 017.png |  | Solved | Front-End, Back-End
BR_018 | Home | Calendar | Children are given default names whenever a different name is entered. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Should display the child's name that is entered. | Default child names are showing up even when they haven’t been entered. | Fail | Medium | 018.png |  | Solved | Front-End, Back-End
BR_019 | Home | Calendar | Can set an event in the past. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Users shouldn’t be able to mark past events on the calendar to avoid any misunderstanding issues. | User is able to set mark on past event | Fail | Medium | 019.png | Need to discuss this matter with client to avoid miss-understanding between co-parent | Unsolved | Back-End | If backend will fix this problem then in my frontend, it wont show the past event.
BR_020 | Home | Calendar | Calendar navigation arrow missing in the frontend | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | The calendar navigation arrow should be positioned to allow viewing of past events. | Missing navigation arrow in calendar | Fail | Medium | 020.png |  | Solved | Front-End
BR_021 | Home | Calendar | Date wise event view failed | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Event number under the date should be implemented according to the Figma requirements. | Event number under the date is missing on the frontend. | Fail | High | 021.png |  | Solved | Front-End
BR_022 | Home | Calendar | Failed to add holiday planner to calendar. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Users should be able to add a holiday planner to their calendar. | Couldn’t add the holiday planner to the calendar section. | Fail | High | 022.png |  | Solved | Front-End
BR_023 | Home | Documents | Can't upload document on the frontend. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | User should be able to upload a document without any issues. | Unable to upload document. | Fail | High | 023.png |  | Solved | Front-End | The images and the pdf is not showing in the website because backend is using local base url
BR_024 | Home | Calendar | All-day event toggle button is missing from the frontend. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender 5. Click on add event | USER CREDENTIAL | Feature should be available as shown in Figma. | All-day event button is missing in the frontend | Fail | High | 024.png |  | Solved | Front-End
BR_025 | Signup | Signup | Dull color theme of the signup button makes users think it’s not clickable. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp | N/A | Button color should be bright from the user's perspective. | Signup button uses a dull color. | Fail | Low | 025.png |  | Solved | Back-End | It is handled by backend
BR_026 | Subscription | Subscription | Yearly subscription failed on both plans. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | Users should be to purchase a monthly or yearly plan on both subscriptions without any issues. | Unable to complete the purchase of the yearly subscription for either. | Fail | High | 026.png |  | Solved | Back-End | It is handled by backend
BR_027 | Subscription | Subscription | After purchasing a plan, it should redirect to the home or dashboard page. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | After a successful purchase, the user should be redirected to the home or dashboard page. | Redirecting to the subscription page doesn’t make sense. | Fail | Medium | 027.png |  | Solved | Front-End
BR_028 | Subscription | Subscription | Purchased a yearly plan, but it shows that both the monthly and yearly plans are active. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | If the subscription card contains both monthly and yearly data, then when a user purchases a yearly plan, it should not display the current plan as active under the monthly data. | Displays both monthly and yearly plans as active on a single subscription card. | Fail | High | 028.png |  | Solved | Front-End
BR_029 | Settings | Profile Information | Email field missing in profile information tab | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on profile information | USER CREDENTIAL | Email field should be visible in the profile information. | Email name field is missing in the profile information section. | Fail | Medium | 029.png |  | Unsolved | Back-End | Email is not coming in profile api
BR_030 | Home | Settings | Logout button should be positioned in the left section. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings | USER CREDENTIAL | Logout button should be placed below the sidebar for convenient access. | Logout button is under setting tab | Fail | Medium | 030.png |  | Solved | Front-End
BR_031 | Home | Home | Responsiveness didn’t work. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials | USER CREDENTIAL | Web app should be responsive and adapt seamlessly to any device. | Sidebar failed to display responsive mode. | Fail | High | 031.png |  | Solved | Front-End
BR_032 | Settings | Profile Information | Co-parent's contact number is not showing up in the user’s co-parent information section. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on co-parent information | USER CREDENTIAL | Contact should be displayed in both parents' profiles | Co-parent’s profile is missing a contact number. | Fail | High | 032.png |  | Unsolved | Back-End | Backend, please check this issue because I am showing all the fields properly
BR_033 | Home | Expense | Placeholder text color blends with the background, making it hard to read. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Placeholder text should be in the opposite color of the background for better visibility and user understanding. | Background color and the placeholder text color are the same, making it difficult to read the text. | Fail | Medium | 033.png |  | Solved | Front-End
BR_034 | Home | Expense | Export feature hasn’t been added yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Export feature should be implemented according to the Figma design. | Export feature is missing on the web. | Fail | High | 034.png |  | Unsolved | Back-End | Export feature is not implmeneted in backend
BR_035 | Home | Expense | Parent and co-parent expenses are not displayed correctly. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Expenses should be displayed accurately. | Mismatch has been noticed between the parent and co-parent expense data. | Fail | High | 035.png |  | Unsolved | Back-End | Backend is not giving the data
BR_036 | Home | Expense | Display issue with the total expense calculation has been noticed. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Calculated amount should be accurately displayed. | Miscalculation has been spotted in the expense tab. | Fail | High | 036.png |  | Unsolved | Back-End | Backend needs to be fixed.
BR_037 | Settings | Profile Information | Name, state, and phone are typically required to create an account, but you can still set one up without them. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on co-parent information | USER CREDENTIAL | Profile setup page should include the required field. | Required fields are not being captured during profile setup. | Fail | High | 037.png |  | Unsolved |  | User cant create account without account setup
BR_038 | Settings | Help and Support | Call support is not integrated yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Call support button should be implemented flawlessly. | Call support feature hasn’t been set up yet. | Fail | High | 038.png |  | Unsolved |  | I need the support phone number
BR_039 | Settings | Help and Support | Email support hasn’t been set up yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Email support should be implemented precisely. | Feature hasn't been implemented yet. | Fail | High | 039.png |  | Unsolved |  | I need teh support email address
BR_040 | Settings | Help and Support | Live chat support hasn’t been set up yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Live chat support should be implemented precisely. | Feature hasn't been implemented yet. | Fail | High | 040.png |  | Solved |  | Its not in figma so I removed it
BR_041
BR_042
BR_043
BR_044

## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Basic Info | Basic Info | BR-001, BR-002, BR-003 | 3 | 7.50% | High: 1 Medium: 1 Low: 1
Home | Calendar | BR-004, BR-005, BR-006, BR-007, BR-008, BR-009 | 6 | 15.00% | High: 3 Medium: 3 Low: 0
Home | Calls | BR-010 | 1 | 2.50% | High: 1 Medium: 0 Low: 0
Home | Chat | BR-011 | 1 | 2.50% | High: 0 Medium: 1 Low: 0
Home | Documents | BR-012 | 1 | 2.50% | High: 1 Medium: 0 Low: 0
Home | Expense | BR-013, BR-014, BR-015, BR-016 | 4 | 10.00% | High: 3 Medium: 1 Low: 0
Home | Home | BR-017, BR-018, BR-019 | 3 | 7.50% | High: 2 Medium: 1 Low: 0
Home | Settings | BR-020 | 1 | 2.50% | High: 0 Medium: 1 Low: 0
Login | Forget Password | BR-021 | 1 | 2.50% | High: 1 Medium: 0 Low: 0
Onboarding | Onboarding | BR-022 | 1 | 2.50% | High: 1 Medium: 0 Low: 0
Settings | Help and Support | BR-023, BR-024, BR-025 | 3 | 7.50% | High: 3 Medium: 0 Low: 0
Settings | Profile Information | BR-026, BR-027, BR-028 | 3 | 7.50% | High: 2 Medium: 1 Low: 0
Signup | OTP | BR-029 | 1 | 2.50% | High: 1 Medium: 0 Low: 0
Signup | Signup | BR-030, BR-031 | 2 | 5.00% | High: 1 Medium: 0 Low: 1
Splash Screen | Splash Screen | BR-032, BR-033 | 2 | 5.00% | High: 0 Medium: 2 Low: 0
Subscription | Subscription | BR-034, BR-035, BR-036, BR-037, BR-038, BR-039, BR-040 |  |  | High: 6 Medium: 1 Low: 0

## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 26
Project URL: |  |  | Medium | 12
Developer: |  |  | Low | 2
OS:
Environment |  |  | Total Test Cases: | 40 | [8 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
|  |  | Test Case Solved : | 29
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment | Tester
BR-001 | Basic Info | Basic Info | The required mark on basic information should be displayed correctly. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | A required mark should be placed in the input field. | Required field are not mentioned. | Fail | Medium | 007.png |  | Solved | Front-End |  | Fahad
BR-002 | Basic Info | Basic Info | Character limit hasn’t been implemented. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | The input field should allow users to enter only a limited number of characters. | Can enter an unlimited number of characters in the input field. | Fail | Low | 008.png |  | Solved | Front-End |  | Fahad
BR-003 | Basic Info | Basic Info | Data validation problem in the basic information. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials | USER CREDENTIAL | Character field should only accept letters, while the number field should only accept numeric values. | Data input validation hasn’t been implemented. | Fail | High | 009.png |  | Solved | Front-End |  | Fahad
BR-004 | Home | Calendar | Children are given default names whenever a different name is entered. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Should display the child's name that is entered. | Default child names are showing up even when they haven’t been entered. | Fail | Medium | 018.png |  | Solved | Front-End, Back-End |  | Fahad
BR-005 | Home | Calendar | Can set an event in the past. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Users shouldn’t be able to mark past events on the calendar to avoid any misunderstanding issues. | User is able to set mark on past event | Fail | Medium | 019.png | Need to discuss this matter with client to avoid miss-understanding between co-parent | Unsolved | Back-End | If backend will fix this problem then in my frontend, it wont show the past event. | Fahad
BR-006 | Home | Calendar | Calendar navigation arrow missing in the frontend | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | The calendar navigation arrow should be positioned to allow viewing of past events. | Missing navigation arrow in calendar | Fail | Medium | 020.png |  | Solved | Front-End |  | Fahad
BR-007 | Home | Calendar | Date wise event view failed | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Event number under the date should be implemented according to the Figma requirements. | Event number under the date is missing on the frontend. | Fail | High | 021.png |  | Solved | Front-End |  | Fahad
BR-008 | Home | Calendar | Failed to add holiday planner to calendar. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | Users should be able to add a holiday planner to their calendar. | Couldn’t add the holiday planner to the calendar section. | Fail | High | 022.png |  | Solved | Front-End |  | Fahad
BR-009 | Home | Calendar | All-day event toggle button is missing from the frontend. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender 5. Click on add event | USER CREDENTIAL | Feature should be available as shown in Figma. | All-day event button is missing in the frontend | Fail | High | 024.png |  | Solved | Front-End |  | Fahad
BR-010 | Home | Calls | Unable to connect with co-parent | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto up comming events section | USER CREDENTIAL | Users should have the option to add co-parents right after creating an account or choose to add them later. | Couldn’t add a co-parent after setting up the account. | Fail | High | 017.png |  | Solved | Front-End, Back-End |  | Fahad
BR-011 | Home | Chat | A non-functional button has been noticed. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto chat | USER CREDENTIAL | The settings button and options should be accessible in the chat section. | Chat options are missing in the frontend. | Fail | Medium | 014.png |  | Solved | Front-End |  | Fahad
BR-012 | Home | Documents | Can't upload document on the frontend. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. Click on calender | USER CREDENTIAL | User should be able to upload a document without any issues. | Unable to upload document. | Fail | High | 023.png |  | Solved | Front-End | The images and the pdf is not showing in the website because backend is using local base url | Fahad
BR-013 | Home | Expense | Placeholder text color blends with the background, making it hard to read. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Placeholder text should be in the opposite color of the background for better visibility and user understanding. | Background color and the placeholder text color are the same, making it difficult to read the text. | Fail | Medium | 033.png |  | Solved | Front-End |  | Fahad
BR-014 | Home | Expense | Export feature hasn’t been added yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Export feature should be implemented according to the Figma design. | Export feature is missing on the web. | Fail | High | 034.png |  | Unsolved | Back-End | Export feature is not implmeneted in backend | Fahad
BR-015 | Home | Expense | Parent and co-parent expenses are not displayed correctly. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Expenses should be displayed accurately. | Mismatch has been noticed between the parent and co-parent expense data. | Fail | High | 035.png |  | Unsolved | Back-End | Backend is not giving the data | Fahad
BR-016 | Home | Expense | Display issue with the total expense calculation has been noticed. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on expense | USER CREDENTIAL | Calculated amount should be accurately displayed. | Miscalculation has been spotted in the expense tab. | Fail | High | 036.png |  | Unsolved | Back-End | Backend needs to be fixed. | Fahad
BR-017 | Home | Home | Quick access settings button isn’t working. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto quick access section | USER CREDENTIAL | User should be able to set quick access manually | Quick access setup failed on the user’s side. | Fail | Medium | 015.png |  | Solved | Front-End |  | Fahad
BR-018 | Home | Home | Failed to redirect user to calender | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credential 3. goto Home 4. goto up comming events section | USER CREDENTIAL | User should be redirected to the desired page when clicking the quick access links | Could not redirect the user to the intended location. | Fail | High | 016.png |  | Solved | Front-End |  | Fahad
BR-019 | Home | Home | Responsiveness didn’t work. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials | USER CREDENTIAL | Web app should be responsive and adapt seamlessly to any device. | Sidebar failed to display responsive mode. | Fail | High | 031.png |  | Solved | Front-End |  | Fahad
BR-020 | Home | Settings | Logout button should be positioned in the left section. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings | USER CREDENTIAL | Logout button should be placed below the sidebar for convenient access. | Logout button is under setting tab | Fail | Medium | 030.png |  | Solved | Front-End |  | Fahad
BR-021 | Login | Forget Password | The forgot password section failed to display the correct error message. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on Forget Password | N/A | The error should clearly display the exact problem. | The user was not found in the database, and the system returned a 400 error code, which doesn’t seem accurate from the user’s side. | Fail | High | 003.png |  | Solved | Front-End |  | Fahad
BR-022 | Onboarding | Onboarding | Secure route has not been implemented yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Goto /accout-setup route | USER CREDENTIAL | Users should not be allowed to change the route manually. | User can manually change the route, which could raise security concerns. | Fail | High | 006.mp4 |  | Solved | Front-End |  | Fahad
BR-023 | Settings | Help and Support | Call support is not integrated yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Call support button should be implemented flawlessly. | Call support feature hasn’t been set up yet. | Fail | High | 038.png |  | Unsolved |  | I need the support phone number | Fahad
BR-024 | Settings | Help and Support | Email support hasn’t been set up yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Email support should be implemented precisely. | Feature hasn't been implemented yet. | Fail | High | 039.png |  | Unsolved |  | I need teh support email address | Fahad
BR-025 | Settings | Help and Support | Live chat support hasn’t been set up yet. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on Help and Support | USER CREDENTIAL | Live chat support should be implemented precisely. | Feature hasn't been implemented yet. | Fail | High | 040.png |  | Solved |  | Its not in figma so I removed it | Fahad
BR-026 | Settings | Profile Information | Email field missing in profile information tab | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on profile information | USER CREDENTIAL | Email field should be visible in the profile information. | Email name field is missing in the profile information section. | Fail | Medium | 029.png |  | Unsolved | Back-End | Email is not coming in profile api | Fahad
BR-027 | Settings | Profile Information | Co-parent's contact number is not showing up in the user’s co-parent information section. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on co-parent information | USER CREDENTIAL | Contact should be displayed in both parents' profiles | Co-parent’s profile is missing a contact number. | Fail | High | 032.png |  | Unsolved | Back-End | Backend, please check this issue because I am showing all the fields properly | Fahad
BR-028 | Settings | Profile Information | Name, state, and phone are typically required to create an account, but you can still set one up without them. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Login using valid credentials 3. click on settings 4. click on co-parent information | USER CREDENTIAL | Profile setup page should include the required field. | Required fields are not being captured during profile setup. | Fail | High | 037.png |  | Unsolved |  | User cant create account without account setup | Fahad
BR-029 | Signup | OTP | Able to signup with expired OTP | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp 4. Enter expired OTP and click on verify | USER CREDENTIAL | User shouldn’t be able to verify their login credentials using an expired OTP. | Users can verify their profile using an expired OTP. | Fail | High | 005.mp4 |  | Solved | Front-End |  | Fahad
BR-030 | Signup | Signup | Failed to signup using google signin | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp | N/A | User should be able to signup through google signup | Unable to sign up using Google. | Fail | High | 004.png |  | Solved | Front-End |  | Fahad
BR-031 | Signup | Signup | Dull color theme of the signup button makes users think it’s not clickable. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Click on SignUp | N/A | Button color should be bright from the user's perspective. | Signup button uses a dull color. | Fail | Low | 025.png |  | Solved | Back-End | It is handled by backend | Fahad
BR-032 | Splash Screen | Splash Screen | "Next Button" is not implemented | User need to able to access website using browser | 1. Open website of ParentBridge | N/A | User should be able to change pages by sliding right to left or click button | Unable to change page screen | Fail | Medium | 001.png |  | Solved | Front-End | Splash screen is removed | Fahad
BR-033 | Splash Screen | Splash Screen | A blank space has been spotted on the splash screen. | User need to able to access website using browser | 1. Open website of ParentBridge | N/A | The screen should be filled with the necessary information. | A blank space has been noticed on the splash screen. | Fail | Medium | 002.png |  | Solved | Front-End | Splash screen is removed | Fahad
BR-034 | Subscription | Subscription | Calculation error has been noticed in ParentBridge Pro plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information | USER CREDENTIAL | The price plan calculation needs to be accurate on the frontend. | Miscalculation in the monthly and yearly plan has been noticed. | Fail | High | 010.png | Add discount rate | Unsolved | Front-End | The whole pricing is controlled from the backend only. | Fahad
BR-035 | Subscription | Subscription | Calculation error has been noticed in ParentBridge Pro Plus plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information | USER CREDENTIAL | The price plan calculation needs to be accurate on the frontend. | Miscalculation in the monthly and yearly plan has been noticed. | Fail | High | 011.png | Add discount rate | Unsolved | Front-End | The whole pricing is controlled from the backend only. | Fahad
BR-036 | Subscription | Subscription | Can't buy the plan | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | Users should not encounter errors when purchasing a plan. | Unable to complete plan purchase | Fail | High | 012.png | Add discount rate | Solved | Front-End |  | Fahad
BR-037 | Subscription | Subscription | Checkout page redirect to localhost url | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | After purchasing a plan, the user should be redirected to either the home page or the payment success page. | After purchasing a plan, the user wasn’t redirected to the home page or the payment success page. | Fail | High | 013.png |  | Solved |  |  | Fahad
BR-038 | Subscription | Subscription | Yearly subscription failed on both plans. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | Users should be to purchase a monthly or yearly plan on both subscriptions without any issues. | Unable to complete the purchase of the yearly subscription for either. | Fail | High | 026.png |  | Solved | Back-End | It is handled by backend | Fahad
BR-039 | Subscription | Subscription | After purchasing a plan, it should redirect to the home or dashboard page. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | After a successful purchase, the user should be redirected to the home or dashboard page. | Redirecting to the subscription page doesn’t make sense. | Fail | Medium | 027.png |  | Solved | Front-End |  | Fahad
BR-040 | Subscription | Subscription | Purchased a yearly plan, but it shows that both the monthly and yearly plans are active. | User need to able to access website using browser | 1. Open website of ParentBridge 2. Goto Login Page 3. Login using valid credentials 4. Fill up Basic information 5. Click next and goto subscription page | USER CREDENTIAL | If the subscription card contains both monthly and yearly data, then when a user purchases a yearly plan, it should not display the current plan as active under the monthly data. | Displays both monthly and yearly plans as active on a single subscription card. | Fail | High | 028.png |  | Solved | Front-End |  | Fahad