## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: | Text Humanizer Pro |  | High | 23
Project URL: | Vite + React |  | Medium | 19
Developer: | AI-Hunter |  | Low | 15
OS:
Environment |  |  | Total Test Cases: | 57
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Comment
BR-001 | Account | Profile | Names can be assigned using numbers. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 11224455 | Only characters should be allowed as input in the name text field. | Numbers can be used as names in the input field. | Fail | High | https://jam.dev/c/4e1b9c45-87e4-4ae3-8ad0-ae76185986e5 |  | Fahad
BR-002 | Account | Security | Forget password button in change password | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | The change password page will include fields for the old password, the new password, and a confirmation for the new password. | The "Forgot Password" button appears on the change password page, which seems irrelevant. | Fail | Medium | https://jam.dev/c/b2451410-1448-4214-adbd-fff9ab827ae1 |  | Fahad | Solved
BR-003 | Admin | AI Detection | The decimal number has too many digits after the point. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | Two decimal places after the point are more representative than a long number. | A long number after the decimal point has been observed. | Fail | Low | https://jam.dev/c/24b4d25f-a7bc-4aa7-b9ac-7324b6be8a80 |  | Fahad | Solved
BR-004 | Admin | AI Detection | Failed to show the precise log number. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | The log number needs to be displayed accurately. | Failed to show the correct log number along with the page number. | Fail | Medium | https://jam.dev/c/12d5a7f3-9c12-469b-903c-c20a1aab2303 |  | Fahad
BR-005 | Admin | AI Detection | The table is missing a sort option. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | The sort option should be positioned and function as per the client's expectations. | The sort option for AI score and human score is missing. | Fail | Medium | https://jam.dev/c/f8f8414e-1535-46f8-9537-39de2ed744e0 |  | Fahad
BR-006 | Admin | Billing | Failed to add plan | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | The admin should have the ability to add a plan, and it should be displayed appropriately. | Failed to display the new plan in the web app after the admin successfully added it. | Fail | High | https://jam.dev/c/802585ee-00fe-4689-a0b4-4abde002a49b | Add an alert message in the word input section when the admin enters a negative value. | Fahad
BR-007 | Admin | Billing | The actions in the billing section are missing in the web app. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | For the admin to take action on different logs, the action button should be visible and function appropriately. | The action button is missing in the billing section. | Fail | High | https://jam.dev/c/d497f137-0fd8-4848-a51f-059672a66e3c |  | Fahad
BR-008 | Admin | Billing | Details of the payment action are missing. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | For a refund or any clarification, it’s essential to check the payment details and take action in the billing section. | The missing details button has been observed in the billing section. | Fail | High | https://jam.dev/c/3fff5928-ed50-46d7-9bc3-9fb2c018e93a |  | Fahad
BR-009 | Admin | Billing | Can set negative values for price and word limit input fields | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | Admins shouldn't be allowed to set negative values for price or word limit. | Can set negetive value in the price and word limit field | Fail | High | https://jam.dev/c/998afa60-b9b1-4558-844d-9837b0cbaa08 |  | Fahad
BR-010 | Admin | Dashboard | The admin's greeting appears on every page. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Greetings should be included only on the overview page, not on other pages. | Admin greetings are displayed on every page. | Fail | Low | https://jam.dev/c/3abc6c28-1e7b-4be9-a042-43b13a81021e |  | Fahad
BR-011 | Admin | Dashboard | The text format is different. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The format and alignment should match the client's requirements. | A different font style has been observed. | Fail | Low | https://jam.dev/c/31bd5727-8f95-40eb-91b6-33a00d096df8 |  | Fahad
BR-012 | Admin | Dashboard | Hovering over the curve does not display the percentage. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Hovering over the percentage should display the specific day and the amount reached on that day. | Hovering over the curve does not display the percentage rate and the date as shown in the Figma design. | Fail | Medium | https://jam.dev/c/4f992d96-8219-4166-846b-53fa43778baf |  | Fahad
BR-013 | Admin | Dashboard | Issue with alignment. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Alignment and design should match the client's requirements. | The percentage value in the chart is not centered properly, indicating an alignment issue. Additionally, it does not match the original design. | Fail | Medium | https://jam.dev/c/e2182ce8-724f-48a8-b40e-91a04bea3f94 |  | Fahad
BR-014 | Admin | Dashboard | The module flow doesn't align with the client design. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The module flow should align with the client's requirements. | A difference between the web app and client requirements has been noticed. | Fail | Medium | https://jam.dev/c/4ad01c00-0540-49ab-bb9a-8dd564b26069 |  | Fahad
BR-015 | Admin | Dashboard | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/6f613b67-78b9-45af-8fea-6f61658ff8a2 |  | Fahad
BR-016 | Admin | Dashboard | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/10d0f972-3b02-454f-83a0-e444a6615e1d |  | Fahad
BR-017 | Admin | Dashboard | Content missing from performance metrics. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | All client content should be displayed in the performance metrics section. | Some key point appears to be missing in the performance metrics section. | Fail | Medium | https://jam.dev/c/ab410a86-100c-4b63-9868-a0d4c84c6edc |  | Fahad
BR-018 | Admin | Edit Cards | Unable to capture the entire content in the banner when the text is large. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Edit Card section | Admin Credentials | The content should be placed within the banner. | Content is too large and extends beyond the banner. | Fail | Medium | https://jam.dev/c/702c357b-0e76-4c42-8c4d-61f44184f1ab |  | Fahad
BR-019 | Admin | Email Subscriber | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/02772a6b-4f1f-4abb-9e09-e406ab1c29a5 |  | Fahad
BR-020 | Admin | Email Subscriber | Send newsletter button missing | User need to be in browser | 1. SignIn by admin credentials 2. Goto Email Subscriber | Admin Credentials | All necessary buttons provided by the client should be visible and functioning properly. | The missing "Send Newsletter" button has been noticed in the email subscription section. | Fail | High | https://jam.dev/c/9e7fd9b0-25ff-430a-86eb-fd2483802f6f |  | Fahad
BR-021 | Admin | Email Subscriber | Page number is not static | User need to be in browser | 1. SignIn by admin credentials 2. Goto Email Subscriber | Admin Credentials | The page number bar needs to remain static. | Number jumps have been observed when clicking to navigate to that page, and it does not remain static. | Fail | Medium | https://jam.dev/c/b4a7316e-fd84-47c2-bd5c-624449515ea5 |  | Fahad
BR-022 | Admin | Humanization | Table headers need to be bold. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | Headers should be bold | Header and content font same | Fail | Low | https://jam.dev/c/cabc749b-18ff-4d24-925e-f5419441a31a |  | Fahad
BR-023 | Admin | Humanization | The result shows the wrong number. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | The web app should display accurate data. | The web app failed to display accurate data. | Fail | Low | https://jam.dev/c/1a60216f-ecc5-4e9a-843e-9c16241085bc |  | Fahad
BR-024 | Admin | Humanization | The table content couldn't be loaded. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | Content should appear when the user navigates to the next page of the table. | The content failed to load when the user clicked on "Next" in the table, and all the content remained unchanged. | Fail | High | https://jam.dev/c/dcf3f184-3464-4834-b684-184d72e15dbc |  | Fahad
BR-025 | Admin | Humanization | The filter UI does not match the client's requirements. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | The design and alignment should match the client's requirements. | A different layout has been observed, which does not align with the client's requirements. | Fail | Low | https://jam.dev/c/ec007a0d-15ad-457b-bf1f-9569536517ef |  | Fahad
BR-026 | Admin | Settings | User image and name alignment issue | User need to be in browser | 1. SignIn by admin credentials 2. Goto setting section | Admin Credentials | The user image change icon and name change icon should be positioned accurately, ensuring they are not placed in a congested manner. | The camera logo is positioned too close to the user profile picture, and the change name feature lacks visual appeal. | Fail | Low | https://jam.dev/c/b88450ed-1ed8-4ede-b646-a13d1ca48918 |  | Fahad
BR-027 | Admin | User Management | Convert to a scrollable table after clicking on the last data action button. | User need to be in browser | 1. SignIn by admin credentials 2. Goto User Management section | Admin Credentials | When clicking on the action of the last data, the action content should pop upward. | The action content moved beneath the log, making the table scrollable. | Fail | Medium | https://jam.dev/c/84cd6bbf-b187-4662-949c-69ddd509006e |  | Fahad
BR-028 | Dashboard | Dashboard | Unable to display the user's word count. | User need to be in browser | 1. Open web app | N/A | Users should be able to see how many words they have used. | Unable to display the word used in the dashboard. | Fail | High | https://jam.dev/c/a80ccb95-52d7-4c27-a88d-856ba5635488 |  | Fahad
BR-029 | Dashboard | Dashboard | The AI detection bar malfunctioned. | User need to be in browser | 1. Open web app | N/A | The AI detection bar should be filled based on the level of similarity detected with AI. | Failed to fill the AI bar on the dashboard page. | Fail | High | https://jam.dev/c/bec88c6d-9cac-48d5-a53d-6077b582aba4 |  | Fahad
BR-030 | Dashboard | Dashboard | AI detection failed | User need to be in browser | 1. Open web app | N/A | If a text is generated by AI, it should indicate that it was created using artificial intelligence. | The displayed text appears to be himazine, but it was actually generated by AI. | Fail | High | https://jam.dev/c/a091e244-6fa8-4000-aeab-717f51a5d628 |  | Fahad
BR-031 | Dashboard | Dashboard | Failed to make the text more relatable. | User need to be in browser | 1. Open web app | N/A | When users paste their text, the generation should be done properly based on the category. | Failed to correct the generation. Simply adding "ing" to words doesn't make the text sound humanized by AI. | Fail | High | https://jam.dev/c/83902d8d-9afa-4a55-bcc4-3f7ca8e84a59 |  | Fahad
BR-032 | Dashboard | Dashboard | The copy prompt doesn't show up when clicked. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | When the user clicks the copy button, a prompt should appear with the message "Copied to clipboard." | No message appears when the copy button is clicked. | Fail | High | https://jam.dev/c/a4b1ae10-d607-4098-ac1d-a271c212a4a5 |  | Fahad
BR-033 | Landing Page | Header | The logo appears to be a bit small. | User need to be in web browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been observed in the homepage header section. | Fail | Low | https://jam.dev/c/627db0fc-28db-436f-a1b2-d1b8cc923450 |  | Fahad
BR-034 | Landing Page | Header | Header section size issue | User need to be in browser | 1. Open web app | N/A | The header section size should match the client's requirements exactly. | The header section appears to be smaller than the client's requirements. | Fail | Low | https://jam.dev/c/01c7fc2b-8290-4158-832a-562137b55e28 |  | Fahad
BR-035 | Landing Page | Home | Text font and color issue | User need to be in browser | 1. Open web app | N/A | The font and color should match the client's requirements. | The font size and text color do not match the client's requirements. | Fail | Low | https://jam.dev/c/2637688e-9f2a-4a43-9490-d77286dc7be0 |  | Fahad
BR-036 | Landing Page | Home | The icon size is smaller than the client's requirement. | User need to be in browser | 1. Open web app | N/A | The alignment and font should match the client's requirements. | The icon appears to be smaller than the client's requirement. | Fail | Low | https://jam.dev/c/9f5b1842-a1c3-4bd6-a0f0-b4e3cf772daf |  | Fahad
BR-037 | Landing Page | Home | Content of SEO Agency banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/8f1ec445-48c1-43a2-99a3-8ae5b5b900a3 |  | Fahad
BR-038 | Landing Page | Home | Content of Student banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/12e60943-b415-4bc0-9433-6002453d7a32 |  | Fahad
BR-039 | Landing Page | Home | Content of Marketer banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/adc197c5-b754-498f-932e-33c1eaaccf48 |  | Fahad
BR-040 | Landing Page | Home | Content of Content Creator banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/4099e7d9-2aef-4774-bbbd-84d4ac4e3fb0 |  | Fahad
BR-041 | Landing Page | Home | Content of Resume/CV banner context missing in client requirement | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/b681f39d-9576-4240-9220-348dc31d9092 |  | Fahad
BR-042 | Pricing | Pricing | Banner content missing | User need to be in browser | 1. Open web app | N/A | Pricing content should align exactly with the client's requirements. | The pricing category and banner content don't align with the client's specifications. | Fail | High | https://jam.dev/c/beb7985c-b9ce-4279-966f-8ddb524c65f7 |  | Fahad
BR-043 | Pricing | Pricing | Popular subscription package is not appearing. | User need to be in browser | 1. Open web app | N/A | The popular package should be highlighted on the price banner to help customers find the best deal. | The popular package is not appearing in the price banner as per the client's requirement. | Fail | Medium | https://jam.dev/c/ac834272-815f-4f86-9bc8-5a025791cb6c |  | Fahad
BR-044 | Pricing | Pricing | Design and alignment problem. | User need to be in browser | 1. Open web app | N/A | Design and alignment should match the client's requirements. | A different design has been noticed in the web app. | Fail | Medium | https://jam.dev/c/7b0d1360-907f-477d-aa18-29bfa019046d |  | Fahad
BR-045 | Pricing | Pricing | Delay in the price indicator. | User need to be in browser | 1. Open web app | N/A | A dynamic response in the web app can greatly enhance client attraction. | A delay in the price bar has been observed when the user adjusts the amount by sliding the bar. | Fail | High | https://jam.dev/c/2cd07e41-ee68-4520-8712-f3cbd9183201 |  | Fahad
BR-046 | Pricing | Pricing | The web app failed to load after completing the payment successfully. | User need to be in browser | 1. Open web app 2. Select price range and confirm payment | N/A | The user should be redirected to the home page after successfully purchasing the subscription. | Connection failed after successfully completing the subscription purchase. | Fail | High | https://jam.dev/c/c7d813c8-8ce3-411a-90a6-7d3a34ecabb5 |  | Fahad
BR-047 | Pricing | Pricing | Enterprise banner is missing. | User need to be in browser | 1. Open web app | N/A | Enterprise subscription should be accessible and visible in the web app. | The missing enterprise banner in the web app has been noticed. | Fail | High | https://jam.dev/c/bbef7505-46f7-40b3-9f5e-dafa0ea62449 |  | Fahad
BR-048 | Pricing | Pricing | Design and alignment issue | User need to be in browser | 1. Open web app | N/A | The design and alignment should match the client's requirements. | A different design has been noticed in the web app, which does not align with the client's requirements. | Fail | Medium | https://jam.dev/c/4afe52c8-6143-400d-93e4-ac8532486fb7 |  | Fahad
BR-049 | Pricing | Pricing | Discount percentage missing | User need to be in browser | 1. Open web app | N/A | The subscription banner should display the discount percentage. | The discount price is displayed, but the percentage isn’t shown in the top corner of the banner. | Fail | Medium | https://jam.dev/c/ecb91c2f-c915-4fce-9730-a06d161d0484 |  | Fahad
BR-050 | Signup | Data Policy | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the data policy, and it needs to be accurate. | The content for the data policy is missing. | Fail | High | https://jam.dev/c/98dd060c-576d-4923-a95c-a990d46ecfd6 |  | Fahad
BR-051 | Signup | Signup | Logo seems to be small | User need to be in browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been noticed on the signup page. | Fail | Low | https://jam.dev/c/1c564669-c315-4a2a-a02f-602b9132f7d5 |  | Fahad
BR-052 | Signup | Signup | Missing the option to sign up with Apple ID. | User need to be in browser | 1. Open web app | N/A | The user should be able to signup using two methods as per the client's requirement. | Missing Apple ID signup method on the signup page. | Fail | High | https://jam.dev/c/df41064e-6b9b-4503-907e-1cd628585d14 |  | Fahad
BR-053 | Signup | Signup | Failed to login with google | User need to be in browser | 1. Open web app | N/A | Users should be able to log in or sign up with their Google account. | Unable to log in or sign up with a Google account. | Fail | High | https://jam.dev/c/bcc54832-a96c-43df-a08e-750eab7e0b76 |  | Fahad
BR-054 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | All inputs in the sign-in and sign-up fields should function flawlessly as intended. | Failed to sign up after entering the password, and even after updating it to meet the requirements, the issue persisted. | Fail | High | https://jam.dev/c/507d8b86-ee98-4b3f-9f77-f04863f8ed7e |  | Fahad
BR-055 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | A password should meet the requirements of being at least 8 characters long and including a combination of symbols, letters, and numbers. | Password met the requirements but the signup process failed. | Fail | High | https://jam.dev/c/a003c45b-c55e-42b9-979d-06098fd87c27 |  | Fahad
BR-056 | Signup | Signup | Terms of Use and Privacy Policy button failed | User need to be in browser | 1. Open web app | N/A | After entering the registration credentials, the user needs to click on the Terms of Use and Privacy button. Then, they can proceed by clicking the signup button. | The user can submit the form without selecting the terms of use and privacy policy button. | Fail | High | https://jam.dev/c/7eb55e28-96e5-44bd-9f8b-1d20f5ff389c |  | Fahad
BR-057 | Signup | Terms and use | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the terms and use, and it needs to be accurate. | The content for the terms and use is missing. | Fail | High | https://jam.dev/c/0d7a142d-483b-4d1c-ae79-9696bfda932a |  | Fahad

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Text Humanizer Pro
Developer: | AI - Hunter
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
BR_001 | Landing Page | Header | The logo appears to be a bit small. | User need to be in web browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been observed in the homepage header section. | Fail | Low | https://jam.dev/c/627db0fc-28db-436f-a1b2-d1b8cc923450
BR_002 | Landing Page | Header | Header section size issue | User need to be in browser | 1. Open web app | N/A | The header section size should match the client's requirements exactly. | The header section appears to be smaller than the client's requirements. | Fail | Low | https://jam.dev/c/01c7fc2b-8290-4158-832a-562137b55e28
BR_003 | Landing Page | Home | Text font and color issue | User need to be in browser | 1. Open web app | N/A | The font and color should match the client's requirements. | The font size and text color do not match the client's requirements. | Fail | Low | https://jam.dev/c/2637688e-9f2a-4a43-9490-d77286dc7be0
BR_004 | Landing Page | Home | The icon size is smaller than the client's requirement. | User need to be in browser | 1. Open web app | N/A | The alignment and font should match the client's requirements. | The icon appears to be smaller than the client's requirement. | Fail | Low | https://jam.dev/c/9f5b1842-a1c3-4bd6-a0f0-b4e3cf772daf
BR_005 | Landing Page | Home | Content of SEO Agency banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/8f1ec445-48c1-43a2-99a3-8ae5b5b900a3
BR_006 | Landing Page | Home | Content of Student banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/12e60943-b415-4bc0-9433-6002453d7a32
BR_007 | Landing Page | Home | Content of Marketer banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/adc197c5-b754-498f-932e-33c1eaaccf48
BR_008 | Landing Page | Home | Content of Content Creator banner hold different context | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/4099e7d9-2aef-4774-bbbd-84d4ac4e3fb0
BR_009 | Landing Page | Home | Content of Resume/CV banner context missing in client requirement | User need to be in browser | 1. Open web app | N/A | Banner content should match the client's requirements exactly. | A difference in the banner content has been noticed. | Fail | Medium | https://jam.dev/c/b681f39d-9576-4240-9220-348dc31d9092
BR_010 | Signup | Signup | Logo seems to be small | User need to be in browser | 1. Open web app | N/A | A website logo should grab users' attention and be visually appealing. | A small-sized logo has been noticed on the signup page. | Fail | Low | https://jam.dev/c/1c564669-c315-4a2a-a02f-602b9132f7d5
BR_011 | Signup | Signup | Missing the option to sign up with Apple ID. | User need to be in browser | 1. Open web app | N/A | The user should be able to signup using two methods as per the client's requirement. | Missing Apple ID signup method on the signup page. | Fail | High | https://jam.dev/c/df41064e-6b9b-4503-907e-1cd628585d14
BR_012 | Signup | Data Policy | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the data policy, and it needs to be accurate. | The content for the data policy is missing. | Fail | High | https://jam.dev/c/98dd060c-576d-4923-a95c-a990d46ecfd6
BR_013 | Signup | Terms and use | Original content missing | User need to be in browser | 1. Open web app | N/A | The client should provide the terms and use, and it needs to be accurate. | The content for the terms and use is missing. | Fail | High | https://jam.dev/c/0d7a142d-483b-4d1c-ae79-9696bfda932a
BR_014 | Signup | Signup | Failed to login with google | User need to be in browser | 1. Open web app | N/A | Users should be able to log in or sign up with their Google account. | Unable to log in or sign up with a Google account. | Fail | High | https://jam.dev/c/bcc54832-a96c-43df-a08e-750eab7e0b76
BR_015 | Pricing | Pricing | Banner content missing | User need to be in browser | 1. Open web app | N/A | Pricing content should align exactly with the client's requirements. | The pricing category and banner content don't align with the client's specifications. | Fail | High | https://jam.dev/c/beb7985c-b9ce-4279-966f-8ddb524c65f7
BR_016 | Pricing | Pricing | Popular subscription package is not appearing. | User need to be in browser | 1. Open web app | N/A | The popular package should be highlighted on the price banner to help customers find the best deal. | The popular package is not appearing in the price banner as per the client's requirement. | Fail | Medium | https://jam.dev/c/ac834272-815f-4f86-9bc8-5a025791cb6c
BR_017 | Pricing | Pricing | Design and alignment problem. | User need to be in browser | 1. Open web app | N/A | Design and alignment should match the client's requirements. | A different design has been noticed in the web app. | Fail | Medium | https://jam.dev/c/7b0d1360-907f-477d-aa18-29bfa019046d
BR_018 | Pricing | Pricing | Delay in the price indicator. | User need to be in browser | 1. Open web app | N/A | A dynamic response in the web app can greatly enhance client attraction. | A delay in the price bar has been observed when the user adjusts the amount by sliding the bar. | Fail | High | https://jam.dev/c/2cd07e41-ee68-4520-8712-f3cbd9183201
BR_019 | Pricing | Pricing | The web app failed to load after completing the payment successfully. | User need to be in browser | 1. Open web app 2. Select price range and confirm payment | N/A | The user should be redirected to the home page after successfully purchasing the subscription. | Connection failed after successfully completing the subscription purchase. | Fail | High | https://jam.dev/c/c7d813c8-8ce3-411a-90a6-7d3a34ecabb5
BR_020 | Pricing | Pricing | Enterprise banner is missing. | User need to be in browser | 1. Open web app | N/A | Enterprise subscription should be accessible and visible in the web app. | The missing enterprise banner in the web app has been noticed. | Fail | High | https://jam.dev/c/bbef7505-46f7-40b3-9f5e-dafa0ea62449
BR_021 | Pricing | Pricing | Design and alignment issue | User need to be in browser | 1. Open web app | N/A | The design and alignment should match the client's requirements. | A different design has been noticed in the web app, which does not align with the client's requirements. | Fail | Medium | https://jam.dev/c/4afe52c8-6143-400d-93e4-ac8532486fb7
BR_022 | Pricing | Pricing | Discount percentage missing | User need to be in browser | 1. Open web app | N/A | The subscription banner should display the discount percentage. | The discount price is displayed, but the percentage isn’t shown in the top corner of the banner. | Fail | Medium | https://jam.dev/c/ecb91c2f-c915-4fce-9730-a06d161d0484
BR_023 | Dashboard | Dashboard | Unable to display the user's word count. | User need to be in browser | 1. Open web app | N/A | Users should be able to see how many words they have used. | Unable to display the word used in the dashboard. | Fail | High | https://jam.dev/c/a80ccb95-52d7-4c27-a88d-856ba5635488
BR_024 | Dashboard | Dashboard | The AI detection bar malfunctioned. | User need to be in browser | 1. Open web app | N/A | The AI detection bar should be filled based on the level of similarity detected with AI. | Failed to fill the AI bar on the dashboard page. | Fail | High | https://jam.dev/c/bec88c6d-9cac-48d5-a53d-6077b582aba4
BR_025 | Dashboard | Dashboard | AI detection failed | User need to be in browser | 1. Open web app | N/A | If a text is generated by AI, it should indicate that it was created using artificial intelligence. | The displayed text appears to be himazine, but it was actually generated by AI. | Fail | High | https://jam.dev/c/a091e244-6fa8-4000-aeab-717f51a5d628
BR_026 | Dashboard | Dashboard | Failed to make the text more relatable. | User need to be in browser | 1. Open web app | N/A | When users paste their text, the generation should be done properly based on the category. | Failed to correct the generation. Simply adding "ing" to words doesn't make the text sound humanized by AI. | Fail | High | https://jam.dev/c/83902d8d-9afa-4a55-bcc4-3f7ca8e84a59
BR_027 | Account | Profile | Names can be assigned using numbers. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 11224455 | Only characters should be allowed as input in the name text field. | Numbers can be used as names in the input field. | Fail | High | https://jam.dev/c/4e1b9c45-87e4-4ae3-8ad0-ae76185986e5
BR_028 | Account | Security | Forget password button in change password | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | The change password page will include fields for the old password, the new password, and a confirmation for the new password. | The "Forgot Password" button appears on the change password page, which seems irrelevant. | Fail | Medium | https://jam.dev/c/b2451410-1448-4214-adbd-fff9ab827ae1
BR_029 | Dashboard | Dashboard | The copy prompt doesn't show up when clicked. | User need to be in browser | 1. Open web app | cavowog889@kwifa.com pass: 112244557788 | When the user clicks the copy button, a prompt should appear with the message "Copied to clipboard." | No message appears when the copy button is clicked. | Fail | High | https://jam.dev/c/a4b1ae10-d607-4098-ac1d-a271c212a4a5
BR_030 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | All inputs in the sign-in and sign-up fields should function flawlessly as intended. | Failed to sign up after entering the password, and even after updating it to meet the requirements, the issue persisted. | Fail | High | https://jam.dev/c/507d8b86-ee98-4b3f-9f77-f04863f8ed7e
BR_031 | Signup | Signup | Password indicator failed | User need to be in browser | 1. Open web app | N/A | A password should meet the requirements of being at least 8 characters long and including a combination of symbols, letters, and numbers. | Password met the requirements but the signup process failed. | Fail | High | https://jam.dev/c/a003c45b-c55e-42b9-979d-06098fd87c27
BR_032 | Signup | Signup | Terms of Use and Privacy Policy button failed | User need to be in browser | 1. Open web app | N/A | After entering the registration credentials, the user needs to click on the Terms of Use and Privacy button. Then, they can proceed by clicking the signup button. | The user can submit the form without selecting the terms of use and privacy policy button. | Fail | High | https://jam.dev/c/7eb55e28-96e5-44bd-9f8b-1d20f5ff389c
BR_033 | Admin | Dashboard | The admin's greeting appears on every page. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Greetings should be included only on the overview page, not on other pages. | Admin greetings are displayed on every page. | Fail | Low | https://jam.dev/c/3abc6c28-1e7b-4be9-a042-43b13a81021e
BR_034 | Admin | Dashboard | The text format is different. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The format and alignment should match the client's requirements. | A different font style has been observed. | Fail | Low | https://jam.dev/c/31bd5727-8f95-40eb-91b6-33a00d096df8
BR_035 | Admin | Dashboard | Hovering over the curve does not display the percentage. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Hovering over the percentage should display the specific day and the amount reached on that day. | Hovering over the curve does not display the percentage rate and the date as shown in the Figma design. | Fail | Medium | https://jam.dev/c/4f992d96-8219-4166-846b-53fa43778baf
BR_036 | Admin | Dashboard | Issue with alignment. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | Alignment and design should match the client's requirements. | The percentage value in the chart is not centered properly, indicating an alignment issue. Additionally, it does not match the original design. | Fail | Medium | https://jam.dev/c/e2182ce8-724f-48a8-b40e-91a04bea3f94
BR_037 | Admin | Dashboard | The module flow doesn't align with the client design. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The module flow should align with the client's requirements. | A difference between the web app and client requirements has been noticed. | Fail | Medium | https://jam.dev/c/4ad01c00-0540-49ab-bb9a-8dd564b26069
BR_038 | Admin | Dashboard | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/6f613b67-78b9-45af-8fea-6f61658ff8a2
BR_039 | Admin | Dashboard | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/10d0f972-3b02-454f-83a0-e444a6615e1d
BR_040 | Admin | Dashboard | Content missing from performance metrics. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | All client content should be displayed in the performance metrics section. | Some key point appears to be missing in the performance metrics section. | Fail | Medium | https://jam.dev/c/ab410a86-100c-4b63-9868-a0d4c84c6edc
BR_041 | Admin | Email Subscriber | The design doesn't align with the client's requirements. | User need to be in browser | 1. SignIn by admin credentials | Admin Credentials | The design and alignment should match the client's requirements. | The design differs from the client's requirements. | Fail | Low | https://jam.dev/c/02772a6b-4f1f-4abb-9e09-e406ab1c29a5
BR_042 | Admin | Email Subscriber | Send newsletter button missing | User need to be in browser | 1. SignIn by admin credentials 2. Goto Email Subscriber | Admin Credentials | All necessary buttons provided by the client should be visible and functioning properly. | The missing "Send Newsletter" button has been noticed in the email subscription section. | Fail | High | https://jam.dev/c/9e7fd9b0-25ff-430a-86eb-fd2483802f6f
BR_043 | Admin | Email Subscriber | Page number is not static | User need to be in browser | 1. SignIn by admin credentials 2. Goto Email Subscriber | Admin Credentials | The page number bar needs to remain static. | Number jumps have been observed when clicking to navigate to that page, and it does not remain static. | Fail | Medium | https://jam.dev/c/b4a7316e-fd84-47c2-bd5c-624449515ea5
BR_044 | Admin | AI Detection | The decimal number has too many digits after the point. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | Two decimal places after the point are more representative than a long number. | A long number after the decimal point has been observed. | Fail | Low | https://jam.dev/c/24b4d25f-a7bc-4aa7-b9ac-7324b6be8a80
BR_045 | Admin | AI Detection | Failed to show the precise log number. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | The log number needs to be displayed accurately. | Failed to show the correct log number along with the page number. | Fail | Medium | https://jam.dev/c/12d5a7f3-9c12-469b-903c-c20a1aab2303
BR_046 | Admin | AI Detection | The table is missing a sort option. | User need to be in browser | 1. SignIn by admin credentials 2. Goto AI Detection | Admin Credentials | The sort option should be positioned and function as per the client's expectations. | The sort option for AI score and human score is missing. | Fail | Medium | https://jam.dev/c/f8f8414e-1535-46f8-9537-39de2ed744e0
BR_047 | Admin | Humanization | Table headers need to be bold. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | Headers should be bold | Header and content font same | Fail | Low | https://jam.dev/c/cabc749b-18ff-4d24-925e-f5419441a31a
BR_048 | Admin | Humanization | The result shows the wrong number. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | The web app should display accurate data. | The web app failed to display accurate data. | Fail | Low | https://jam.dev/c/1a60216f-ecc5-4e9a-843e-9c16241085bc
BR_049 | Admin | Humanization | The table content couldn't be loaded. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | Content should appear when the user navigates to the next page of the table. | The content failed to load when the user clicked on "Next" in the table, and all the content remained unchanged. | Fail | High | https://jam.dev/c/dcf3f184-3464-4834-b684-184d72e15dbc
BR_050 | Admin | Humanization | The filter UI does not match the client's requirements. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Humanization | Admin Credentials | The design and alignment should match the client's requirements. | A different layout has been observed, which does not align with the client's requirements. | Fail | Low | https://jam.dev/c/ec007a0d-15ad-457b-bf1f-9569536517ef
BR_051 | Admin | Billing | Failed to add plan | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | The admin should have the ability to add a plan, and it should be displayed appropriately. | Failed to display the new plan in the web app after the admin successfully added it. | Fail | High | https://jam.dev/c/802585ee-00fe-4689-a0b4-4abde002a49b | Add an alert message in the word input section when the admin enters a negative value.
BR_052 | Admin | Billing | The actions in the billing section are missing in the web app. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | For the admin to take action on different logs, the action button should be visible and function appropriately. | The action button is missing in the billing section. | Fail | High | https://jam.dev/c/d497f137-0fd8-4848-a51f-059672a66e3c
BR_053 | Admin | Billing | Details of the payment action are missing. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | For a refund or any clarification, it’s essential to check the payment details and take action in the billing section. | The missing details button has been observed in the billing section. | Fail | High | https://jam.dev/c/3fff5928-ed50-46d7-9bc3-9fb2c018e93a
BR_054 | Admin | User Management | Convert to a scrollable table after clicking on the last data action button. | User need to be in browser | 1. SignIn by admin credentials 2. Goto User Management section | Admin Credentials | When clicking on the action of the last data, the action content should pop upward. | The action content moved beneath the log, making the table scrollable. | Fail | Medium | https://jam.dev/c/84cd6bbf-b187-4662-949c-69ddd509006e
BR_055 | Admin | Billing | Can set negative values for price and word limit input fields | User need to be in browser | 1. SignIn by admin credentials 2. Goto Billing section | Admin Credentials | Admins shouldn't be allowed to set negative values for price or word limit. | Can set negetive value in the price and word limit field | Fail | High | https://jam.dev/c/998afa60-b9b1-4558-844d-9837b0cbaa08
BR_056 | Admin | Edit Cards | Unable to capture the entire content in the banner when the text is large. | User need to be in browser | 1. SignIn by admin credentials 2. Goto Edit Card section | Admin Credentials | The content should be placed within the banner. | Content is too large and extends beyond the banner. | Fail | Medium | https://jam.dev/c/702c357b-0e76-4c42-8c4d-61f44184f1ab
BR_057 | Admin | Settings | User image and name alignment issue | User need to be in browser | 1. SignIn by admin credentials 2. Goto setting section | Admin Credentials | The user image change icon and name change icon should be positioned accurately, ensuring they are not placed in a congested manner. | The camera logo is positioned too close to the user profile picture, and the change name feature lacks visual appeal. | Fail | Low | https://jam.dev/c/b88450ed-1ed8-4ede-b646-a13d1ca48918
BR_058
BR_059
BR_060
BR_061
BR_062
BR_063
BR_064

## Tahsin
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Account | Profile | BR-001 | 1 | 1.75% | High: 1 Medium: 0 Low: 0
Account | Security | BR-002 | 1 | 1.75% | High: 0 Medium: 1 Low: 0
Admin | AI Detection | BR-003, BR-004, BR-005 | 3 | 5.26% | High: 0 Medium: 2 Low: 1
Admin | Billing | BR-006, BR-007, BR-008, BR-009 | 4 | 7.02% | High: 4 Medium: 0 Low: 0
Admin | Dashboard | BR-010, BR-011, BR-012, BR-013, BR-014, BR-015, BR-016, BR-017 | 8 | 14.04% | High: 0 Medium: 4 Low: 4
Admin | Edit Cards | BR-018 | 1 | 1.75% | High: 0 Medium: 1 Low: 0
Admin | Email Subscriber | BR-019, BR-020, BR-021 | 3 | 5.26% | High: 1 Medium: 1 Low: 1
Admin | Humanization | BR-022, BR-023, BR-024, BR-025 | 4 | 7.02% | High: 1 Medium: 0 Low: 3
Admin | Settings | BR-026 | 1 | 1.75% | High: 0 Medium: 0 Low: 1
Admin | User Management | BR-027 | 1 | 1.75% | High: 0 Medium: 1 Low: 0
Dashboard | Dashboard | BR-028, BR-029, BR-030, BR-031, BR-032 | 5 | 8.77% | High: 5 Medium: 0 Low: 0
Landing Page | Header | BR-033, BR-034 | 2 | 3.51% | High: 0 Medium: 0 Low: 2
Landing Page | Home | BR-035, BR-036, BR-037, BR-038, BR-039, BR-040, BR-041 | 7 | 12.28% | High: 0 Medium: 5 Low: 2
Pricing | Pricing | BR-042, BR-043, BR-044, BR-045, BR-046, BR-047, BR-048, BR-049 | 8 | 14.04% | High: 4 Medium: 4 Low: 0
Signup | Data Policy | BR-050 | 1 | 1.75% | High: 1 Medium: 0 Low: 0
Signup | Signup | BR-051, BR-052, BR-053, BR-054, BR-055, BR-056 | 6 | 10.53% | High: 5 Medium: 0 Low: 1