## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: | Pollable |  | High | 15
Project URL: |  |  | Medium | 12
Developer: | AI Venture |  | Low | 4
OS:
Environment |  |  | Total Test Cases: | 31
|  |  | Test Case Solved : | 25
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Comment
BR-001 | Authentication | Authentication | Missing flow in the frontend | User need to be able to access pollable link with their browser | 1. Open link 2. Click on forget password | User Credentials | The flow should match the Figma design accurately. | A missing flow has been spotted in the frontend. | Fail | High | https://jam.dev/c/8db5adba-8ef4-4b9f-8e25-89617ed25241 |  | Fahad | Solved | In web, we are taking this info after signup (from profile settings)
BR-002 | Forget password | OTP | The OTP for the forgot password process failed to be received, making the feature non-functional. | User need to be able to access pollable link with their browser | 1. Open link 2. Click on forget password | User Credentials | Forgot password OTP should be received without any issues. | Not receiving the forgot password OTP email, making the feature unusable. | Fail | High | https://jam.dev/c/2c7b0c2a-2f35-4c1f-93f2-934a7df4fc15 |  | Fahad | Solved
BR-003 | Home | Comments | Comments should be placed with the first one at the top. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | The oldest comment should appear at the top. | The latest comment appears at the top of the comment thread. | Fail | Low | https://jam.dev/c/8e8b738e-4b55-4084-8616-c07676245401 |  | Fahad | Solved | he set the name like that, its not frontend fault
BR-004 | Home | Home | The username contains numeric values. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | User name should only contain alphabetical characters. | Also accepts numeric values | Fail | Low | https://jam.dev/c/fef33b85-515f-42a4-837f-690ae4937d1a |  | Fahad | Solved | he set the name like that, its not frontend fault
BR-005 | Home | Home | The same poll is showing up twice on the homepage | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | The poll should appear only once on the homepage list. | Poll appears multiple time in home page | Fail | Medium | https://jam.dev/c/df212532-2f33-4b5f-9dc4-15a74f9d7630 |  | Fahad | Solved
BR-006 | Home | Home | unable to view poll of the day | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | User should be able to view poll of the day | Failed to redirect to poll of the day | Fail | Medium | https://jam.dev/c/95e86274-7cbd-4093-a62c-12c4efa97730 |  | Fahad | Solved
BR-007 | Home | Home | The error page isn’t displaying properly. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | An error page should be displayed correctly when the API is not found. | The error page isn’t showing, it just redirects to the home page. | Fail | High | https://jam.dev/c/203acca1-2bef-4693-b94c-6435569c8d4a |  | Fahad | Solved
BR-008 | Home | Home | Trending polls fail to display on any tabs other than Home. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Trending polls | User Credentials | Trending polls should be accessible from every page. | Unable to access from any tabs other than the home tab. | Fail | High | https://jam.dev/c/0806ce3e-eacd-4189-af72-90e9255da543 |  | Fahad | Solved
BR-009 | Home | Upgrade | A non-functional button has been spotted. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | All buttons should be functional and work as intended. | A non-functional button has been spotted on the home page. | Fail | High | https://jam.dev/c/caf27753-0917-4a6d-a751-7ee9214ca969 |  | Fahad | Solved
BR-010 | Login | Login | In Figma, the name is split into two sections, but on the frontend, it appears as a single section showing the full name. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The design should be accurately created following Figma. | Different design has been noticed | Fail | Medium | https://jam.dev/c/8d7cc1b8-4311-4b9d-af59-6d641a37ada2 |  | Fahad | Solved | The design was like this
BR-011 | Login | Login | The separate country code section hasn’t been implemented in the frontend. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The design should be accurately created following Figma. | Different design has been noticed | Fail | High | https://jam.dev/c/cdd2985f-885f-4fc5-adc5-3ad4c283bee9 |  | Fahad | Solved | The design was like this
BR-012 | Login | Login | Clicking on Terms shows the Privacy title if the Privacy page was last opened, and vice versa. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The titles for the Terms and Conditions and Privacy pages should be displayed accurately. | Clicking on Terms shows the Privacy title if the Privacy page was last opened, and vice versa. | Fail | Medium | https://jam.dev/c/7cd8cc20-a277-4281-93f3-0bd467b028ae |  | Fahad | Solved | This is for network issue
BR-013 | Login | Login | Frontend doesn’t have a character limit implemented. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Each input field should have a character limit. | No limit is implemented in frontend | Fail | Medium | https://jam.dev/c/93a55fb7-0fa0-483d-a80e-b5e65feb2474 |  | Fahad | Solved
BR-014 | Login | Login | The format should be a dummy number, not the actual number. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Format error display should hold dummy number not actual number | The actual number is displayed in the specified format. | Fail | Medium | https://jam.dev/c/dc2411c6-9b10-4d64-8946-1e9134e8fe11 |  | Fahad | Solved
BR-015 | Login | Login | Frontend doesn’t have a character limit implemented. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Each input field should have a character limit. | No limit is implemented in frontend | Fail | Medium | https://jam.dev/c/fc544271-fb45-47ce-b1ad-a077573fb3ae |  | Fahad | Solved
BR-016 | Login | Login | Can enter alphabet characters in a numeric input field. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Implementing input field validation is essential. | The input field doesn’t have any validation implemented. | Fail | High | https://jam.dev/c/974dca56-c47e-4d48-929e-e83c35f4d1e5 |  | Fahad | Solved
BR-017 | Login | Login | Unable to signup new user | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Users should be able to sign up without encountering any issues. | Failed to signup | Fail | High | https://jam.dev/c/b4eee402-6094-4deb-9c4d-c8865eee027f |  | Fahad | Solved
BR-018 | Message | Message | Couldn’t send the message to the user. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Send message to user | User Credentials | A user should be able to send a message directly to another user. | Unable to send message to another user | Fail | High | https://jam.dev/c/ffcd5328-117e-440e-bd38-83fbfb98231c |  | Fahad | Solved
BR-019 | Notification | Notification | The user received double notifications for a message request. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | The user should receive only unique notifications, not duplicates. | Got a double notification for the same thing. | Fail | Medium | https://jam.dev/c/67c848b9-c89d-49ac-a6ce-dca6fe60d360 |  | Fahad | Backend | Backend Issue
BR-020 | Poll | Poll | The image crop size isn’t accurate for every poll. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | Image cropping should be flexible. | With this default cropping, some polls may not be perfect. | Fail | High | https://jam.dev/c/dcba0aed-85b1-4bf7-883a-0d3dcea12b60 |  | Fahad | frontend | Image must be cropped in well manner
BR-021 | Poll | Poll | Created a draft poll with the description "Which one is your favorite," but in the recent activity, it showed that I had reacted to my own poll. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | Recent activity should display an accurate message. | A different message appeared in recent activity. | Fail | High | https://jam.dev/c/c43f11f6-535e-4376-be2d-d2b3d2b57e5e |  | Fahad | Solved
BR-022 | Poll | Poll | Voted in the same poll from two accounts, but it only shows one vote. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | Vote updates should be dynamic. | A static update was noticed when voting on the same poll from two accounts, but only one vote from each account was displayed. | Fail | High | https://jam.dev/c/b08761d2-7033-41b0-8a54-3e8a87a0c167 |  | Fahad | Backend
BR-023 | Poll | Poll | UI is different from Figma. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on poll demographics | User Credentials | The design and alignment should match exactly as shown in Figma. | A different design has been noticed on the frontend. | Fail | Medium | https://jam.dev/c/0501f409-7e39-4923-a02b-583d5d8b7732 |  | Fahad | Solved | No matter
BR-024 | Poll | Poll | The option to close the poll is missing when the user scrolls down. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | The poll close button should be visible at every stage so the user doesn’t have to scroll up to close the page. | The close button disappears when the user scrolls down. | Fail | Low | BR-30.mp4 |  | Fahad | Solved
BR-025 | Profile | Profile | The user couldn’t update their profile. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile | User Credentials | Users should be able to update their profiles. | Encountered an error while updating profile. | Fail | High | https://jam.dev/c/5b0d20c2-098f-4e7e-b19b-ca6fd0ad3da8 |  | Fahad | Backend
BR-026 | Profile | Profile | The test_test_1 user is active and online, but on the test_test_2 account, it shows test_test_1 as offline. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | A user should be visible as active or online globally whenever they are active on the platform. | The user appears as offline even though they are actually online on the platform. | Fail | High | https://jam.dev/c/fae3f108-aab8-4c8c-ab39-ad4d07f03c16 |  | Fahad | Solved | First part is only stats, and below part is clickable button
BR-027 | Profile | Profile | Should be linked up | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | Polls, followers, and following should be connected to the actual sites. | Not linked up with the sites | Fail | Medium | https://jam.dev/c/58a741e9-a865-4b5e-a309-7af7115bfecd |  | Fahad | Solved
BR-028 | Profile | Profile | No confirmation popup appears when deleting the account. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile 4. Click on delete account | User Credentials | A confirmation should pop up when deleting an account. | No confirmation popup appeared. | Fail | High | https://jam.dev/c/05e04ba6-db53-4c4f-b0f7-d294ca732e21 |  | Fahad | Solved
BR-029 | Profile | Profile | User still navigates back to the home and poll pages after logging out. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile 4. Click on delete account | User Credentials | A user shouldn’t be able to backtrack while in a logged-out state. | Able to backtrack during logout | Fail | Medium | BR-29.mp4 |  | Fahad | Solved
BR-030 | Upgrade | Upgrade | The monthly and yearly plans are not showing up correctly. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | A separate screen should be implemented for the monthly and yearly plans. | Use the same screen for both the monthly and yearly plans. | Fail | Medium | https://jam.dev/c/2b1f556b-b8eb-45d1-9356-692135deb1b9 |  | Fahad
BR-031 | Upgrade | Upgrade | Alignment and design issue | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | The alignment and design should match the Figma design accurately. | An alignment issue has been spotted. | Fail | Low | BR-31.png |  | Fahad

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Pollable App
Developer: | AI Venture
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
BR_001 | Login | Login | In Figma, the name is split into two sections, but on the frontend, it appears as a single section showing the full name. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The design should be accurately created following Figma. | Different design has been noticed | Fail | Medium | https://jam.dev/c/8d7cc1b8-4311-4b9d-af59-6d641a37ada2
BR_002 | Login | Login | The separate country code section hasn’t been implemented in the frontend. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The design should be accurately created following Figma. | Different design has been noticed | Fail | High | https://jam.dev/c/cdd2985f-885f-4fc5-adc5-3ad4c283bee9
BR_003 | Login | Login | Clicking on Terms shows the Privacy title if the Privacy page was last opened, and vice versa. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | The titles for the Terms and Conditions and Privacy pages should be displayed accurately. | Clicking on Terms shows the Privacy title if the Privacy page was last opened, and vice versa. | Fail | Medium | https://jam.dev/c/7cd8cc20-a277-4281-93f3-0bd467b028ae
BR_004 | Login | Login | Frontend doesn’t have a character limit implemented. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Each input field should have a character limit. | No limit is implemented in frontend | Fail | Medium | https://jam.dev/c/93a55fb7-0fa0-483d-a80e-b5e65feb2474
BR_005 | Login | Login | The format should be a dummy number, not the actual number. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Format error display should hold dummy number not actual number | The actual number is displayed in the specified format. | Fail | Medium | https://jam.dev/c/dc2411c6-9b10-4d64-8946-1e9134e8fe11
BR_006 | Login | Login | Frontend doesn’t have a character limit implemented. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Each input field should have a character limit. | No limit is implemented in frontend | Fail | Medium | https://jam.dev/c/fc544271-fb45-47ce-b1ad-a077573fb3ae
BR_007 | Login | Login | Can enter alphabet characters in a numeric input field. | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Implementing input field validation is essential. | The input field doesn’t have any validation implemented. | Fail | High | https://jam.dev/c/974dca56-c47e-4d48-929e-e83c35f4d1e5
BR_008 | Login | Login | Unable to signup new user | User need to be able to access pollable link with their browser | 1. Open link 2. Goto Signin Page | N/A | Users should be able to sign up without encountering any issues. | Failed to signup | Fail | High | https://jam.dev/c/b4eee402-6094-4deb-9c4d-c8865eee027f
BR_009 | Home | Home | The username contains numeric values. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | User name should only contain alphabetical characters. | Also accepts numeric values | Fail | Low | https://jam.dev/c/fef33b85-515f-42a4-837f-690ae4937d1a
BR_010 | Home | Home | The same poll is showing up twice on the homepage | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | The poll should appear only once on the homepage list. | Poll appears multiple time in home page | Fail | Medium | https://jam.dev/c/df212532-2f33-4b5f-9dc4-15a74f9d7630
BR_011 | Home | Home | unable to view poll of the day | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | User should be able to view poll of the day | Failed to redirect to poll of the day | Fail | Medium | https://jam.dev/c/95e86274-7cbd-4093-a62c-12c4efa97730
BR_012 | Home | Comments | Comments should be placed with the first one at the top. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | The oldest comment should appear at the top. | The latest comment appears at the top of the comment thread. | Fail | Low | https://jam.dev/c/8e8b738e-4b55-4084-8616-c07676245401
BR_013 | Home | Upgrade | A non-functional button has been spotted. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | All buttons should be functional and work as intended. | A non-functional button has been spotted on the home page. | Fail | High | https://jam.dev/c/caf27753-0917-4a6d-a751-7ee9214ca969
BR_014 | Forget password | OTP | The OTP for the forgot password process failed to be received, making the feature non-functional. | User need to be able to access pollable link with their browser | 1. Open link 2. Click on forget password | User Credentials | Forgot password OTP should be received without any issues. | Not receiving the forgot password OTP email, making the feature unusable. | Fail | High | https://jam.dev/c/2c7b0c2a-2f35-4c1f-93f2-934a7df4fc15
BR_015 | Authentication | Authentication | Missing flow in the frontend | User need to be able to access pollable link with their browser | 1. Open link 2. Click on forget password | User Credentials | The flow should match the Figma design accurately. | A missing flow has been spotted in the frontend. | Fail | High | https://jam.dev/c/8db5adba-8ef4-4b9f-8e25-89617ed25241
BR_016 | Poll | Poll | The image crop size isn’t accurate for every poll. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | Image cropping should be flexible. | With this default cropping, some polls may not be perfect. | Fail | High | https://jam.dev/c/dcba0aed-85b1-4bf7-883a-0d3dcea12b60
BR_017 | Profile | Profile | The user couldn’t update their profile. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile | User Credentials | Users should be able to update their profiles. | Encountered an error while updating profile. | Fail | High | https://jam.dev/c/5b0d20c2-098f-4e7e-b19b-ca6fd0ad3da8
BR_018 | Home | Home | The error page isn’t displaying properly. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | An error page should be displayed correctly when the API is not found. | The error page isn’t showing, it just redirects to the home page. | Fail | High | https://jam.dev/c/203acca1-2bef-4693-b94c-6435569c8d4a
BR_019 | Poll | Poll | Created a draft poll with the description "Which one is your favorite," but in the recent activity, it showed that I had reacted to my own poll. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | Recent activity should display an accurate message. | A different message appeared in recent activity. | Fail | High | https://jam.dev/c/c43f11f6-535e-4376-be2d-d2b3d2b57e5e
BR_020 | Poll | Poll | Voted in the same poll from two accounts, but it only shows one vote. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home | User Credentials | Vote updates should be dynamic. | A static update was noticed when voting on the same poll from two accounts, but only one vote from each account was displayed. | Fail | High | https://jam.dev/c/b08761d2-7033-41b0-8a54-3e8a87a0c167
BR_021 | Profile | Profile | The test_test_1 user is active and online, but on the test_test_2 account, it shows test_test_1 as offline. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | A user should be visible as active or online globally whenever they are active on the platform. | The user appears as offline even though they are actually online on the platform. | Fail | High | https://jam.dev/c/fae3f108-aab8-4c8c-ab39-ad4d07f03c16
BR_022 | Notification | Notification | The user received double notifications for a message request. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | The user should receive only unique notifications, not duplicates. | Got a double notification for the same thing. | Fail | Medium | https://jam.dev/c/67c848b9-c89d-49ac-a6ce-dca6fe60d360
BR_023 | Message | Message | Couldn’t send the message to the user. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Send message to user | User Credentials | A user should be able to send a message directly to another user. | Unable to send message to another user | Fail | High | https://jam.dev/c/ffcd5328-117e-440e-bd38-83fbfb98231c
BR_024 | Upgrade | Upgrade | The monthly and yearly plans are not showing up correctly. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | A separate screen should be implemented for the monthly and yearly plans. | Use the same screen for both the monthly and yearly plans. | Fail | Medium | https://jam.dev/c/2b1f556b-b8eb-45d1-9356-692135deb1b9
BR_025 | Profile | Profile | Should be linked up | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Search user by their name | User Credentials | Polls, followers, and following should be connected to the actual sites. | Not linked up with the sites | Fail | Medium | https://jam.dev/c/58a741e9-a865-4b5e-a309-7af7115bfecd
BR_026 | Home | Home | Trending polls fail to display on any tabs other than Home. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Trending polls | User Credentials | Trending polls should be accessible from every page. | Unable to access from any tabs other than the home tab. | Fail | High | https://jam.dev/c/0806ce3e-eacd-4189-af72-90e9255da543
BR_027 | Poll | Poll | UI is different from Figma. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on poll demographics | User Credentials | The design and alignment should match exactly as shown in Figma. | A different design has been noticed on the frontend. | Fail | Medium | https://jam.dev/c/0501f409-7e39-4923-a02b-583d5d8b7732
BR_028 | Profile | Profile | No confirmation popup appears when deleting the account. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile 4. Click on delete account | User Credentials | A confirmation should pop up when deleting an account. | No confirmation popup appeared. | Fail | High | https://jam.dev/c/05e04ba6-db53-4c4f-b0f7-d294ca732e21
BR_029 | Profile | Profile | User still navigates back to the home and poll pages after logging out. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Profile 4. Click on delete account | User Credentials | A user shouldn’t be able to backtrack while in a logged-out state. | Able to backtrack during logout | Fail | Medium | BR-29.mp4
BR_030 | Poll | Poll | The option to close the poll is missing when the user scrolls down. | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Create Poll | User Credentials | The poll close button should be visible at every stage so the user doesn’t have to scroll up to close the page. | The close button disappears when the user scrolls down. | Fail | Low | BR-30.mp4
BR_031 | Upgrade | Upgrade | Alignment and design issue | User need to be able to access pollable link with their browser | 1. Open link 2. Signin using valid credentials 3. Goto Home 4. Click on Upgrade | User Credentials | The alignment and design should match the Figma design accurately. | An alignment issue has been spotted. | Fail | Low | BR-31.png

## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Authentication | Authentication | BR-001 | 1 | 3.23% | High: 1 Medium: 0 Low: 0
Forget password | OTP | BR-002 | 1 | 3.23% | High: 1 Medium: 0 Low: 0
Home | Comments | BR-003 | 1 | 3.23% | High: 0 Medium: 0 Low: 1
Home | Home | BR-004, BR-005, BR-006, BR-007, BR-008 | 5 | 16.13% | High: 2 Medium: 2 Low: 1
Home | Upgrade | BR-009 | 1 | 3.23% | High: 1 Medium: 0 Low: 0
Login | Login | BR-010, BR-011, BR-012, BR-013, BR-014, BR-015, BR-016, BR-017 | 8 | 25.81% | High: 3 Medium: 5 Low: 0
Message | Message | BR-018 | 1 | 3.23% | High: 1 Medium: 0 Low: 0
Notification | Notification | BR-019 | 1 | 3.23% | High: 0 Medium: 1 Low: 0
Poll | Poll | BR-020, BR-021, BR-022, BR-023, BR-024 | 5 | 16.13% | High: 3 Medium: 1 Low: 1
Profile | Profile | BR-025, BR-026, BR-027, BR-028, BR-029 | 5 | 16.13% | High: 3 Medium: 2 Low: 0
Upgrade | Upgrade | BR-030, BR-031 | 2 | 6.45% | High: 0 Medium: 1 Low: 1