## Test_Plan (hidden)
Software Test Plan : [Porject Name]
Project Information :
Project Objective :
Project Scope : |  | In Scope : Out of scope :
Project Scope :
Test Strategy :
Test Type : |  | Functional : Non-Functional :
Test Type :
Test Enviroment :
Test Data :

## Test_Scenario (hidden)
Test Scenario
Scenario ID | Requirement ID | Module | Sub-Module | Test Scenario | Test Type | Priority | Precondition | Test Data | Expected Outcome | Remarks

## Test_Case (hidden)
Test Case
Test Case ID | Test Scenario ID | Requirement ID | Module | Sub-Module | Test Case Title | Test Type | Priority | Preconditions | Test Data | Test Steps | Expected Result | Actual Result | Status | Severity | Environment | Tester | Evidence | Remarks

## Bug_report
Tester : | Mohammed Fahad Faisal |  |  | mom : jvai57574@gmail.com ¦¦ Password123# dad : teamaithunder@gmail.com ¦¦ Password123#
Project Name:
Developer:
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127 | [11 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment
BR_001 | Mother Account | OTP | Failed to receive OTP for account verification | User need to use the app on their mobile device | 1. Open app | MOM user credential | User should be able to receive the OTP without any issues. | Used failed to receive OTP | Fail | High | 001.png
BR_002 | Mother Account | OTP | Toast stays in a constant state. Should be vanish after 3-4 seconds | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page | MOM user credential | Toast error message should only appear for 3-5 seconds | Toast message remains in app unless it was removed | Fail | Medium | 002.png
BR_003 | Mother Account | Subscription | Spell mistake has been noticed | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Spell mistake should not be visible | Spelling mistake has been noticed. | Fail | Low | 003.png
BR_004 | Mother Account | Subscription | Yearly rate per month isn’t showing when a user selects the yearly subscription. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Alignment and design should be as same as figma | Alignment issue occurred when the user switched to a yearly subscription. | Fail | Medium | 004.png
BR_005 | Mother Account | Subscription | Goes to the subscription page but then redirects to the website’s home page, where the user isn’t logged in. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | User should be redirected to a webpage with their login state intact, and from there, be taken to the subscription page. | User is redirected to the web page in a logged-out state. | Fail | High | 005.mp4
BR_006 | Mother Account | Subscription | Didn’t automatically redirect the user to app after they purchased it. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Should redirect users to app | Unable to redirect the user to the app after completing the subscription purchase. | Fail | Medium | 006.mp4
BR_007 | Mother Account | Subscription | Highlight the discounted price when a user chooses the yearly package instead of the monthly package. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on settings 4. Goto subscription | MOM user credential | Highlight the discount percentage for purchasing the yearly package instead of the monthly package. | No discount price has been shown | Fail | Medium | 007.png
BR_008 | Mother Account | Message | No send icon visible, but the image gets sent when clicking on the “crop” option. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on message | MOM user credential | Send button should be visible. | Send button is missing but can still send a picture by clicking on the crop option. | Fail | High | 008.mp4
BR_009 | Mother Account | Message | Download chat redirects to the API backend page. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on message | MOM user credential | Should be able to download full conversation | Failed to download conversation, redirect to backend api page | Fail | High | 009.mp4
BR_010 | Mother Account | Call | Alignment issue | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on call | MOM user credential | Design and alignment should be as same as figma | Overlapp issue has been noticed | Fail | Medium | 010.png
BR_011 | Mother Account | Call | Displays co-parent as offline even when no co-parent has been added. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on call | MOM user credential | If no co-parent has been added, thanit should now display co-parent offline | Display co-parent is offline where there is no co-parent added | Fail | High | 011.png
BR_012 | Mother Account | Document | No document has been uploaded, yet the document banner is still showing. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Blank page should be displayed if there is not document | Show document banner when there is not document | Fail | Medium | 012.png
BR_013 | Mother Account | Document | Image preview missing in edit document section | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Image should be displayed properly | Missing image, no preview | Fail | Medium | 013.png
BR_014 | Mother Account | Document | Failed to store description message | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Description message should be store properly | Failed to displaye description message | Fail | High | 014.mp4
BR_015 | Mother Account | Document | Unable to download the document | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | User should be able to download document | Failed to download document on user side | Fail | High | 015.mp4
BR_016 | Mother Account | Document | Unable to preview image. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | User should be able to preview image | Failed to preview image | Fail | High | 016.mp4
BR_017 | Mother Account | Document | Failed to display file size | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | File size should displayed properly | Failed to view file size | Fail | Medium | 017.png
BR_018 | Mother Account | Document | Failed to upload document. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Users should be able to upload their documents without encountering any issues. | Failed to upload document | Fail | High | 018.png
BR_019 | Mother Account | Document | Should display user name | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Should display user name, not user ID | Showing user ID as user name | Fail | Low | 019.png
BR_020 | Father Account | Bridge Mode | Code validation is not yet implemented in co-parent bridge mode. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Enter co-parent code | DAD user credential | Code validation should be implemented | Without invitation code validation, user can go to next step | Fail | High | 020.mp4
BR_021 | Father Account | Login | Number format should be displayed to match the correct code (country code + number). | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials | DAD user credential | Should suggest the number format to match with backend | Valid account displays an invalid/unregistered number error when attempting to log in. | Fail | High | 021.png
BR_022 | Father Account | Login | Failed to sign up using Google. | User need to use the app on their mobile device | 1. Open app 2. Signup using google signup | DAD user credential | User should be able to signup using google signup | faile to signup using google signup | Fail | High | 022.png
BR_023 | Father Account | Settings -> Subscription | Payment went through successfully, but when opening the app, it shows that no payment has been made and no plan has been purchased. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | DAD user credential | co-parent should be able to purchase the subscription | Failed to purchase plan on co-parent side | Fail | High | 023.mp4
BR_024 | Father Account | Settings -> Co-Parent information | Failed to show co-parent contact number on another co-parent profile | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on co-parent information | DAD user credential | On both accounts, the co-parent information should be displayed correctly. | Failed to show co-parent contact information on both account | Fail | High | 024.png
BR_025 | Father Account | Settings -> Choose The App | Non-functional module has been seen | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Choose The App section | DAD user credential | Module should works properly as expected | non functional module has been nothced | Fail | High | 025.png
BR_026 | Father Account | Settings -> Legacy Contact | Dummy legacy contact has been set by default. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Legacy Contact | DAD user credential | Dummy data should not be displayed on user side | Dummy data store by default | Fail | High | 026.png
BR_027 | Father Account | Settings -> Help & Support | dummy email should be set as placeholder | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Help & Support | DAD user credential | Placeholder value should be displayed instead of the actual data. | Dummy email set as actual text | Fail | Low | 027.png
BR_028 | Father Account | Notification | Failed to receive calendar notification even though the co-parent enabled notifications. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender 4. Check if notification popup in co-parent account | DAD user credential | Co-parents should receive a notification if they turn on the receive notification toggle. | Did not receive notification on the co-parent's side. | Fail | High | 028.png
BR_029 | Father Account | Event | Event scheduled for the entire day. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Time and date should display properly | Set all day as event time but in playcard it shows blank | Fail | Medium | 029.png
BR_030 | Father Account | Event | Can set the event to reverse time. Logical error | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | start time should be smaller than end time | Can set event end time before event start time | Fail | Medium | 030.png
BR_031 | Father Account | Event | Event doesn’t update dynamically when it’s created and the user is logged in. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Event should update dynamically with a notification popup. | No popup is displayed, and the event doesn’t update dynamically. | Fail | High | 031.png
BR_032 | Father Account | Event | Difference between a real device and an emulator, must be precise | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Design should be as same as figma | Difference in app on button has been noticed | Fail | Medium | 032.png
BR_033 | Father Account | Expense | Failed to close the popup box by clicking on a random spot on the page. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Dialouge box should close when user clicks on random site than dialouge box | Failed to close the dialogue box by clicking on random places other than the dialogue box. | Fail | Medium | 033.mp4
BR_034 | Father Account | Expense | Different font style used | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | All text font should be same | Different font used | Fail | Low | 034.png
BR_035 | Father Account | Expense | Alignment broke when selecting catagory | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Alignment and design should be same | Broken alignment has been noticed when selecting catagory | Fail | Medium | 035.png
BR_036 | Father Account | Expense | Flow broken | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | There should be a validation process between two parents, where one submits a request and the other has the authority to approve or reject it. Additionally, a double validation should be implemented to verify whether the requested amount has been paid or not. | Add expense and manage flow broken | Fail | High | 036.png
BR_037 | Father Account | Expense | All expenses are listed under the "Paid" category, but they don’t appear in the "Approved" tab. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Expenses should be validated on both sides for authenticity. | Missing approve/reject on co-parent account | Fail | High | 037.mp4
BR_038 | Father Account | Expense | Expense spent in August but showing in September | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Expense month should be shown correctly. | August expenses are showing under the September month. | Fail | High | 038.mp4
BR_039 | Father Account | Expense | Not all categories are showing in the filter section. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | All categories should be displayed to address the filter issue. | Only a limited number of categories are shown for filtering. | Fail | Medium | 039.png
BR_040 | Father Account | Expense | Calculation error was found, as the total spend is $170 and each share amounts to $85. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Calculation needs to be accurate. | Calculation error has been noticed | Fail | High | 040.png
BR_041 | Father Account | Support Forum | Email and token number shown in user name | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Show the user's name or display "Anonymous" if they choose to post anonymously. | Displaying the email and token name as the username | Fail | Medium | 041.png
BR_042 | Father Account | Support Forum | See more button is displayed on all posts, whether they are long or short. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | "See more" button should apper when the post is too long to display | The "See more" button shows up all the time, whether it's a short post or a long one. | Fail | Medium | 042.mp4
BR_043 | Father Account | Support Forum | Couldn’t close the post banner because no close button was found. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Banner’s close button should be positioned at the top right. | Could not close the banner for the post. | Fail | Medium | 043.mp4
BR_044 | Father Account | Support Forum | Unable to upload the post anonymously. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Post should be uploaded without revealing the author’s identity. | Anonymous post feature didn’t work. | Fail | High | 044.mp4
BR_045 | Father Account | Support Forum | Options to edit, delete, or share the post are not available. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Post edit, delete, or share options should be clearly visible and positioned correctly. | Post edit, delete, or share options are missing in the frontend. | Fail | High | 045.png
BR_046 | Father Account | Support Forum | Comments on the post aren’t updating in real time. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Comments should update in real time with a popup notification. | Comments don’t update automatically, and no notifications appear when someone comments on a post. | Fail | High | 046.png
BR_047 | Father Account | Support Forum | Comments are not showing when posts pop up. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Comments are not visible when banner popup | Comments should be visible when the banner popups | Fail | Medium | 047.mp4
BR_048 | Father Account | Support Forum | Category name should appear below the username. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Category name should be displayed beneath the username. | Category name is missing from the post banner. | Fail | Low | 048.png
BR_049 | Father Account | Support Forum | Post banner displays a different time than expected. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Time should be same in post in different banner | Post banner displays different times on different sites. | Fail | Medium | 049.mp4
BR_050 | Father Account | Legal Records | Failed to open legal records. Not working properly. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Legal Records | DAD user credential | Functions should works properly as expected | Function should work as expected | Fail | High | 050.png
BR_051 | Father Account | Home | Clicking on the profile should redirect the user to their profile page. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Home | MOM user credential | Clicking the profile should take the user straight to their profile page. | Clicking on the profile doesn’t redirect to the profile page. | Fail | Medium | 051.png
BR_052 | Mother Account | Home | Clicking on the home icon opened the home page, which was overlapping. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Home | MOM user credential | Home page should open with a single click. | Clicking multiple times on the home page opens several home tabs. | Fail | Medium | 052.mp4
BR_053 | Backend | Wallet | Unable to redirect the user to the home page after completing a subscription purchase. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Purchase plan | MOM user credential | User should redirect to home page after purchasing plan | Failed to redirect user to home page | Fail | High | 053.png
BR_054 | Backend | Profile | Unable to save Twilio data after setting up a new account. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto settings -> profile | MOM user credential | Twilio information should be stored after a user creates an account. | Failed to store users twilio information in backend | Fail | High | 054.png
BR_055
BR_056
BR_057
BR_058
BR_059
BR_060

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Backend | Profile | BR-001 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Backend | Wallet | BR-002 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Bridge Mode | BR-003 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Event | BR-004, BR-005, BR-006, BR-007 | 4 | 7.41% | High: 1 Medium: 3 Low: 0
Father Account | Expense | BR-008, BR-009, BR-010, BR-011, BR-012, BR-013, BR-014, BR-015 | 8 | 14.81% | High: 4 Medium: 3 Low: 1
Father Account | Home | BR-016 | 1 | 1.85% | High: 0 Medium: 1 Low: 0
Father Account | Legal Records | BR-017 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Login | BR-018, BR-019 | 2 | 3.70% | High: 2 Medium: 0 Low: 0
Father Account | Notification | BR-020 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Settings -> Choose The App | BR-021 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Settings -> Co-Parent information | BR-022 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Settings -> Help & Support | BR-023 | 1 | 1.85% | High: 0 Medium: 0 Low: 1
Father Account | Settings -> Legacy Contact | BR-024 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Settings -> Subscription | BR-025 | 1 | 1.85% | High: 1 Medium: 0 Low: 0
Father Account | Support Forum | BR-026, BR-027, BR-028, BR-029, BR-030, BR-031, BR-032, BR-033, BR-034 | 9 | 16.67% | High: 3 Medium: 5 Low: 1
Mother Account | Call | BR-035, BR-036 | 2 | 3.70% | High: 1 Medium: 1 Low: 0
Mother Account | Document | BR-037, BR-038, BR-039, BR-040, BR-041, BR-042, BR-043, BR-044 | 8 | 14.81% | High: 4 Medium: 3 Low: 1
Mother Account | Home | BR-045 | 1 | 1.85% | High: 0 Medium: 1 Low: 0
Mother Account | Message | BR-046, BR-047 | 2 | 3.70% | High: 2 Medium: 0 Low: 0
Mother Account | OTP | BR-048, BR-049 |  |  | High: 1 Medium: 1 Low: 0
Mother Account | Subscription

## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 28
Project URL: |  |  | Medium | 21
Developer: |  |  | Low | 5
OS:
Environment |  |  | Total Test Cases: | 54
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment | Tester
BR-001 | Backend | Profile | Unable to save Twilio data after setting up a new account. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto settings -> profile | MOM user credential | Twilio information should be stored after a user creates an account. | Failed to store users twilio information in backend | Fail | High | 054.png |  |  |  |  | Fahad
BR-002 | Backend | Wallet | Unable to redirect the user to the home page after completing a subscription purchase. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Purchase plan | MOM user credential | User should redirect to home page after purchasing plan | Failed to redirect user to home page | Fail | High | 053.png |  |  |  |  | Fahad
BR-003 | Father Account | Bridge Mode | Code validation is not yet implemented in co-parent bridge mode. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Enter co-parent code | DAD user credential | Code validation should be implemented | Without invitation code validation, user can go to next step | Fail | High | 020.mp4 |  |  |  |  | Fahad
BR-004 | Father Account | Event | Event scheduled for the entire day. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Time and date should display properly | Set all day as event time but in playcard it shows blank | Fail | Medium | 029.png |  |  |  |  | Fahad
BR-005 | Father Account | Event | Can set the event to reverse time. Logical error | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | start time should be smaller than end time | Can set event end time before event start time | Fail | Medium | 030.png |  |  |  |  | Fahad
BR-006 | Father Account | Event | Event doesn’t update dynamically when it’s created and the user is logged in. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Event should update dynamically with a notification popup. | No popup is displayed, and the event doesn’t update dynamically. | Fail | High | 031.png |  |  |  |  | Fahad
BR-007 | Father Account | Event | Difference between a real device and an emulator, must be precise | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender | DAD user credential | Design should be as same as figma | Difference in app on button has been noticed | Fail | Medium | 032.png |  |  |  |  | Fahad
BR-008 | Father Account | Expense | Failed to close the popup box by clicking on a random spot on the page. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Dialouge box should close when user clicks on random site than dialouge box | Failed to close the dialogue box by clicking on random places other than the dialogue box. | Fail | Medium | 033.mp4 |  |  |  |  | Fahad
BR-009 | Father Account | Expense | Different font style used | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | All text font should be same | Different font used | Fail | Low | 034.png |  |  |  |  | Fahad
BR-010 | Father Account | Expense | Alignment broke when selecting catagory | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Alignment and design should be same | Broken alignment has been noticed when selecting catagory | Fail | Medium | 035.png |  |  |  |  | Fahad
BR-011 | Father Account | Expense | Flow broken | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | There should be a validation process between two parents, where one submits a request and the other has the authority to approve or reject it. Additionally, a double validation should be implemented to verify whether the requested amount has been paid or not. | Add expense and manage flow broken | Fail | High | 036.png |  |  |  |  | Fahad
BR-012 | Father Account | Expense | All expenses are listed under the "Paid" category, but they don’t appear in the "Approved" tab. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Expenses should be validated on both sides for authenticity. | Missing approve/reject on co-parent account | Fail | High | 037.mp4 |  |  |  |  | Fahad
BR-013 | Father Account | Expense | Expense spent in August but showing in September | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Expense month should be shown correctly. | August expenses are showing under the September month. | Fail | High | 038.mp4 |  |  |  |  | Fahad
BR-014 | Father Account | Expense | Not all categories are showing in the filter section. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | All categories should be displayed to address the filter issue. | Only a limited number of categories are shown for filtering. | Fail | Medium | 039.png |  |  |  |  | Fahad
BR-015 | Father Account | Expense | Calculation error was found, as the total spend is $170 and each share amounts to $85. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on expense | DAD user credential | Calculation needs to be accurate. | Calculation error has been noticed | Fail | High | 040.png |  |  |  |  | Fahad
BR-016 | Father Account | Home | Clicking on the profile should redirect the user to their profile page. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Home | MOM user credential | Clicking the profile should take the user straight to their profile page. | Clicking on the profile doesn’t redirect to the profile page. | Fail | Medium | 051.png |  |  |  |  | Fahad
BR-017 | Father Account | Legal Records | Failed to open legal records. Not working properly. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Legal Records | DAD user credential | Functions should works properly as expected | Function should work as expected | Fail | High | 050.png |  |  |  |  | Fahad
BR-018 | Father Account | Login | Number format should be displayed to match the correct code (country code + number). | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials | DAD user credential | Should suggest the number format to match with backend | Valid account displays an invalid/unregistered number error when attempting to log in. | Fail | High | 021.png |  |  |  |  | Fahad
BR-019 | Father Account | Login | Failed to sign up using Google. | User need to use the app on their mobile device | 1. Open app 2. Signup using google signup | DAD user credential | User should be able to signup using google signup | faile to signup using google signup | Fail | High | 022.png |  |  |  |  | Fahad
BR-020 | Father Account | Notification | Failed to receive calendar notification even though the co-parent enabled notifications. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Set event in calender 4. Check if notification popup in co-parent account | DAD user credential | Co-parents should receive a notification if they turn on the receive notification toggle. | Did not receive notification on the co-parent's side. | Fail | High | 028.png |  |  |  |  | Fahad
BR-021 | Father Account | Settings -> Choose The App | Non-functional module has been seen | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Choose The App section | DAD user credential | Module should works properly as expected | non functional module has been nothced | Fail | High | 025.png |  |  |  |  | Fahad
BR-022 | Father Account | Settings -> Co-Parent information | Failed to show co-parent contact number on another co-parent profile | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on co-parent information | DAD user credential | On both accounts, the co-parent information should be displayed correctly. | Failed to show co-parent contact information on both account | Fail | High | 024.png |  |  |  |  | Fahad
BR-023 | Father Account | Settings -> Help & Support | dummy email should be set as placeholder | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Help & Support | DAD user credential | Placeholder value should be displayed instead of the actual data. | Dummy email set as actual text | Fail | Low | 027.png |  |  |  |  | Fahad
BR-024 | Father Account | Settings -> Legacy Contact | Dummy legacy contact has been set by default. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Settings 4. Click on Legacy Contact | DAD user credential | Dummy data should not be displayed on user side | Dummy data store by default | Fail | High | 026.png |  |  |  |  | Fahad
BR-025 | Father Account | Settings -> Subscription | Payment went through successfully, but when opening the app, it shows that no payment has been made and no plan has been purchased. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | DAD user credential | co-parent should be able to purchase the subscription | Failed to purchase plan on co-parent side | Fail | High | 023.mp4 |  |  |  |  | Fahad
BR-026 | Father Account | Support Forum | Email and token number shown in user name | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Show the user's name or display "Anonymous" if they choose to post anonymously. | Displaying the email and token name as the username | Fail | Medium | 041.png |  |  |  |  | Fahad
BR-027 | Father Account | Support Forum | See more button is displayed on all posts, whether they are long or short. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | "See more" button should apper when the post is too long to display | The "See more" button shows up all the time, whether it's a short post or a long one. | Fail | Medium | 042.mp4 |  |  |  |  | Fahad
BR-028 | Father Account | Support Forum | Couldn’t close the post banner because no close button was found. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Banner’s close button should be positioned at the top right. | Could not close the banner for the post. | Fail | Medium | 043.mp4 |  |  |  |  | Fahad
BR-029 | Father Account | Support Forum | Unable to upload the post anonymously. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Post should be uploaded without revealing the author’s identity. | Anonymous post feature didn’t work. | Fail | High | 044.mp4 |  |  |  |  | Fahad
BR-030 | Father Account | Support Forum | Options to edit, delete, or share the post are not available. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Post edit, delete, or share options should be clearly visible and positioned correctly. | Post edit, delete, or share options are missing in the frontend. | Fail | High | 045.png |  |  |  |  | Fahad
BR-031 | Father Account | Support Forum | Comments on the post aren’t updating in real time. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Comments should update in real time with a popup notification. | Comments don’t update automatically, and no notifications appear when someone comments on a post. | Fail | High | 046.png |  |  |  |  | Fahad
BR-032 | Father Account | Support Forum | Comments are not showing when posts pop up. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Comments are not visible when banner popup | Comments should be visible when the banner popups | Fail | Medium | 047.mp4 |  |  |  |  | Fahad
BR-033 | Father Account | Support Forum | Category name should appear below the username. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Category name should be displayed beneath the username. | Category name is missing from the post banner. | Fail | Low | 048.png |  |  |  |  | Fahad
BR-034 | Father Account | Support Forum | Post banner displays a different time than expected. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Click on Support Forum | DAD user credential | Time should be same in post in different banner | Post banner displays different times on different sites. | Fail | Medium | 049.mp4 |  |  |  |  | Fahad
BR-035 | Mother Account | Call | Alignment issue | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on call | MOM user credential | Design and alignment should be as same as figma | Overlapp issue has been noticed | Fail | Medium | 010.png |  |  |  |  | Fahad
BR-036 | Mother Account | Call | Displays co-parent as offline even when no co-parent has been added. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on call | MOM user credential | If no co-parent has been added, thanit should now display co-parent offline | Display co-parent is offline where there is no co-parent added | Fail | High | 011.png |  |  |  |  | Fahad
BR-037 | Mother Account | Document | No document has been uploaded, yet the document banner is still showing. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Blank page should be displayed if there is not document | Show document banner when there is not document | Fail | Medium | 012.png |  |  |  |  | Fahad
BR-038 | Mother Account | Document | Image preview missing in edit document section | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Image should be displayed properly | Missing image, no preview | Fail | Medium | 013.png |  |  |  |  | Fahad
BR-039 | Mother Account | Document | Failed to store description message | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Description message should be store properly | Failed to displaye description message | Fail | High | 014.mp4 |  |  |  |  | Fahad
BR-040 | Mother Account | Document | Unable to download the document | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | User should be able to download document | Failed to download document on user side | Fail | High | 015.mp4 |  |  |  |  | Fahad
BR-041 | Mother Account | Document | Unable to preview image. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | User should be able to preview image | Failed to preview image | Fail | High | 016.mp4 |  |  |  |  | Fahad
BR-042 | Mother Account | Document | Failed to display file size | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | File size should displayed properly | Failed to view file size | Fail | Medium | 017.png |  |  |  |  | Fahad
BR-043 | Mother Account | Document | Failed to upload document. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Users should be able to upload their documents without encountering any issues. | Failed to upload document | Fail | High | 018.png |  |  |  |  | Fahad
BR-044 | Mother Account | Document | Should display user name | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on Document | MOM user credential | Should display user name, not user ID | Showing user ID as user name | Fail | Low | 019.png |  |  |  |  | Fahad
BR-045 | Mother Account | Home | Clicking on the home icon opened the home page, which was overlapping. | User need to use the app on their mobile device | 1. Open app 2. Login with valid credentials 3. Goto Home | MOM user credential | Home page should open with a single click. | Clicking multiple times on the home page opens several home tabs. | Fail | Medium | 052.mp4 |  |  |  |  | Fahad
BR-046 | Mother Account | Message | No send icon visible, but the image gets sent when clicking on the “crop” option. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on message | MOM user credential | Send button should be visible. | Send button is missing but can still send a picture by clicking on the crop option. | Fail | High | 008.mp4 |  |  |  |  | Fahad
BR-047 | Mother Account | Message | Download chat redirects to the API backend page. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on message | MOM user credential | Should be able to download full conversation | Failed to download conversation, redirect to backend api page | Fail | High | 009.mp4 |  |  |  |  | Fahad
BR-048 | Mother Account | OTP | Failed to receive OTP for account verification | User need to use the app on their mobile device | 1. Open app | MOM user credential | User should be able to receive the OTP without any issues. | Used failed to receive OTP | Fail | High | 001.png |  |  |  |  | Fahad
BR-049 | Mother Account | OTP | Toast stays in a constant state. Should be vanish after 3-4 seconds | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page | MOM user credential | Toast error message should only appear for 3-5 seconds | Toast message remains in app unless it was removed | Fail | Medium | 002.png |  |  |  |  | Fahad
BR-050 | Mother Account | Subscription | Spell mistake has been noticed | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Spell mistake should not be visible | Spelling mistake has been noticed. | Fail | Low | 003.png |  |  |  |  | Fahad
BR-051 | Mother Account | Subscription | Yearly rate per month isn’t showing when a user selects the yearly subscription. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Alignment and design should be as same as figma | Alignment issue occurred when the user switched to a yearly subscription. | Fail | Medium | 004.png |  |  |  |  | Fahad
BR-052 | Mother Account | Subscription | Goes to the subscription page but then redirects to the website’s home page, where the user isn’t logged in. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | User should be redirected to a webpage with their login state intact, and from there, be taken to the subscription page. | User is redirected to the web page in a logged-out state. | Fail | High | 005.mp4 |  |  |  |  | Fahad
BR-053 | Mother Account | Subscription | Didn’t automatically redirect the user to app after they purchased it. | User need to use the app on their mobile device | 1. Open app 2. Sign up by filling required field 3. Goto OTP page 4. Verify OTP and go to next page | MOM user credential | Should redirect users to app | Unable to redirect the user to the app after completing the subscription purchase. | Fail | Medium | 006.mp4 |  |  |  |  | Fahad
BR-054 | Mother Account | Subscription | Highlight the discounted price when a user chooses the yearly package instead of the monthly package. | User need to use the app on their mobile device | 1. Open app 2. Login using valid credentials 3. Click on settings 4. Goto subscription | MOM user credential | Highlight the discount percentage for purchasing the yearly package instead of the monthly package. | No discount price has been shown | Fail | Medium | 007.png |  |  |  |  | Fahad