## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 50
Project URL: |  |  | Medium | 31
Developer: |  |  | Low | 19
OS:
Environment |  |  | Total Test Cases: | 100
|  |  | Test Case Solved : | 82
|  |  | Remaining : | 18
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Tester
BR-001 | Booking | Booking | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on booking in bottom option | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 037.png |  | Solved | Please check Update Apk | Fahad
BR-002 | Booking | Booking | Booking button in booking page which is not functional | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on booking in bottom option | User Credential | The functional button should be positioned accurately. | Booking button placed in filter button place | Fail | High | 038.png |  | Solved | Please check Update Apk | Fahad
BR-003 | Community | Community | Add photo section missing in community | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | The UI should match the Figma design accurately. | Add photo button missing in community section | Fail | High | 039.png |  | Solved | Please check Update Apk | Fahad
BR-004 | Community | Community | Failed to display pet name in community post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | User and pet name should be displayed as per as client requirement | Failed to display pet name with user name in community post | Fail | High | 040.png |  | Solved |  | Fahad
BR-005 | Community | Community | Options like Report, Don’t Recommend, and similar features found on Facebook are missing. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | Should be implement as per as client requirement | Missing feature | Fail | High | 041.png |  | Unsolve |  | Fahad
BR-006 | Community | Community | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 042.png |  | Solved | Figma will update | Fahad
BR-007 | Community | Community | Share post button placement issue | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 043.png |  | Solved |  | Fahad
BR-008 | Community | Community | The UI looks different from the Figma design. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 044.png |  | Solved |  | Fahad
BR-009 | Community | Community | The feature didn’t work. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | Functionality needs to be precise. | Unable to open gif | Fail | High | 045.png |  | Solved | Rmoved this feature | Fahad
BR-010 | Community | Location | Selected 2nd one but 1st one also shown as selected | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | Only one location should be selected | Shown multiple location selected but only one location is selected | Fail | Medium | 049.png |  | Solved |  | Fahad
BR-011 | Home Screen | Post | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 051.png |  | Solved |  | Fahad
BR-012 | Home Screen | Post | Unable to see who like the post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | User should be able to see who liked the post | Unable to see who liked the post | Fail | High | 052.png |  | Solved |  | Fahad
BR-013 | Home Screen | Post | Positioned in a different place; it should be on the right side. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 053.png |  | Solved | ui need fixed | Fahad
BR-014 | Home Screen | Post | Replies should expand when clicked | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Replies should start collapsed and expand when clicked. | Replies are expanded all the time. Static page | Fail | Low | 054.png |  | Solved |  | Fahad
BR-015 | Home Screen | Post | Alignment issue in post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Design and alignment should be as same as figma | Differen icon noticed | Fail | Medium | 072.png |  | Solved |  | Fahad
BR-016 | Home Screen | Post | Tag's should be clickable | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Tags should be clickable and able to filter posts based on the keyword. | Tags are normal text | Fail | Medium | 073.png |  | Solved |  | Fahad
BR-017 | Home Screen | Post | The post is available, but the user profile couldn’t be found. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | A user's profile should be visible once their post is published. | Post found, but the user profile is missing. | Fail | High | 075.mp4 |  | Solved |  | Fahad
BR-018 | Home Screen | Post | Unable to upload the post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | The user should be able to upload a post without any issues. | Post upload failed | Fail | High | 076.png |  | Solved |  | Fahad
BR-019 | Landing Page | Home Screen | Different UI design in app from figma design | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 001.png |  | Solved |  | Fahad
BR-020 | Landing Page | Home Screen | Divider line misalignment issue | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 002.png |  | Solved |  | Fahad
BR-021 | Landing Page | Home Screen | Noticed different option compared to Figma. | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 003.png |  | Solved |  | Fahad
BR-022 | Landing Page | Home Screen | Noticed a difference in how the profile name and pet name are displayed in the app compared to Figma. | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 004.png |  | Solved |  | Fahad
BR-023 | Landing Page | Home Screen | User profile and pet profile failed to load | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | User profile and pet profile should be visible in app | Failed to load profile of user and pet. Authorization token missing | Fail | High | 005.mp4 |  | Solved |  | Fahad
BR-024 | Landing Page | Home Screen | same operation in different method | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential | User Credential | Operation method should be one way | Multiple method for one operation | Fail | Low | 012.png |  | Solved |  | Fahad
BR-025 | Landing Page | Home Screen | Different UI for Home button | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential | User Credential | App UI should be as same as figma design | Noticed a slightly different design for Home button in the APK. | Fail | Low | 013.png |  | Solved |  | Fahad
BR-026 | Landing Page | Home Screen | Gesture overlay issue | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential | User Credential | Phone UI gesture overlay with App UI | UI should not overlapped with phone UI | Fail | High | 034.png |  | Unsolve |  | Fahad
BR-027 | Landing Page | Home Screen | AI Chatbot missing in home screen | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential | User Credential | AI chatbot should be present in home screen as per as client requirement | Missing AI chatbot in home screen | Fail | High | 035.png |  |  | Client will be implement later | Fahad
BR-028 | Landing Page | Home Screen | Encountered a request timeout | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | User should be able to use the app without encountering request time out | Faced request timeout in home screen | Fail | High | 046.png |  | Solved |  | Fahad
BR-029 | Landing Page | Home Screen | Unable to display updated profile picture | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | The updated profile picture should load quickly and appear seamlessly. | Failed to display updated profile picture | Fail | Medium | 048.png |  | Solved |  | Fahad
BR-030 | Landing Page | Home Screen | Recent post is not displayed at top | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | Recent post should be displayed at top of home screen | The top post was published an hour ago, and the second post was shared recently. | Fail | Medium | 050.mp4 |  | Solved |  | Fahad
BR-031 | Landing Page | Landing Page | Different landing page than in Figma | User need to download the Petzy apk file in their mobile device | 1. Open app | User Credential | Design and alignment should be as same as figma | Differen icon noticed | Fail | Medium | 077.png |  | Solved |  | Fahad
BR-032 | Landing Page | Landing Page | The back button closes the app immediately without prompting the user to confirm if they want to exit. | User need to download the Petzy apk file in their mobile device | 1. Open app | User Credential | Pressing the back button will take the user to the home page, and pressing it again will bring up a prompt asking if the client wants to quit the app. | App closes directly from the page | Fail | Medium | 083.mp4 |  |  |  | Fahad
BR-033 | Landing Page | Login Screen | The placeholder value is set as a number, not in a specific format. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | Placeholder value should be set as format, not as actual number | Actual phone number is set as placeholder value | Fail | Low | 006.png |  | Solved |  | Fahad
BR-034 | Landing Page | Login Screen | No limit set for input | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | Input field limit should be fixed . it should be 3-15 digit | There’s no limit set for the phone number input. | Fail | Medium | 008.png |  | Solved |  | Fahad
BR-035 | Landing Page | Login Screen | Naver & kakao login gateway is not implemented | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | All 3 payment login should be implemented | Only google login gateway is functional | Fail | High | 009.png |  | Solved | waiting for backend | Fahad
BR-036 | Landing Page | Login Screen | Overlapped issue in login page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | No overlapped issue should be visible in app | Faced overlapped issue in login paeg with keyboard | Fail | Medium | 010.png |  | Solved |  | Fahad
BR-037 | Landing Page | Menu | Same icon used for different feature | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Icon should be different for each feature | same icon used for different feature | Fail | Low | 014.png |  | Solved |  | Fahad
BR-038 | Landing Page | Menu | Notification icon is missing in quick access | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Design and features should be positioned accurately. | Notification feature is missing in the quick access | Fail | Low | 015.png |  | Solved | Need Remove From Figma | Fahad
BR-039 | Landing Page | Menu | missing icons of top hotel catagories | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Icons should be placed accurately in the app | Missing top hotel catagory icon | Fail | Medium | 016.png |  | Solved |  | Fahad
BR-040 | Landing Page | Menu | Top package category missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | The package list needs to be shown accurately. | Missing top package catagory is app | Fail | High | 017.png |  | Solved |  | Fahad
BR-041 | Landing Page | Menu | Server error in pet wash | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Pet wash | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 018.png |  | Solved |  | Fahad
BR-042 | Landing Page | Menu | Server error in pet grooming | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Pet grooming | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 019.png |  | Solved |  | Fahad
BR-043 | Landing Page | Menu | Server error in nail cutting | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Nail Cutting | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 020.png |  | Solved |  | Fahad
BR-044 | Landing Page | Menu | Server error in teeth cleaning section | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Teeth Cleaning | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 021.png |  | Solved |  | Fahad
BR-045 | Landing Page | Menu | Server error in paw cleaning | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Paw Cleaning | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 022.png |  | Solved |  | Fahad
BR-046 | Landing Page | OTP | Page flow broken.Failed to load OTP page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button 3. Input number and click login | N/A | Page flow should be accurate | OTP page missing in phone login section | Fail | High | 011.mp4 |  |  |  | Fahad
BR-047 | Landing Page | Profile | took more than 10 minutes to display updated profile picture | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto Profile section | User Credential | The updated profile picture should be displayed seamlessly. | Took more than waiting time to load and display the updated profile picture | Fail | Medium | 047.png |  | Solved |  | Fahad
BR-048 | Landing Page | Signup Screen | Required field are not mentioned in signup page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button 3. Click on signup | N/A | Required fields should be mentioned in input title | Not mentioned any required fields | Fail | Medium | 007.png |  | Solved |  | Fahad
BR-049 | Landing Page | Story | Failed to show others/friends story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | Story should be displayed properly | Failed to display story of others | Fail | High | 025.mp4 |  | Solved |  | Fahad
BR-050 | Menu | My Cart | The cart page failed to display the correct message. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Select My cart | User Credential | The page should display correctly even when the cart is empty. | Showing incorrect message when the cart is empty | Fail | High | 023.png |  | Solved |  | Fahad
BR-051 | Menu | Notification | JWT Expire message shown instead of notification | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Notification | User Credential | The app’s notifications should be displayed correctly. | Unable to display the correct notification. | Fail | Medium | 024.png |  | Solved | Processing | Fahad
BR-052 | Messages | Community | Wasn’t able to create the community. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on Community | User Credential | User should be able to create community without facing any issue | Failed to create community | Fail | High | 081.png |  | Unsolve |  | Fahad
BR-053 | Messages | Community | The cancel button isn’t working properly. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on community | User Credential | The cancel button needs to work properly. | The cancel button functionality failed. | Fail | High | 082.png |  | Solved |  | Fahad
BR-054 | Messages | Group | Encountering an error while trying to create a group. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on group | User Credential | User should be able to create group without facing any issue | Failed to create group | Fail | High | 079.png |  | Solved |  | Fahad
BR-055 | Messages | Group | The cancel button isn’t working properly. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on group | User Credential | The cancel button needs to work properly. | The cancel button functionality failed. | Fail | High | 080.png |  | Solved |  | Fahad
BR-056 | Messages | Messages | JWT token expired in message | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | Message should display to the user properly | Failed to open message. JWT token expire | Fail | High | 063.png |  | Solved |  | Fahad
BR-057 | Messages | Messages | No latest conversation found but title remains | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | If the content is visible, the title should appear. | No content available but title is displayed | Fail | Medium | 064.png |  | Solved |  | Fahad
BR-058 | Messages | Messages | The channel join button didn’t update after joining. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The Join button should change to Joined when a user joins a channel. | The join button still shows as "Join" even after the user has joined the channel. | Fail | Medium | 065.png |  | Solved |  | Fahad
BR-059 | Messages | Messages | Back button is not integrated in message page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The back button should be visible on every page. | No back button is visible in message page | Fail | High | 066.mp4 |  | Solved |  | Fahad
BR-060 | Messages | Messages | Button not functional | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The create group button should be functional. | Button is not functional | Fail | Medium | 067.png |  | Solved |  | Fahad
BR-061 | My Profile | Add Pet | Icon different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 068.png |  | Solved |  | Fahad
BR-062 | My Profile | Add Pet | weight icon is missing in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 069.png |  | Solved |  | Fahad
BR-063 | My Profile | Add Pet | Different icon used in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 070.png |  | Solved |  | Fahad
BR-064 | My Profile | Add Pet | Failed to add pet | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | User should be able to add pet in their profile | Failed to add pet | Fail | High | 071.png |  | Solved |  | Fahad
BR-065 | My Profile | My Profile | Friend request option missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | App UI and module should be as same as figma design | Module missing in app | Fail | High | 058.png |  | Solved | need fix ui/ux | Fahad
BR-066 | My Profile | My Profile | Change cover photo option missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | Features should be placed accurately according to the Figma design. | Feature missing in app | Fail | High | 059.png |  | Solved | Figma need change | Fahad
BR-067 | My Profile | My Profile | Add a pet option cut on side and it is scrollable which should be fit to window | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | It should be static and fit to window | Feature scrollable and cut on one side | Fail | Medium | 060.png |  | Solved |  | Fahad
BR-068 | My Profile | My Profile | Missing post option in profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | High | 061.png |  | Solved |  | Fahad
BR-069 | My Profile | My Profile | JWT token expire on my profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | The user should be able to view their profile without any problems. | JWT token expire in profile | Fail | High | 062.png |  | Solved |  | Fahad
BR-070 | Notification | Notification | Different UI implemented than figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Notification | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 031.png |  | Solved |  | Fahad
BR-071 | Notification | Notification | Different UI implemented than figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Notification | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 032.png |  | Solved |  | Fahad
BR-072 | Pet Hotel | Pet Hotel | The booking icon is missing in the pet hotel. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 085.png |  | Solved |  | Fahad
BR-073 | Pet Hotel | Pet Hotel | pension stay and apartment hotel missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 086.png |  | Solved |  | Fahad
BR-074 | Pet Hotel | Pet Hotel | Can't add as a wishlist | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | It should store the wishlist data and display it on the pet hotel page. | Unable to store and display data in the pet hotel system. | Fail | High | 087.mp4 |  |  |  | Fahad
BR-075 | Pet Hotel | Pet Hotel | Share option is not integrated in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a pet hotel | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 088.png |  | Solved |  | Fahad
BR-076 | Pet Hotel | Pet Hotel | The booking icon is missing in the pet hotel. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 089.png |  | Solved |  | Fahad
BR-077 | Pet Hotel | Pet Hotel | country code is not implemented | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Contry code in phone number input field should be placed perfectly | Missing contry code in phone number input field | Fail | Low | 090.png |  |  |  | Fahad
BR-078 | Pet Hotel | Pet Hotel | Hotel was suggested twice | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The suggested hotel card should only appear once. | The hotel card appears multiple times. | Fail | Medium | 091.png |  |  |  | Fahad
BR-079 | Pet Hotel | Pet Hotel | missing location in filter which was designed in figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 092.png |  |  |  | Fahad
BR-080 | Pet Hotel | Pet Hotel | Same icon set in all category which was missing in figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 093.png |  |  |  | Fahad
BR-081 | Pet Hotel | Pet Hotel | It’s set as static, but in the design, it should pop up within the page layout. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 094.png |  |  |  | Fahad
BR-082 | Pet Hotel | Pet Hotel | Missing client name in review | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 095.png |  |  |  | Fahad
BR-083 | Pet Hotel | Pet Hotel | Unable to make payment | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The user should be able to make a payment and book a hotel without any issues. | Unable to book hotel and make payment | Fail | High | 096.png |  |  |  | Fahad
BR-084 | Pet Hotel | Pet Hotel | UI is different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 097.png |  |  |  | Fahad
BR-085 | Pet Hotel | Pet Hotel | The coupon cannot be used after it has been selected. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Users should be able to use a coupon if it’s displayed. | Couldn't use the coupon after selecting it | Fail | High | 098.png |  |  |  | Fahad
BR-086 | Pet Hotel | Pet Hotel | UI is different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 099.png |  |  |  | Fahad
BR-087 | Pet Hotel | Pet Hotel | Chat option missing in hotel profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 100.png |  |  |  | Fahad
BR-088 | QR | QR | Failed to scan QR code from image | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on QR | User Credential | Should be able to scan qt data properly | Failed to scan qr data from image | Fail | Medium | 033.mp4 |  | Solved |  | Fahad
BR-089 | Shorts | Comment | Reply on comment is not integrated | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on shorts 4. Click on comment | User Credential | User should be able to reply on comment in short section | Failed to reply on comment and like comment | Fail | High | 036.png |  | Solved |  | Fahad
BR-090 | Shorts | Like | JWT token expire on like button | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Shorts | User Credential | User should be able to like shorts video | Failed to store like on shorts , JWT token expires | Fail | High | 029.png |  | Solved |  | Fahad
BR-091 | Shorts | Shorts | The displayed video and the actual video are not the same. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on shorts | User Credential | The thumbnail video and the actual video should be the same. | The video and thumbnail should be the same. | Fail | Medium | 084.mp4 |  | Solved |  | Fahad
BR-092 | Shorts | Upload | JWT token expire. Unable to upload shorts video | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Shorts | User Credential | User should be able to upload shorts video without facing any issues | Failed to upload shorts , JWT token expires | Fail | High | 030.png |  | Solved |  | Fahad
BR-093 | Story | Story | Location picker is not integrated | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | Location picker should be integrated in the location input field | Manual location input has been noticed | Fail | Medium | 026.png |  | Solved |  | Fahad
BR-094 | Story | Story | Can share images as stories, but sharing live videos in stories isn’t available. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | User should be able to share live capture image and video as story | Only live capture image is shareble in story but video is not | Fail | High | 027.png |  | Solved |  | Fahad
BR-095 | Story | Story | unable to upload story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Story | User Credential | The story should upload smoothly without any errors. | Failed to upload story. JWT token expires | Fail | High | 028.png |  | Solved |  | Fahad
BR-096 | Story | Story | Failed to upload story. Request timeout | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | User should be able to upload story without any issue | Failed to upload story | Fail | High | 055.mp4 |  | Solved |  | Fahad
BR-097 | Story | Story | After upload story, page doesn't redirect to home | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | After successful story upload, it should redirect to home page | Stays in create story page after uploading a story | Fail | Medium | 056.mp4 |  | Solved |  | Fahad
BR-098 | Story | Story | Failed to view story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | User should be able to see story without any issue | Failed to display uploaded story | Fail | High | 057.mp4 |  | Solved |  | Fahad
BR-099 | Story | Story | Uploaded a different image, but this one was displayed instead. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | Users should be able to update their preferred picture as a story. | The default image is showing as the story instead of the one selected. | Fail | High | 074.png |  | Solved |  | Fahad
BR-100 | Story | Story | The story countdown timer logic hasn’t been implemented yet. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | The story will be visible 24 hours after uploading. | The story expiration timer logic has not been implemented. | Fail | High | 078.png |  | Solved |  | Fahad

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Petzy
Developer: | Softvence
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | realme C63 model : RMX3939 Android Version : 15 Dimention : (6.59 x 3.02 x 0.30)in | [11 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack
BR_001 | Landing Page | Home Screen | Different UI design in app from figma design | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 001.png |  | Solved
BR_002 | Landing Page | Home Screen | Divider line misalignment issue | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 002.png |  | Solved
BR_003 | Landing Page | Home Screen | Noticed different option compared to Figma. | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 003.png |  | Solved
BR_004 | Landing Page | Home Screen | Noticed a difference in how the profile name and pet name are displayed in the app compared to Figma. | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | App UI should be as same as figma design | Noticed a slightly different design in the APK. | Fail | Low | 004.png |  | Solved
BR_005 | Landing Page | Home Screen | User profile and pet profile failed to load | User need to download the Petzy apk file in their mobile device | 1. Open app | N/A | User profile and pet profile should be visible in app | Failed to load profile of user and pet. Authorization token missing | Fail | High | 005.mp4 |  | Solved
BR_006 | Landing Page | Login Screen | The placeholder value is set as a number, not in a specific format. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | Placeholder value should be set as format, not as actual number | Actual phone number is set as placeholder value | Fail | Low | 006.png |  | Solved
BR_007 | Landing Page | Signup Screen | Required field are not mentioned in signup page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button 3. Click on signup | N/A | Required fields should be mentioned in input title | Not mentioned any required fields | Fail | Medium | 007.png |  | Solved
BR_008 | Landing Page | Login Screen | No limit set for input | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | Input field limit should be fixed . it should be 3-15 digit | There’s no limit set for the phone number input. | Fail | Medium | 008.png |  | Solved
BR_009 | Landing Page | Login Screen | Naver & kakao login gateway is not implemented | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | All 3 payment login should be implemented | Only google login gateway is functional | Fail | High | 009.png |  | Solved | waiting for backend
BR_010 | Landing Page | Login Screen | Overlapped issue in login page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button | N/A | No overlapped issue should be visible in app | Faced overlapped issue in login paeg with keyboard | Fail | Medium | 010.png |  | Solved
BR_011 | Landing Page | OTP | Page flow broken.Failed to load OTP page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Click on Login Button 3. Input number and click login | N/A | Page flow should be accurate | OTP page missing in phone login section | Fail | High | 011.mp4
BR_012 | Landing Page | Home Screen | same operation in different method | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential | User Credential | Operation method should be one way | Multiple method for one operation | Fail | Low | 012.png |  | Solved
BR_013 | Landing Page | Home Screen | Different UI for Home button | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential | User Credential | App UI should be as same as figma design | Noticed a slightly different design for Home button in the APK. | Fail | Low | 013.png |  | Solved
BR_014 | Landing Page | Menu | Same icon used for different feature | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Icon should be different for each feature | same icon used for different feature | Fail | Low | 014.png |  | Solved
BR_015 | Landing Page | Menu | Notification icon is missing in quick access | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Design and features should be positioned accurately. | Notification feature is missing in the quick access | Fail | Low | 015.png |  | Solved | Need Remove From Figma
BR_016 | Landing Page | Menu | missing icons of top hotel catagories | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | Icons should be placed accurately in the app | Missing top hotel catagory icon | Fail | Medium | 016.png |  | Solved
BR_017 | Landing Page | Menu | Top package category missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu | User Credential | The package list needs to be shown accurately. | Missing top package catagory is app | Fail | High | 017.png |  | Solved
BR_018 | Landing Page | Menu | Server error in pet wash | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Pet wash | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 018.png |  | Solved
BR_019 | Landing Page | Menu | Server error in pet grooming | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Pet grooming | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 019.png |  | Solved
BR_020 | Landing Page | Menu | Server error in nail cutting | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Nail Cutting | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 020.png |  | Solved
BR_021 | Landing Page | Menu | Server error in teeth cleaning section | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Teeth Cleaning | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 021.png |  | Solved
BR_022 | Landing Page | Menu | Server error in paw cleaning | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Paw Cleaning | User Credential | Should not display server error in app on client side | Shows server error in app | Fail | High | 022.png |  | Solved
BR_023 | Menu | My Cart | The cart page failed to display the correct message. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Select My cart | User Credential | The page should display correctly even when the cart is empty. | Showing incorrect message when the cart is empty | Fail | High | 023.png |  | Solved
BR_024 | Menu | Notification | JWT Expire message shown instead of notification | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on menu 4. Click on Notification | User Credential | The app’s notifications should be displayed correctly. | Unable to display the correct notification. | Fail | Medium | 024.png |  | Solved | Processing
BR_025 | Landing Page | Story | Failed to show others/friends story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | Story should be displayed properly | Failed to display story of others | Fail | High | 025.mp4 |  | Solved
BR_026 | Story | Story | Location picker is not integrated | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | Location picker should be integrated in the location input field | Manual location input has been noticed | Fail | Medium | 026.png |  | Solved
BR_027 | Story | Story | Can share images as stories, but sharing live videos in stories isn’t available. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Friends Story | User Credential | User should be able to share live capture image and video as story | Only live capture image is shareble in story but video is not | Fail | High | 027.png |  | Solved
BR_028 | Story | Story | unable to upload story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Story | User Credential | The story should upload smoothly without any errors. | Failed to upload story. JWT token expires | Fail | High | 028.png |  | Solved
BR_029 | Shorts | Like | JWT token expire on like button | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Shorts | User Credential | User should be able to like shorts video | Failed to store like on shorts , JWT token expires | Fail | High | 029.png |  | Solved
BR_030 | Shorts | Upload | JWT token expire. Unable to upload shorts video | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Shorts | User Credential | User should be able to upload shorts video without facing any issues | Failed to upload shorts , JWT token expires | Fail | High | 030.png |  | Solved
BR_031 | Notification | Notification | Different UI implemented than figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Notification | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 031.png |  | Solved
BR_032 | Notification | Notification | Different UI implemented than figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using Valid Credential 3. Click on Notification | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 032.png |  | Solved
BR_033 | QR | QR | Failed to scan QR code from image | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on QR | User Credential | Should be able to scan qt data properly | Failed to scan qr data from image | Fail | Medium | 033.mp4 |  | Solved
BR_034 | Landing Page | Home Screen | Gesture overlay issue | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential | User Credential | Phone UI gesture overlay with App UI | UI should not overlapped with phone UI | Fail | High | 034.png |  | Unsolve
BR_035 | Landing Page | Home Screen | AI Chatbot missing in home screen | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential | User Credential | AI chatbot should be present in home screen as per as client requirement | Missing AI chatbot in home screen | Fail | High | 035.png |  |  | Client will be implement later
BR_036 | Shorts | Comment | Reply on comment is not integrated | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on shorts 4. Click on comment | User Credential | User should be able to reply on comment in short section | Failed to reply on comment and like comment | Fail | High | 036.png |  | Solved
BR_037 | Booking | Booking | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on booking in bottom option | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 037.png |  | Solved | Please check Update Apk
BR_038 | Booking | Booking | Booking button in booking page which is not functional | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on booking in bottom option | User Credential | The functional button should be positioned accurately. | Booking button placed in filter button place | Fail | High | 038.png |  | Solved | Please check Update Apk
BR_039 | Community | Community | Add photo section missing in community | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | The UI should match the Figma design accurately. | Add photo button missing in community section | Fail | High | 039.png |  | Solved | Please check Update Apk
BR_040 | Community | Community | Failed to display pet name in community post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | User and pet name should be displayed as per as client requirement | Failed to display pet name with user name in community post | Fail | High | 040.png |  | Solved
BR_041 | Community | Community | Options like Report, Don’t Recommend, and similar features found on Facebook are missing. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community | User Credential | Should be implement as per as client requirement | Missing feature | Fail | High | 041.png |  | Unsolve
BR_042 | Community | Community | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 042.png |  | Solved | Figma will update
BR_043 | Community | Community | Share post button placement issue | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 043.png |  | Solved
BR_044 | Community | Community | The UI looks different from the Figma design. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 044.png |  | Solved
BR_045 | Community | Community | The feature didn’t work. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Community 4. Click on post | User Credential | Functionality needs to be precise. | Unable to open gif | Fail | High | 045.png |  | Solved | Rmoved this feature
BR_046 | Landing Page | Home Screen | Encountered a request timeout | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | User should be able to use the app without encountering request time out | Faced request timeout in home screen | Fail | High | 046.png |  | Solved
BR_047 | Landing Page | Profile | took more than 10 minutes to display updated profile picture | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto Profile section | User Credential | The updated profile picture should be displayed seamlessly. | Took more than waiting time to load and display the updated profile picture | Fail | Medium | 047.png |  | Solved
BR_048 | Landing Page | Home Screen | Unable to display updated profile picture | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | The updated profile picture should load quickly and appear seamlessly. | Failed to display updated profile picture | Fail | Medium | 048.png |  | Solved
BR_049 | Community | Location | Selected 2nd one but 1st one also shown as selected | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | Only one location should be selected | Shown multiple location selected but only one location is selected | Fail | Medium | 049.png |  | Solved
BR_050 | Landing Page | Home Screen | Recent post is not displayed at top | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home | User Credential | Recent post should be displayed at top of home screen | The top post was published an hour ago, and the second post was shared recently. | Fail | Medium | 050.mp4 |  | Solved
BR_051 | Home Screen | Post | UI different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Low | 051.png |  | Solved
BR_052 | Home Screen | Post | Unable to see who like the post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | User should be able to see who liked the post | Unable to see who liked the post | Fail | High | 052.png |  | Solved
BR_053 | Home Screen | Post | Positioned in a different place; it should be on the right side. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | Medium | 053.png |  | Solved | ui need fixed
BR_054 | Home Screen | Post | Replies should expand when clicked | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Replies should start collapsed and expand when clicked. | Replies are expanded all the time. Static page | Fail | Low | 054.png |  | Solved
BR_055 | Story | Story | Failed to upload story. Request timeout | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | User should be able to upload story without any issue | Failed to upload story | Fail | High | 055.mp4 |  | Solved
BR_056 | Story | Story | After upload story, page doesn't redirect to home | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | After successful story upload, it should redirect to home page | Stays in create story page after uploading a story | Fail | Medium | 056.mp4 |  | Solved
BR_057 | Story | Story | Failed to view story | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | User should be able to see story without any issue | Failed to display uploaded story | Fail | High | 057.mp4 |  | Solved
BR_058 | My Profile | My Profile | Friend request option missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | App UI and module should be as same as figma design | Module missing in app | Fail | High | 058.png |  | Solved | need fix ui/ux
BR_059 | My Profile | My Profile | Change cover photo option missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | Features should be placed accurately according to the Figma design. | Feature missing in app | Fail | High | 059.png |  | Solved | Figma need change
BR_060 | My Profile | My Profile | Add a pet option cut on side and it is scrollable which should be fit to window | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | It should be static and fit to window | Feature scrollable and cut on one side | Fail | Medium | 060.png |  | Solved
BR_061 | My Profile | My Profile | Missing post option in profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | App UI should be as same as figma design | Different design noticed in apk | Fail | High | 061.png |  | Solved
BR_062 | My Profile | My Profile | JWT token expire on my profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile | User Credential | The user should be able to view their profile without any problems. | JWT token expire in profile | Fail | High | 062.png |  | Solved
BR_063 | Messages | Messages | JWT token expired in message | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | Message should display to the user properly | Failed to open message. JWT token expire | Fail | High | 063.png |  | Solved
BR_064 | Messages | Messages | No latest conversation found but title remains | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | If the content is visible, the title should appear. | No content available but title is displayed | Fail | Medium | 064.png |  | Solved
BR_065 | Messages | Messages | The channel join button didn’t update after joining. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The Join button should change to Joined when a user joins a channel. | The join button still shows as "Join" even after the user has joined the channel. | Fail | Medium | 065.png |  | Solved
BR_066 | Messages | Messages | Back button is not integrated in message page | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The back button should be visible on every page. | No back button is visible in message page | Fail | High | 066.mp4 |  | Solved
BR_067 | Messages | Messages | Button not functional | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages | User Credential | The create group button should be functional. | Button is not functional | Fail | Medium | 067.png |  | Solved
BR_068 | My Profile | Add Pet | Icon different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 068.png |  | Solved
BR_069 | My Profile | Add Pet | weight icon is missing in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 069.png |  | Solved
BR_070 | My Profile | Add Pet | Different icon used in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | Design and icon should be as same as figma | Differen icon noticed | Fail | Low | 070.png |  | Solved
BR_071 | My Profile | Add Pet | Failed to add pet | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Goto my profile 4. Click on Add Pet | User Credential | User should be able to add pet in their profile | Failed to add pet | Fail | High | 071.png |  | Solved
BR_072 | Home Screen | Post | Alignment issue in post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Design and alignment should be as same as figma | Differen icon noticed | Fail | Medium | 072.png |  | Solved
BR_073 | Home Screen | Post | Tag's should be clickable | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | Tags should be clickable and able to filter posts based on the keyword. | Tags are normal text | Fail | Medium | 073.png |  | Solved
BR_074 | Story | Story | Uploaded a different image, but this one was displayed instead. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | Users should be able to update their preferred picture as a story. | The default image is showing as the story instead of the one selected. | Fail | High | 074.png |  | Solved
BR_075 | Home Screen | Post | The post is available, but the user profile couldn’t be found. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | A user's profile should be visible once their post is published. | Post found, but the user profile is missing. | Fail | High | 075.mp4 |  | Solved
BR_076 | Home Screen | Post | Unable to upload the post | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Home 4. Click on post | User Credential | The user should be able to upload a post without any issues. | Post upload failed | Fail | High | 076.png |  | Solved
BR_077 | Landing Page | Landing Page | Different landing page than in Figma | User need to download the Petzy apk file in their mobile device | 1. Open app | User Credential | Design and alignment should be as same as figma | Differen icon noticed | Fail | Medium | 077.png |  | Solved
BR_078 | Story | Story | The story countdown timer logic hasn’t been implemented yet. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Story | User Credential | The story will be visible 24 hours after uploading. | The story expiration timer logic has not been implemented. | Fail | High | 078.png |  | Solved
BR_079 | Messages | Group | Encountering an error while trying to create a group. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on group | User Credential | User should be able to create group without facing any issue | Failed to create group | Fail | High | 079.png |  | Solved
BR_080 | Messages | Group | The cancel button isn’t working properly. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on group | User Credential | The cancel button needs to work properly. | The cancel button functionality failed. | Fail | High | 080.png |  | Solved
BR_081 | Messages | Community | Wasn’t able to create the community. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on Community | User Credential | User should be able to create community without facing any issue | Failed to create community | Fail | High | 081.png |  | Unsolve
BR_082 | Messages | Community | The cancel button isn’t working properly. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Messages 4. Click on community | User Credential | The cancel button needs to work properly. | The cancel button functionality failed. | Fail | High | 082.png |  | Solved
BR_083 | Landing Page | Landing Page | The back button closes the app immediately without prompting the user to confirm if they want to exit. | User need to download the Petzy apk file in their mobile device | 1. Open app | User Credential | Pressing the back button will take the user to the home page, and pressing it again will bring up a prompt asking if the client wants to quit the app. | App closes directly from the page | Fail | Medium | 083.mp4
BR_084 | Shorts | Shorts | The displayed video and the actual video are not the same. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on shorts | User Credential | The thumbnail video and the actual video should be the same. | The video and thumbnail should be the same. | Fail | Medium | 084.mp4 |  | Solved
BR_085 | Pet Hotel | Pet Hotel | The booking icon is missing in the pet hotel. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 085.png |  | Solved
BR_086 | Pet Hotel | Pet Hotel | pension stay and apartment hotel missing | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 086.png |  | Solved
BR_087 | Pet Hotel | Pet Hotel | Can't add as a wishlist | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel | User Credential | It should store the wishlist data and display it on the pet hotel page. | Unable to store and display data in the pet hotel system. | Fail | High | 087.mp4
BR_088 | Pet Hotel | Pet Hotel | Share option is not integrated in app | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a pet hotel | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 088.png |  | Solved
BR_089 | Pet Hotel | Pet Hotel | The booking icon is missing in the pet hotel. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The icon and design should match exactly as they appear in Figma. | A difference between the app and Figma has been noticed. | Fail | Medium | 089.png |  | Solved
BR_090 | Pet Hotel | Pet Hotel | country code is not implemented | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Contry code in phone number input field should be placed perfectly | Missing contry code in phone number input field | Fail | Low | 090.png
BR_091 | Pet Hotel | Pet Hotel | Hotel was suggested twice | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The suggested hotel card should only appear once. | The hotel card appears multiple times. | Fail | Medium | 091.png
BR_092 | Pet Hotel | Pet Hotel | missing location in filter which was designed in figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 092.png
BR_093 | Pet Hotel | Pet Hotel | Same icon set in all category which was missing in figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 093.png
BR_094 | Pet Hotel | Pet Hotel | It’s set as static, but in the design, it should pop up within the page layout. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 094.png
BR_095 | Pet Hotel | Pet Hotel | Missing client name in review | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 095.png
BR_096 | Pet Hotel | Pet Hotel | Unable to make payment | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | The user should be able to make a payment and book a hotel without any issues. | Unable to book hotel and make payment | Fail | High | 096.png
BR_097 | Pet Hotel | Pet Hotel | UI is different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 097.png
BR_098 | Pet Hotel | Pet Hotel | The coupon cannot be used after it has been selected. | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Users should be able to use a coupon if it’s displayed. | Couldn't use the coupon after selecting it | Fail | High | 098.png
BR_099 | Pet Hotel | Pet Hotel | UI is different from figma | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | Medium | 099.png
BR_100 | Pet Hotel | Pet Hotel | Chat option missing in hotel profile | User need to download the Petzy apk file in their mobile device | 1. Open app 2. Login using valid credential 3. Click on Menu 4. Select Pet Hotel 5. Select a hotel and click on book icon | User Credential | Design and featue should be as same as figma | The share option in the app is missing, even though it’s available in Figma. | Fail | High | 100.png
BR_101
BR_102
BR_103
BR_104
BR_105
BR_106
BR_107
BR_108
BR_109

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Booking | Booking | BR-001, BR-002 | 2 | 2.00% | High: 1 Medium: 0 Low: 1
Community | Community | BR-003, BR-004, BR-005, BR-006, BR-007, BR-008, BR-009 | 7 | 7.00% | High: 4 Medium: 2 Low: 1
Community | Location | BR-010 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Home Screen | Post | BR-011, BR-012, BR-013, BR-014, BR-015, BR-016, BR-017, BR-018 | 8 | 8.00% | High: 3 Medium: 3 Low: 2
Landing Page | Home Screen | BR-019, BR-020, BR-021, BR-022, BR-023, BR-024, BR-025, BR-026, BR-027, BR-028, BR-029, BR-030 | 12 | 12.00% | High: 4 Medium: 2 Low: 6
Landing Page | Landing Page | BR-031, BR-032 | 2 | 2.00% | High: 0 Medium: 2 Low: 0
Landing Page | Login Screen | BR-033, BR-034, BR-035, BR-036 | 4 | 4.00% | High: 1 Medium: 2 Low: 1
Landing Page | Menu | BR-037, BR-038, BR-039, BR-040, BR-041, BR-042, BR-043, BR-044, BR-045 | 9 | 9.00% | High: 6 Medium: 1 Low: 2
Landing Page | OTP | BR-046 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Landing Page | Profile | BR-047 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Landing Page | Signup Screen | BR-048 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Landing Page | Story | BR-049 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Menu | My Cart | BR-050 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Menu | Notification | BR-051 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Messages | Community | BR-052, BR-053 | 2 | 2.00% | High: 2 Medium: 0 Low: 0
Messages | Group | BR-054, BR-055 | 2 | 2.00% | High: 2 Medium: 0 Low: 0
Messages | Messages | BR-056, BR-057, BR-058, BR-059, BR-060 | 5 | 5.00% | High: 2 Medium: 3 Low: 0
My Profile | Add Pet | BR-061, BR-062, BR-063, BR-064 | 4 | 4.00% | High: 1 Medium: 0 Low: 3
My Profile | My Profile | BR-065, BR-066, BR-067, BR-068, BR-069 | 5 | 5.00% | High: 4 Medium: 1 Low: 0
Notification | Notification | BR-070, BR-071 | 2 | 2.00% | High: 0 Medium: 0 Low: 2
Pet Hotel | Pet Hotel | BR-072, BR-073, BR-074, BR-075, BR-076, BR-077, BR-078, BR-079, BR-080, BR-081, BR-082, BR-083, BR-084, BR-085, BR-086, BR-087 | 16 | 16.00% | High: 8 Medium: 7 Low: 1
QR | QR | BR-088 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Shorts | Comment | BR-089 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Shorts | Like | BR-090 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Shorts | Shorts | BR-091 | 1 | 1.00% | High: 0 Medium: 1 Low: 0
Shorts | Upload | BR-092 | 1 | 1.00% | High: 1 Medium: 0 Low: 0
Story | Story | BR-093, BR-094, BR-095, BR-096, BR-097, BR-098, BR-099, BR-100 | 8 | 8.00% | High: 6 Medium: 2 Low: 0

## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback