## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: | Thai Massage |  | High | 17
Project URL: |  |  | Medium | 9
Developer: | AI Venture |  | Low | 21
OS:
Environment |  |  | Total Test Cases: | 47
|  |  | Test Case Solved : | 16
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Comment
BR-001 | Client (APK) | Add card | Simplify the card addition bar in the mobile app. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | All payment card gateways should be clearly visible to the client. | A reduction in the payment card border has been observed. | Fail | Medium | https://drive.google.com/file/d/1u29w_Wa7h4bOdm9m9WXAH4cPvm-ZdEVi/view?usp=drive_link |  | Fahad
BR-002 | Client (APK) | Appointment | The location details input field is slightly different from the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1F6zNQsG49gDUpfguLk-u9nFlyuXhBEkF/view?usp=drive_link |  | Fahad | Solved
BR-003 | Client (APK) | Appointment | The age preference does not align with the client requirement. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1loH6gbOEVYxwdpQtNm0INqLyHo92xJbM/view?usp=drive_link |  | Fahad | Solved
BR-004 | Client (APK) | Appointment | Error bars on selected therapist schedules | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The error bar should not be visible on the client side. | An error bar on the "Done" button in the select schedule section has been identified. | Fail | Medium | https://drive.google.com/file/d/1IeVWxa2y6sKCMgIvz9n6y_GsWL13OHBt/view?usp=drive_link |  | Fahad | Solved
BR-005 | Client (APK) | Appointment | The agree button overlaps with the section bar. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The field shadow effect should not exceed its boundary. | The cross-boundary effect has been observed. | Fail | Low | https://drive.google.com/file/d/1haRoWx_fzP2CktG0LbdGtOVcBGkZOyAs/view?usp=drive_link |  | Fahad | Solved
BR-006 | Client (APK) | Appointment | The layout varies for questions about medical appointments. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/15VG_T_k1OUzSG0xdJjXgTgkniEmLBDiK/view?usp=drive_link |  | Fahad | Solved
BR-007 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/13exhdxanyYbRnL4ACc2CJe65OBwTpcvO/view?usp=drive_link |  | Fahad | Solved
BR-008 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1nkwEoAO2orWPxnW4t-8bcBiKzHGDoJ3k/view?usp=drive_link |  | Fahad | Solved
BR-009 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/14x0H8Cj1yGkq9nIRIMEkEh_BrqGUHyb1/view?usp=drive_link |  | Fahad | Solved
BR-010 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Medical questions should be properly submitted without any issues. | Unable to submit client medical questions via the app. | Fail | High | https://drive.google.com/file/d/1NY-OIs6XpToQOBkdBXzOT54gHBKu1Cqs/view?usp=drive_link |  | Fahad | Solved
BR-011 | Client (APK) | Bookings | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1XULhwCogBaakOiUDnvk7CeZvdJsu3sA8/view?usp=drive_link |  | Fahad | Unsolved
BR-012 | Client (APK) | Bookings | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1ZMLGhPiBHCYWW_rYz_vdbn7yGqNo7ufB/view?usp=drive_link |  | Fahad | Solved
BR-013 | Client (APK) | Bookings | The review option is missing in the booking. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Users should have the option to rate their therapist in the booking section after receiving therapy. | Missing review option found. | Fail | Medium | https://drive.google.com/file/d/1fdwYRTVFwtxj4a2cQUcNE-JxcPItyks3/view?usp=drive_link |  | Fahad | Solved
BR-014 | Client (APK) | Bookings | Cancellation policy alignment and design concern. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | The paragraph title in the cancellation policy should be bold and easily noticeable. | An alignment issue was identified, and the bold formatting for the text topic is also missing. | Fail | Low | https://drive.google.com/file/d/1rJLjMwI8nniNOY5xZ4xPNHNk_XH0otlu/view?usp=drive_link |  | Fahad | Solved | Client approval
BR-015 | Client (APK) | Card Information | An overflow bar has been observed in the card information. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | No overflow bar should appear from the client's perspective. | The overflow bar appears on card information where the card number format is provided. | Fail | High | https://drive.google.com/file/d/1tkCaCf4ymxthAx4ysDqpZc37wM_ilSrc/view?usp=drive_link |  | Fahad | Unsolved
BR-016 | Client (APK) | Card Information | Data validation is yet to be implemented. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Can you use random characters and special symbols in the expiry date and CVV fields on card information? | Specific formatting should be applied to card data information, and accurate data validation formatting should be implemented. | Fail | High | https://drive.google.com/file/d/1dDJVgs6mWVi6alCalMXd7yxJHutTTxwX/view?usp=drive_link |  | Fahad | Solved
BR-017 | Client (APK) | Chat | The chat and call section is missing in the APK. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | The chat section should include both chat and call logs to ensure client satisfaction and enable tracking. | The call log is missing in the chat section. | Fail | High | https://drive.google.com/file/d/1GnNqqEV4v5p5Ljd7anvErcGqlXhXMURA/view?usp=drive_link |  | Fahad | Solved
BR-018 | Client (APK) | Chat | The call option is missing in the chat. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | A call option in chat should be available for clients to directly call the therapist for further assistance. | The absence of a call option in the chat has been noted. | Fail | High | https://drive.google.com/file/d/1MU7PrtlmpF0l9Kd6tOG3EKwmh-MN_iBj/view?usp=drive_link |  | Fahad | Solved
BR-019 | Client (APK) | Chat | Sending voice messages from chat is missing. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | A voice send option should be integrated into chat for a better user experience. | The absence of the voice button has been observed. | Fail | High | https://drive.google.com/file/d/1bdn-YJqS2VeAxlTuwYjr7VDnlWXHIEiW/view?usp=drive_link |  | Fahad | Solved
BR-020 | Client (APK) | Chat | The option to send pictures is missing in the app. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | Adding a send picture option to the app would enhance the user experience. | The missing option for sending pictures has been noticed. | Fail | High | https://drive.google.com/file/d/1j8uc21xxRQ_ITR17s6bei4f8y8S6KfZm/view?usp=drive_link |  | Fahad
BR-021 | Client (APK) | Chat | The pattern of sending voice messages is different. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1qvXSarQEFjZqbinUQeb_-yuLm_mOg4ue/view?usp=drive_link |  | Fahad
BR-022 | Client (APK) | Forget Password | Forgot password OTP is set to email instead of phone number. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Forget Password | N/A | The password reset OTP should align with the client's requirements. | The OTP for the password reset was sent via email instead of the phone number, which did not align with the client's requirements. | Fail | High | https://drive.google.com/file/d/1KLex23-Fe5dyghKSBYH7lkrzS1-6VG83/view?usp=drive_link |  | Fahad
BR-023 | Client (APK) | Home | Category "See All" button is missing. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | A "See All" button in the category should be included, allowing clients to view all types of massages and select the one that suits them best. | The absence of a "See All" button in the category section might prevent users from accessing the full range of massage categories. | Fail | High | https://drive.google.com/file/d/1WdUwhoAKw9VJZP45R6Lp1FmGJsyFdL6E/view?usp=drive_link |  | Fahad
BR-024 | Client (APK) | Home | Therapist names are missing in the Nearby Therapist section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Therapists nearby should be easily accessible to clients, ensuring shorter travel distances and better engagement. | Unable to refresh the list of nearby therapists. | Fail | High | https://drive.google.com/file/d/1vRuK4G_c6ytmt6_kN1NbkV66uglkd5sg/view?usp=drive_link |  | Fahad
BR-025 | Client (APK) | Home | The therapist search feature is not working. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click search bar | email: lowovip595@elobits.com password: 112244557788 | Recommended and searched therapists should appear correctly in the search field. | The search functionality is broken, but therapists can be found using filters. | Fail | High | https://drive.google.com/file/d/1YMgFbIWV65v8MTTx_AxcKyawpTNmhx-6/view?usp=drive_link |  | Fahad
BR-026 | Client (APK) | Login | The login and signup buttons remain as "Client" when the user has already selected "Client" in a previous operation. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button | N/A | Button names should align with client requirements. | The button name "Login as client" is displayed instead of "Login." | Fail | Low | https://jam.dev/c/ee57675a-f88f-48a4-a150-f334c0b3b244 |  | Fahad
BR-027 | Client (APK) | Login | The app logo appears slightly shorter than usual. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login | N/A | The app logo should be prominently displayed to catch users' attention. | A slightly shorter logo was noticed. | Fail | Low | 1.png | Make it slightly larger to catch the user's attention. | Fahad
BR-028 | Client (APK) | Login | The password visibility icon is missing on the client login page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login | N/A | The password field should display the password visibly with a hide icon to enhance user convenience. | The absence of the password visibility icon has been noted. | Fail | Medium | https://jam.dev/c/7e6fdbbf-6f54-4449-933b-872542d4e03c |  | Fahad
BR-029 | Client (APK) | Notification | Notification failed to load | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Notification Section | email: lowovip595@elobits.com password: 112244557788 | Notifications should load correctly on the client side for smoother interaction. | Notification missing. Error displayed: No room found. | Fail | High | https://drive.google.com/file/d/17Qe2pumq6nLmzLEcvseV514o8eAPVwvk/view?usp=drive_link |  | Fahad
BR-030 | Client (APK) | OTP Mail | The OTP email came from a personal Gmail account. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on signup | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | OTP should come from the app's email to address user trust issues. | An OTP sent from a personal email can appear suspicious from the user's perspective. | Fail | Medium | https://drive.google.com/file/d/1JrtbpqQLDuv5_lQH09pimvpog6-DRnfk/view?usp=drive_link |  | Fahad
BR-031 | Client (APK) | Payment | The payment page failed to load. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The payment gateway should load smoothly and function accurately. | An error appears indicating the payment page failed to load. | Fail | High | https://drive.google.com/file/d/13f38e09rp29Hk6b4D8ZGRbUSFG2lR1oh/view?usp=drive_link |  | Fahad
BR-032 | Client (APK) | Profile | The error bar on the profile is visible between transactions. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credentials 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The app should function smoothly on the user's side without any issues or conflicts. | An error bar appears on the app, even during transactions. | Fail | High | https://drive.google.com/file/d/1qVZUY5HAL95TM-2hkpnqeXZyQytKUBhp/view?usp=drive_link |  | Fahad
BR-033 | Client (APK) | Profile | An error bar has appeared in the edit profile section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credentials 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The app should function smoothly on the user's side without any issues or conflicts. | During the page transition between editing profiles, an error bar is faintly visible to the naked eye. | Fail | Medium | https://drive.google.com/file/d/1JILOLDJL3ZWUtIgXsdtqYVhSS2SsivjF/view?usp=drive_link |  | Fahad
BR-034 | Client (APK) | Profile | The app logo is showing up in the profile section, even though it wasn't part of the client requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | App flow design should align with client requirements. | A logo has been observed on the profile page, which was not included in the client requirements. | Fail | Low | https://drive.google.com/file/d/1peyCAyGuVmf8hAUGmlgxXsx5UMbuKPcp/view?usp=drive_link |  | Fahad
BR-035 | Client (APK) | Profile | Updating the user name does not dynamically change it in the user profile. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The username should update dynamically whenever the user modifies their profile. | The username on the profile page doesn't update unless the page is refreshed or navigated away. | Fail | Medium | https://drive.google.com/file/d/1RbtUnvLHsD55thLNeEVwQ1MgI9Z7xuPz/view?usp=drive_link |  | Fahad
BR-036 | Client (APK) | Profile | The profile information submit bar is misaligned. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Proper alignment is essential for enhancing user engagement. | Misalignment has been noticed, which can lead to user dissatisfaction. | Fail | Medium | https://drive.google.com/file/d/12zZZkoeIIt7uIINMkN7lZASb7hHmx1ku/view?usp=drive_link |  | Fahad
BR-037 | Client (APK) | Profile | The edit button on the profile editing page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | No additional edit button should appear on the edit page since the user is already in the edit profile section. | The edit button on the edit profile section seems unnecessary and illogical. | Fail | Low | https://drive.google.com/file/d/1tLz7FYBRXK9Eu6YDRz9Y0FsFd89qfRJw/view?usp=drive_link |  | Fahad
BR-038 | Client (APK) | Profile | Date of birth on edit profile can be change | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The date of birth should be updated only once when the user creates their profile. After that, it should remain unchanged. | User can update your date of birth in the edit profile section. | Fail | Medium | https://drive.google.com/file/d/1bFQYk40PYBndphFPjwWfT30fA6DO3DzV/view?usp=drive_link | The best approach is to require users to input their date of birth when creating a profile initially. If the client requires the option to update the date, a one-time update feature can be implemented, which would be beneficial for the client side. | Fahad
BR-039 | Client (APK) | Profile | Unable to enter the date of birth in the edit profile section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The date of birth should be updated only once when the user creates their profile. After that, it should remain unchanged. | User can update your date of birth in the edit profile section. | Fail | High | https://drive.google.com/file/d/1Gt5Puly1E-sAvpeI4mSzi1RZP0R_L4yu/view?usp=drive_link | The best approach is to require users to input their date of birth when creating a profile initially. If the client requires the option to update the date, a one-time update feature can be implemented, which would be beneficial for the client side. | Fahad
BR-040 | Client (APK) | Profile | The friend invitation was unsuccessful. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: lowovip595@elobits.com password: 112244557788 | Users should have the ability to invite their friends via email. | The user invitation was unsuccessful. | Fail | High | https://drive.google.com/file/d/1_Tv60KP7Tkjkh7iHUX0DXhCzqf0GqRa6/view?usp=drive_link |  | Fahad
BR-041 | Client (APK) | Rewards | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on seetings 6. Goto to My reward | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/12Cm5nTsruL5XSoLlq8Yxoce1pw1qnBLP/view?usp=drive_link |  | Fahad
BR-042 | Client (APK) | SignUp | The signup page title is slightly different from the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The page title for signup should match the client requirement, which is "Sign Up". | A different title was displayed on the signup page. | Fail | Low | https://drive.google.com/file/d/137_IAutQm0DnUI1gB8itRAnvYJAmFeXA/view?usp=drive_link |  | Fahad
BR-043 | Client (APK) | SignUp | The password field has been added to the signup page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The signup page should include fields for the user's name, email, and contact number, as per the client's requirements. | An additional password field is present on the signup page, which is logically not valid. | Fail | Low | https://drive.google.com/file/d/1yzOF9rTHhxP77BLFZDCEz0CJ9j5EreVH/view?usp=drive_link |  | Fahad
BR-044 | Client (APK) | SignUp | The partition of country codes and numbers is missing in the APK. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The separation between the contact's international code and the contact number should be clear and visible. | The partition bar is missing in the contact number field on the signup page. | Fail | Low | https://drive.google.com/file/d/19OFGB8yI6Tf1inb-a0baZQXWDcWpTwN6/view?usp=drive_link |  | Fahad
BR-045 | Client (APK) | Start Page | The logo is a bit small. | The user needs to have the APK running on their mobile device. | 1. Open app |  | The app's logo should be larger to catch the client's attention. | The app logo appears too small when the application launches. | Fail | Low | https://drive.google.com/file/d/1RFb7u1ZHfXg9BeNBpxaU6znbd1L7l1pY/view?usp=drive_link |  | Fahad
BR-046 | Client (APK) | Wallet | The wallet background does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Wallet | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1vuwLGy45Ov_jwNwkOWM8j2I8mdmSQiLp/view?usp=drive_link |  | Fahad
BR-047 | Client (APK) | Wallet | Add payment methode cut down one payment gateway | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on wallet | email: lowovip595@elobits.com password: 112244557788 | All payment gateways should be clearly visible on the client side. | Apple Pay reduced its visibility in the payment gateway display. | Fail | High | https://drive.google.com/file/d/1COZrnyKh5NUytg_K2txs6xE4q7KEHg-m/view?usp=drive_link |  | Fahad
BR-048
BR-049
BR-050

## Tahsin
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | Thai Massage
Developer: | AI Venture
OS:
Environment
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
BR-001 | Client (APK) | Login | The login and signup buttons remain as "Client" when the user has already selected "Client" in a previous operation. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button | N/A | Button names should align with client requirements. | The button name "Login as client" is displayed instead of "Login." | Fail | Low | https://jam.dev/c/ee57675a-f88f-48a4-a150-f334c0b3b244
BR-002 | Client (APK) | Login | The app logo appears slightly shorter than usual. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login | N/A | The app logo should be prominently displayed to catch users' attention. | A slightly shorter logo was noticed. | Fail | Low | 1.png | Make it slightly larger to catch the user's attention.
BR-003 | Client (APK) | Login | The password visibility icon is missing on the client login page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login | N/A | The password field should display the password visibly with a hide icon to enhance user convenience. | The absence of the password visibility icon has been noted. | Fail | Medium | https://jam.dev/c/7e6fdbbf-6f54-4449-933b-872542d4e03c
BR-004 | Client (APK) | SignUp | The signup page title is slightly different from the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The page title for signup should match the client requirement, which is "Sign Up". | A different title was displayed on the signup page. | Fail | Low | https://drive.google.com/file/d/137_IAutQm0DnUI1gB8itRAnvYJAmFeXA/view?usp=drive_link
BR-005 | Client (APK) | SignUp | The password field has been added to the signup page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The signup page should include fields for the user's name, email, and contact number, as per the client's requirements. | An additional password field is present on the signup page, which is logically not valid. | Fail | Low | https://drive.google.com/file/d/1yzOF9rTHhxP77BLFZDCEz0CJ9j5EreVH/view?usp=drive_link
BR-006 | Client (APK) | SignUp | The partition of country codes and numbers is missing in the APK. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Signup | N/A | The separation between the contact's international code and the contact number should be clear and visible. | The partition bar is missing in the contact number field on the signup page. | Fail | Low | https://drive.google.com/file/d/19OFGB8yI6Tf1inb-a0baZQXWDcWpTwN6/view?usp=drive_link
BR-007 | Client (APK) | Forget Password | Forgot password OTP is set to email instead of phone number. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on Login 4. Click on Forget Password | N/A | The password reset OTP should align with the client's requirements. | The OTP for the password reset was sent via email instead of the phone number, which did not align with the client's requirements. | Fail | High | https://drive.google.com/file/d/1KLex23-Fe5dyghKSBYH7lkrzS1-6VG83/view?usp=drive_link
BR-008 | Client (APK) | Profile | The error bar on the profile is visible between transactions. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credentials 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The app should function smoothly on the user's side without any issues or conflicts. | An error bar appears on the app, even during transactions. | Fail | High | https://drive.google.com/file/d/1qVZUY5HAL95TM-2hkpnqeXZyQytKUBhp/view?usp=drive_link
BR-009 | Client (APK) | Profile | An error bar has appeared in the edit profile section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credentials 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The app should function smoothly on the user's side without any issues or conflicts. | During the page transition between editing profiles, an error bar is faintly visible to the naked eye. | Fail | Medium | https://drive.google.com/file/d/1JILOLDJL3ZWUtIgXsdtqYVhSS2SsivjF/view?usp=drive_link
BR-010 | Client (APK) | OTP Mail | The OTP email came from a personal Gmail account. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Click on signup | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | OTP should come from the app's email to address user trust issues. | An OTP sent from a personal email can appear suspicious from the user's perspective. | Fail | Medium | https://drive.google.com/file/d/1JrtbpqQLDuv5_lQH09pimvpog6-DRnfk/view?usp=drive_link
BR-011 | Client (APK) | Profile | The app logo is showing up in the profile section, even though it wasn't part of the client requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | App flow design should align with client requirements. | A logo has been observed on the profile page, which was not included in the client requirements. | Fail | Low | https://drive.google.com/file/d/1peyCAyGuVmf8hAUGmlgxXsx5UMbuKPcp/view?usp=drive_link
BR-012 | Client (APK) | Add card | Simplify the card addition bar in the mobile app. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | All payment card gateways should be clearly visible to the client. | A reduction in the payment card border has been observed. | Fail | Medium | https://drive.google.com/file/d/1u29w_Wa7h4bOdm9m9WXAH4cPvm-ZdEVi/view?usp=drive_link
BR-013 | Client (APK) | Card Information | An overflow bar has been observed in the card information. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | No overflow bar should appear from the client's perspective. | The overflow bar appears on card information where the card number format is provided. | Fail | High | https://drive.google.com/file/d/1tkCaCf4ymxthAx4ysDqpZc37wM_ilSrc/view?usp=drive_link
BR-014 | Client (APK) | Card Information | Data validation is yet to be implemented. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto profile section 5. Click on Add payment methode | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Can you use random characters and special symbols in the expiry date and CVV fields on card information? | Specific formatting should be applied to card data information, and accurate data validation formatting should be implemented. | Fail | High | https://drive.google.com/file/d/1dDJVgs6mWVi6alCalMXd7yxJHutTTxwX/view?usp=drive_link
BR-015 | Client (APK) | Home | Category "See All" button is missing. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | A "See All" button in the category should be included, allowing clients to view all types of massages and select the one that suits them best. | The absence of a "See All" button in the category section might prevent users from accessing the full range of massage categories. | Fail | High | https://drive.google.com/file/d/1WdUwhoAKw9VJZP45R6Lp1FmGJsyFdL6E/view?usp=drive_link
BR-016 | Client (APK) | Home | Therapist names are missing in the Nearby Therapist section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Therapists nearby should be easily accessible to clients, ensuring shorter travel distances and better engagement. | Unable to refresh the list of nearby therapists. | Fail | High | https://drive.google.com/file/d/1vRuK4G_c6ytmt6_kN1NbkV66uglkd5sg/view?usp=drive_link
BR-017 | Client (APK) | Profile | Updating the user name does not dynamically change it in the user profile. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The username should update dynamically whenever the user modifies their profile. | The username on the profile page doesn't update unless the page is refreshed or navigated away. | Fail | Medium | https://drive.google.com/file/d/1RbtUnvLHsD55thLNeEVwQ1MgI9Z7xuPz/view?usp=drive_link
BR-018 | Client (APK) | Profile | The profile information submit bar is misaligned. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | Proper alignment is essential for enhancing user engagement. | Misalignment has been noticed, which can lead to user dissatisfaction. | Fail | Medium | https://drive.google.com/file/d/12zZZkoeIIt7uIINMkN7lZASb7hHmx1ku/view?usp=drive_link
BR-019 | Client (APK) | Profile | The edit button on the profile editing page. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | No additional edit button should appear on the edit page since the user is already in the edit profile section. | The edit button on the edit profile section seems unnecessary and illogical. | Fail | Low | https://drive.google.com/file/d/1tLz7FYBRXK9Eu6YDRz9Y0FsFd89qfRJw/view?usp=drive_link
BR-020 | Client (APK) | Profile | Date of birth on edit profile can be change | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The date of birth should be updated only once when the user creates their profile. After that, it should remain unchanged. | User can update your date of birth in the edit profile section. | Fail | Medium | https://drive.google.com/file/d/1bFQYk40PYBndphFPjwWfT30fA6DO3DzV/view?usp=drive_link | The best approach is to require users to input their date of birth when creating a profile initially. If the client requires the option to update the date, a one-time update feature can be implemented, which would be beneficial for the client side.
BR-021 | Client (APK) | Profile | Unable to enter the date of birth in the edit profile section. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: itcrlbmzxpfmfowcfe@xfavaj.com password: 1122334455 | The date of birth should be updated only once when the user creates their profile. After that, it should remain unchanged. | User can update your date of birth in the edit profile section. | Fail | High | https://drive.google.com/file/d/1Gt5Puly1E-sAvpeI4mSzi1RZP0R_L4yu/view?usp=drive_link | The best approach is to require users to input their date of birth when creating a profile initially. If the client requires the option to update the date, a one-time update feature can be implemented, which would be beneficial for the client side.
BR-022 | Client (APK) | Profile | The friend invitation was unsuccessful. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Profile Section | email: lowovip595@elobits.com password: 112244557788 | Users should have the ability to invite their friends via email. | The user invitation was unsuccessful. | Fail | High | https://drive.google.com/file/d/1_Tv60KP7Tkjkh7iHUX0DXhCzqf0GqRa6/view?usp=drive_link
BR-023 | Client (APK) | Notification | Notification failed to load | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Notification Section | email: lowovip595@elobits.com password: 112244557788 | Notifications should load correctly on the client side for smoother interaction. | Notification missing. Error displayed: No room found. | Fail | High | https://drive.google.com/file/d/17Qe2pumq6nLmzLEcvseV514o8eAPVwvk/view?usp=drive_link
BR-024 | Client (APK) | Payment | The payment page failed to load. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The payment gateway should load smoothly and function accurately. | An error appears indicating the payment page failed to load. | Fail | High | https://drive.google.com/file/d/13f38e09rp29Hk6b4D8ZGRbUSFG2lR1oh/view?usp=drive_link
BR-025 | Client (APK) | Appointment | The location details input field is slightly different from the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1F6zNQsG49gDUpfguLk-u9nFlyuXhBEkF/view?usp=drive_link
BR-026 | Client (APK) | Appointment | The age preference does not align with the client requirement. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1loH6gbOEVYxwdpQtNm0INqLyHo92xJbM/view?usp=drive_link
BR-027 | Client (APK) | Appointment | Error bars on selected therapist schedules | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The error bar should not be visible on the client side. | An error bar on the "Done" button in the select schedule section has been identified. | Fail | Medium | https://drive.google.com/file/d/1IeVWxa2y6sKCMgIvz9n6y_GsWL13OHBt/view?usp=drive_link
BR-028 | Client (APK) | Appointment | The agree button overlaps with the section bar. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section | email: lowovip595@elobits.com password: 112244557788 | The field shadow effect should not exceed its boundary. | The cross-boundary effect has been observed. | Fail | Low | https://drive.google.com/file/d/1haRoWx_fzP2CktG0LbdGtOVcBGkZOyAs/view?usp=drive_link
BR-029 | Client (APK) | Appointment | The layout varies for questions about medical appointments. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/15VG_T_k1OUzSG0xdJjXgTgkniEmLBDiK/view?usp=drive_link
BR-030 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/13exhdxanyYbRnL4ACc2CJe65OBwTpcvO/view?usp=drive_link
BR-031 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1nkwEoAO2orWPxnW4t-8bcBiKzHGDoJ3k/view?usp=drive_link
BR-032 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/14x0H8Cj1yGkq9nIRIMEkEh_BrqGUHyb1/view?usp=drive_link
BR-033 | Client (APK) | Appointment | The button layout does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Appointment Section 5. After select required fields, goto medical questions | email: lowovip595@elobits.com password: 112244557788 | Medical questions should be properly submitted without any issues. | Unable to submit client medical questions via the app. | Fail | High | https://drive.google.com/file/d/1NY-OIs6XpToQOBkdBXzOT54gHBKu1Cqs/view?usp=drive_link
BR-034 | Client (APK) | Home | The therapist search feature is not working. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click search bar | email: lowovip595@elobits.com password: 112244557788 | Recommended and searched therapists should appear correctly in the search field. | The search functionality is broken, but therapists can be found using filters. | Fail | High | https://drive.google.com/file/d/1YMgFbIWV65v8MTTx_AxcKyawpTNmhx-6/view?usp=drive_link
BR-035 | Client (APK) | Wallet | The wallet background does not match the client's requirements. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Wallet | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1vuwLGy45Ov_jwNwkOWM8j2I8mdmSQiLp/view?usp=drive_link
BR-036 | Client (APK) | Wallet | Add payment methode cut down one payment gateway | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on wallet | email: lowovip595@elobits.com password: 112244557788 | All payment gateways should be clearly visible on the client side. | Apple Pay reduced its visibility in the payment gateway display. | Fail | High | https://drive.google.com/file/d/1COZrnyKh5NUytg_K2txs6xE4q7KEHg-m/view?usp=drive_link
BR-037 | Client (APK) | Rewards | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on seetings 6. Goto to My reward | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/12Cm5nTsruL5XSoLlq8Yxoce1pw1qnBLP/view?usp=drive_link
BR-038 | Client (APK) | Bookings | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1XULhwCogBaakOiUDnvk7CeZvdJsu3sA8/view?usp=drive_link
BR-039 | Client (APK) | Bookings | There seems to be an alignment issue. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1ZMLGhPiBHCYWW_rYz_vdbn7yGqNo7ufB/view?usp=drive_link
BR-040 | Client (APK) | Bookings | The review option is missing in the booking. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | Users should have the option to rate their therapist in the booking section after receiving therapy. | Missing review option found. | Fail | Medium | https://drive.google.com/file/d/1fdwYRTVFwtxj4a2cQUcNE-JxcPItyks3/view?usp=drive_link
BR-041 | Client (APK) | Bookings | Cancellation policy alignment and design concern. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Click on Client button 3. Login using valid credential 4. Goto Home page 5. Click on Bookings | email: lowovip595@elobits.com password: 112244557788 | The paragraph title in the cancellation policy should be bold and easily noticeable. | An alignment issue was identified, and the bold formatting for the text topic is also missing. | Fail | Low | https://drive.google.com/file/d/1rJLjMwI8nniNOY5xZ4xPNHNk_XH0otlu/view?usp=drive_link
BR-042 | Client (APK) | Start Page | The logo is a bit small. | The user needs to have the APK running on their mobile device. | 1. Open app |  | The app's logo should be larger to catch the client's attention. | The app logo appears too small when the application launches. | Fail | Low | https://drive.google.com/file/d/1RFb7u1ZHfXg9BeNBpxaU6znbd1L7l1pY/view?usp=drive_link
BR-043 | Client (APK) | Chat | The chat and call section is missing in the APK. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | The chat section should include both chat and call logs to ensure client satisfaction and enable tracking. | The call log is missing in the chat section. | Fail | High | https://drive.google.com/file/d/1GnNqqEV4v5p5Ljd7anvErcGqlXhXMURA/view?usp=drive_link
BR-044 | Client (APK) | Chat | The call option is missing in the chat. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | A call option in chat should be available for clients to directly call the therapist for further assistance. | The absence of a call option in the chat has been noted. | Fail | High | https://drive.google.com/file/d/1MU7PrtlmpF0l9Kd6tOG3EKwmh-MN_iBj/view?usp=drive_link
BR-045 | Client (APK) | Chat | Sending voice messages from chat is missing. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | A voice send option should be integrated into chat for a better user experience. | The absence of the voice button has been observed. | Fail | High | https://drive.google.com/file/d/1bdn-YJqS2VeAxlTuwYjr7VDnlWXHIEiW/view?usp=drive_link
BR-046 | Client (APK) | Chat | The option to send pictures is missing in the app. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | Adding a send picture option to the app would enhance the user experience. | The missing option for sending pictures has been noticed. | Fail | High | https://drive.google.com/file/d/1j8uc21xxRQ_ITR17s6bei4f8y8S6KfZm/view?usp=drive_link
BR-047 | Client (APK) | Chat | The pattern of sending voice messages is different. | The user needs to have the APK running on their mobile device. | 1. Open app 2. Login using valid credentials 3. Goto Chat | email : sayduntuhin.sta@gmail.com pass: 12345678 | Alignment and design should match the client's requirements. | A different design and layout have been observed. | Fail | Low | https://drive.google.com/file/d/1qvXSarQEFjZqbinUQeb_-yuLm_mOg4ue/view?usp=drive_link
BR-048
BR-049
BR-050
BR-051
BR-052
BR-053

## Summary Report
Module | Sub Module | Test Case Count | Bug Count | Bug Rate % | Bug Severity
Client (APK) | Add card | BR-001 | 47 | 100.00% | High: 17 Medium: 9 Low: 21
| Appointment | BR-002, BR-003, BR-004, BR-005, BR-006, BR-007, BR-008, BR-009, BR-010
| Bookings | BR-011, BR-012, BR-013, BR-014
| Card Information | BR-015, BR-016
| Chat | BR-017, BR-018, BR-019, BR-020, BR-021
| Forget Password | BR-022
| Home | BR-023, BR-024, BR-025
| Login | BR-026, BR-027, BR-028
| Notification | BR-029
| OTP Mail | BR-030
| Payment | BR-031
| Profile | BR-032, BR-033, BR-034, BR-035, BR-036, BR-037, BR-038, BR-039, BR-040
| Rewards | BR-041
| SignUp | BR-042, BR-043, BR-044
| Start Page | BR-045
| Wallet | BR-046, BR-047