## Fahad
Tester : | Mohammed Fahad Faisal |  |  | passenger : jvai57547@gmail.com ¦¦ Password123# Driver : teamaithunder@gmail.com ¦¦ Password123# | [5 empty] | driver : fahad.cseiiuc@gmail.com ¦¦ pass : testdriver101 user : mdfahadfaisal7@gmail.com ¦¦ pass : testuser101
Project Name: | Ulendo Connect
Developer: | AI Pulse
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127 | [11 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment
BR_001 | Onbording | Onbording | font alignment issue | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 001.png |  |  | Front-End | changed
BR_002 | Onbording | Onbording | font alignment issue | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 002.png |  |  | Front-End | changed
BR_003 | Onbording | Onbording | Icon needs to be bigger. | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 003.png |  |  | Front-End | Taken whole as image..one will effect others
BR_004 | Onbording | Onbording | Title looks different from the Figma design, and there’s a font alignment issue. | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 004.png |  |  | Front-End | chnaged
BR_005 | Role | Role | Should be under the driver, according to the Figma design. | user need to install this app on their device | 1. Open app 2. Select passenger role | N/A | Design and alignment should match the Figma file as confirmed by the client. | Message should be placed below the driver button as shown in Figma. | Fail | Low | 005.png |  |  | Front-End | changed
BR_006 | Passenger | SignIn | Should be slightly smaller, and the notification panel needs to be visible as per the Figma design. Should be in center | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | Design should match the Figma layout, with the title centered and the notification panel clearly visible. | Notification bar is missing, the header section is larger than in Figma, and the title is not centered. | Fail | Medium | 006.png |  |  | Front-End | changed
BR_007 | Passenger | SignUp | Need to set an input limit on the signup page. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Need to put input limit for users and driver | Can take infinite input in the input field. | Fail | Medium | 007.jpg
BR_008 | Passenger | SignUp | Non functional button | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Password visibility button should function as intended. | Toggle function isn’t working as expected. | Fail | High | 008.jpg |  |  | Front-End | MicrosoftTeams-video.mp4
BR_009 | Passenger | SignUp | Failed to sign up using Google. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Users should be able to sign up with their Google account through Google sign-up. | Failed to signup by google signup | Fail | High | 009.png
BR_010 | Passenger | SignUp | Encountered a server error during sign-up. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | User should not get server error while signup | Server error message displayed while signup | Fail | High | 010.jpg |  |  | Front-End | number length problem fixed
BR_011 | Passenger | OTP | A jumping action has been observed when entering the OTP. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | Should be stable when entering OTP | Jumping action has been observed | Fail | Medium | 011.mp4 |  |  | Front-End | Fixed
BR_012 | Passenger | OTP | Resend OTP failed | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | Function should work as expected | Failed to resend OTP | Fail | High | 012.png |  |  | Front-End | fixed
BR_013 | Passenger | OTP | Valid OTP is showing as invalid. Time is not expired | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | OTP should remain valid based on its designated validity period. | OTP shows as invalid, but it’s still within its validity period. | Fail | High | 013.png |  |  | Front-End | Validation time 10 min
BR_014 | Passenger | SignUp | Server error occurred while signing up as a driver. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | User should not get server error while signup | Server error message displayed while signup | Fail | High | 014.png |  |  | Front-End | Same phone number and same email won't work
BR_015 | Passenger | SignIn | Failed to store data when a user logs in with Google. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | User data should be visible when user signup by google | Failed to | Fail | High | 015.png
BR_016 | Passenger | SignIn | App name failed to display on Gmail which triggered during Google signup. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | App name should be displayed correctly in the email section. | App name is missing, and it’s showing the project as a number instead. | Fail | Medium | 016.png
BR_017 | Driver | SignUp | Backend shows the account as approved, but on the frontend, it’s still marked as under review. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Goto signup page | Driver Credentials | Frontend should show the updated status once the user has been approved in the backend. | Driver is still in review state even after they were approved from the backend. | Fail | High | 017.png |  |  | Front-End | use pull to refresh
BR_018 | Driver | Backend | Displays unauthorized on continuous API calls. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | API calls fail rate should be reduce and should only call one time if it get 200 status | API call should be control to reduce pressure on backend | Fail | High | 018.png |  |  | Front-End | fixed
BR_019 | Driver | Backend | Constant API calls on my trips and messages. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | API call should be handled with limit | Non-stop api call has been noticed on backed | Fail | High | 019.mp4 |  |  | Front-End | fixed
BR_020 | Driver | Notification | Notification panel is empty, yet it still displays the unread notification icon. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on notifications | Driver Credentials | If notification is empty than, should display simple bell icon | mark on notification has been displayed weather it has no notification unread | Fail | Medium | 020.mp4 |  |  | Front-End | fixed
BR_021 | Driver | Home | Design is different from Figma. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials | Driver Credentials | Design and aligment should as same as figma for client satisfaction | Icon missing from figma has been seen | Fail | Medium | 021.png |  |  | Front-End | fixed
BR_022 | Driver | Backend | User was deleted on the backend, but after refreshing, they remained logged into the app. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | User session management need to be handled carefully | User is deleted from the backend, but the login session still remains active on the frontend. | Fail | High | 022.png |  |  | Front-End | App state whole so time
BR_023 | Driver | Post New ride | Unable to display location suggestions. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Should display suggested locations for better user experience | Failed to suggest locations | Fail | High | 023.png |  |  | Front-End
BR_024 | Driver | Post New ride | needs more polish in the text font and design | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | App could use some extra polish on both the text and design. | Need more polish on app | Fail | Medium | 024.png
BR_025 | Driver | Post New ride | Function isn’t behaving as intended. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Function should perform as intended. | Failed to upload photos in the verification fields. | Fail | High | 025.png |  |  | Front-End
BR_026 | Driver | Post New ride | Can’t create a ride because it’s asking me to select a location from a dropdown, but the dropdown isn’t showing up. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Suggested location should be clearly visible to avoid any conflict with the actual location. | System failed to suggest the correct location, and the dropdown menu also didn’t provide any suggestions. | Fail | High | 026.png |  |  | Front-End
BR_027 | Driver | SignIn | Google signup failed and was unable to store the username and information. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Signin using google signin | Driver Credentials | User should be able to signin using google account | Failed to signin with google login | Fail | High | 027.mp4
BR_028 | Driver | SignUp | Signup using google failed | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup | Driver Credentials | User should be able to signup using google account | Failed to signup with google login | Fail | High | 028.mp4
BR_029 | Driver | Drive verification | Validation failed on the frontend, causing a server-side validation issue. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | Should put validation in user input field | No validation has been noticed in app | Fail | High | 029.png |  |  | Front-End | Solved...field name change problem from backend
BR_030 | Driver | Drive verification | Notification popup should appear when the admin approves a driver's verification. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | User should receive a notification of account verification | No notification received when admin approves user (driver) account | Fail | High | 030.png
BR_031 | Driver | Drive verification | default name set for user | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | Should be placeholder | Name was set for default | Fail | Medium | 031.png
BR_032 | Driver | My Trips | Offering multiple seats for sharing but displaying only one as available | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post ride | Driver Credentials | Seat availability should display properly on posted rides | Display only one seat as available on every ride share post, even if the user lists more than one seat. | Fail | High | 032.png
BR_033 | Driver | My Trips | Unable to find a ride through the search. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post ride | Driver Credentials | User (passenger) should be able to get the ride if the time matches with rider | Failed to get the ride, and no record was displayed. | Fail | High | 033.mp4
BR_034
BR_035
BR_036
BR_037
BR_038

## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 20
Project URL: |  |  | Medium | 8
Developer: |  |  | Low | 5
OS:
Environment |  |  | Total Test Cases: | 33
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment | Tester
BR-001 | Driver | Backend | Displays unauthorized on continuous API calls. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | API calls fail rate should be reduce and should only call one time if it get 200 status | API call should be control to reduce pressure on backend | Fail | High | 018.png |  |  | Front-End | fixed | Fahad
BR-002 | Driver | Backend | Constant API calls on my trips and messages. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | API call should be handled with limit | Non-stop api call has been noticed on backed | Fail | High | 019.mp4 |  |  | Front-End | fixed | Fahad
BR-003 | Driver | Backend | User was deleted on the backend, but after refreshing, they remained logged into the app. | user need to install this app on their device | 1. Open app 2. Login in backend framework | Driver Credentials | User session management need to be handled carefully | User is deleted from the backend, but the login session still remains active on the frontend. | Fail | High | 022.png |  |  | Front-End | App state whole so time | Fahad
BR-004 | Driver | Drive verification | Validation failed on the frontend, causing a server-side validation issue. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | Should put validation in user input field | No validation has been noticed in app | Fail | High | 029.png |  |  | Front-End | Solved...field name change problem from backend | Fahad
BR-005 | Driver | Drive verification | Notification popup should appear when the admin approves a driver's verification. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | User should receive a notification of account verification | No notification received when admin approves user (driver) account | Fail | High | 030.png |  |  |  |  | Fahad
BR-006 | Driver | Drive verification | default name set for user | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup 4. Fill necessary information and click on next | Driver Credentials | Should be placeholder | Name was set for default | Fail | Medium | 031.png |  |  |  |  | Fahad
BR-007 | Driver | Home | Design is different from Figma. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials | Driver Credentials | Design and aligment should as same as figma for client satisfaction | Icon missing from figma has been seen | Fail | Medium | 021.png |  |  | Front-End | fixed | Fahad
BR-008 | Driver | My Trips | Offering multiple seats for sharing but displaying only one as available | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post ride | Driver Credentials | Seat availability should display properly on posted rides | Display only one seat as available on every ride share post, even if the user lists more than one seat. | Fail | High | 032.png |  |  |  |  | Fahad
BR-009 | Driver | My Trips | Unable to find a ride through the search. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post ride | Driver Credentials | User (passenger) should be able to get the ride if the time matches with rider | Failed to get the ride, and no record was displayed. | Fail | High | 033.mp4 |  |  |  |  | Fahad
BR-010 | Driver | Notification | Notification panel is empty, yet it still displays the unread notification icon. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on notifications | Driver Credentials | If notification is empty than, should display simple bell icon | mark on notification has been displayed weather it has no notification unread | Fail | Medium | 020.mp4 |  |  | Front-End | fixed | Fahad
BR-011 | Driver | Post New ride | Unable to display location suggestions. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Should display suggested locations for better user experience | Failed to suggest locations | Fail | High | 023.png |  |  | Front-End |  | Fahad
BR-012 | Driver | Post New ride | needs more polish in the text font and design | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | App could use some extra polish on both the text and design. | Need more polish on app | Fail | Medium | 024.png |  |  |  |  | Fahad
BR-013 | Driver | Post New ride | Function isn’t behaving as intended. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Function should perform as intended. | Failed to upload photos in the verification fields. | Fail | High | 025.png |  |  | Front-End |  | Fahad
BR-014 | Driver | Post New ride | Can’t create a ride because it’s asking me to select a location from a dropdown, but the dropdown isn’t showing up. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Login using valid credentials 4. Click on post a new ride | Driver Credentials | Suggested location should be clearly visible to avoid any conflict with the actual location. | System failed to suggest the correct location, and the dropdown menu also didn’t provide any suggestions. | Fail | High | 026.png |  |  | Front-End |  | Fahad
BR-015 | Driver | SignIn | Google signup failed and was unable to store the username and information. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Signin using google signin | Driver Credentials | User should be able to signin using google account | Failed to signin with google login | Fail | High | 027.mp4 |  |  |  |  | Fahad
BR-016 | Driver | SignUp | Backend shows the account as approved, but on the frontend, it’s still marked as under review. | user need to install this app on their device | 1. Open app 2. Select driver role 3. Goto signup page | Driver Credentials | Frontend should show the updated status once the user has been approved in the backend. | Driver is still in review state even after they were approved from the backend. | Fail | High | 017.png |  |  | Front-End | use pull to refresh | Fahad
BR-017 | Driver | SignUp | Signup using google failed | user need to install this app on their device | 1. Open app 2. Select driver role 3. Click on signup and click on google signup | Driver Credentials | User should be able to signup using google account | Failed to signup with google login | Fail | High | 028.mp4 |  |  |  |  | Fahad
BR-018 | Onbording | Onbording | font alignment issue | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 001.png |  |  | Front-End | changed | Fahad
BR-019 | Onbording | Onbording | font alignment issue | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 002.png |  |  | Front-End | changed | Fahad
BR-020 | Onbording | Onbording | Icon needs to be bigger. | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 003.png |  |  | Front-End | Taken whole as image..one will effect others | Fahad
BR-021 | Onbording | Onbording | Title looks different from the Figma design, and there’s a font alignment issue. | user need to install this app on their device | 1. Open app | N/A | Design and alignment should match the Figma file as confirmed by the client. | Font alignment issue has been noticed | Fail | Low | 004.png |  |  | Front-End | chnaged | Fahad
BR-022 | Passenger | OTP | A jumping action has been observed when entering the OTP. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | Should be stable when entering OTP | Jumping action has been observed | Fail | Medium | 011.mp4 |  |  | Front-End | Fixed | Fahad
BR-023 | Passenger | OTP | Resend OTP failed | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | Function should work as expected | Failed to resend OTP | Fail | High | 012.png |  |  | Front-End | fixed | Fahad
BR-024 | Passenger | OTP | Valid OTP is showing as invalid. Time is not expired | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page 4. Fillup necessary information and click next to get OTP | User Credentials | OTP should remain valid based on its designated validity period. | OTP shows as invalid, but it’s still within its validity period. | Fail | High | 013.png |  |  | Front-End | Validation time 10 min | Fahad
BR-025 | Passenger | SignIn | Should be slightly smaller, and the notification panel needs to be visible as per the Figma design. Should be in center | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | Design should match the Figma layout, with the title centered and the notification panel clearly visible. | Notification bar is missing, the header section is larger than in Figma, and the title is not centered. | Fail | Medium | 006.png |  |  | Front-End | changed | Fahad
BR-026 | Passenger | SignIn | Failed to store data when a user logs in with Google. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | User data should be visible when user signup by google | Failed to | Fail | High | 015.png |  |  |  |  | Fahad
BR-027 | Passenger | SignIn | App name failed to display on Gmail which triggered during Google signup. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signin page | N/A | App name should be displayed correctly in the email section. | App name is missing, and it’s showing the project as a number instead. | Fail | Medium | 016.png |  |  |  |  | Fahad
BR-028 | Passenger | SignUp | Need to set an input limit on the signup page. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Need to put input limit for users and driver | Can take infinite input in the input field. | Fail | Medium | 007.jpg |  |  |  |  | Fahad
BR-029 | Passenger | SignUp | Non functional button | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Password visibility button should function as intended. | Toggle function isn’t working as expected. | Fail | High | 008.jpg |  |  | Front-End | MicrosoftTeams-video.mp4 | Fahad
BR-030 | Passenger | SignUp | Failed to sign up using Google. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | Users should be able to sign up with their Google account through Google sign-up. | Failed to signup by google signup | Fail | High | 009.png |  |  |  |  | Fahad
BR-031 | Passenger | SignUp | Encountered a server error during sign-up. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | User should not get server error while signup | Server error message displayed while signup | Fail | High | 010.jpg |  |  | Front-End | number length problem fixed | Fahad
BR-032 | Passenger | SignUp | Server error occurred while signing up as a driver. | user need to install this app on their device | 1. Open app 2. Select passenger role 3. Goto signup page | N/A | User should not get server error while signup | Server error message displayed while signup | Fail | High | 014.png |  |  | Front-End | Same phone number and same email won't work | Fahad
BR-033 | Role | Role | Should be under the driver, according to the Figma design. | user need to install this app on their device | 1. Open app 2. Select passenger role | N/A | Design and alignment should match the Figma file as confirmed by the client. | Message should be placed below the driver button as shown in Figma. | Fail | Low | 005.png |  |  | Front-End | changed | Fahad

## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Stack | Comment

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Driver | Backend | BR-001, BR-002, BR-003 | 3 | 9.09% | High: 3 Medium: 0 Low: 0
Driver | Drive verification | BR-004, BR-005, BR-006 | 3 | 9.09% | High: 2 Medium: 1 Low: 0
Driver | Home | BR-007 | 1 | 3.03% | High: 0 Medium: 1 Low: 0
Driver | My Trips | BR-008, BR-009 | 2 | 6.06% | High: 2 Medium: 0 Low: 0
Driver | Notification | BR-010 | 1 | 3.03% | High: 0 Medium: 1 Low: 0
Driver | Post New ride | BR-011, BR-012, BR-013, BR-014 | 4 | 12.12% | High: 3 Medium: 1 Low: 0
Driver | SignIn | BR-015 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
Driver | SignUp | BR-016, BR-017 | 2 | 6.06% | High: 2 Medium: 0 Low: 0
Onbording | Onbording | BR-018, BR-019, BR-020, BR-021 | 4 | 12.12% | High: 0 Medium: 0 Low: 4
Passenger | OTP | BR-022, BR-023, BR-024 | 3 | 9.09% | High: 2 Medium: 1 Low: 0
Passenger | SignIn | BR-025, BR-026, BR-027 | 3 | 9.09% | High: 1 Medium: 2 Low: 0
Passenger | SignUp | BR-028, BR-029, BR-030, BR-031, BR-032 | 5 | 15.15% | High: 4 Medium: 1 Low: 0
Role | Role | BR-033 | 1 | 3.03% | High: 0 Medium: 0 Low: 1