## Main Report
Tester : | Mohammed Fahad Faisal Tahsin Ahmmed |  | Severity | Issues
Project Name: | VALR |  | High | 11
Project URL: | VALR |  | Medium | 18
Developer: |  |  | Low | 14
OS:
Environment |  |  | Total Test Cases: | 43
|  |  | Test Case Solved : | 33
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
TC-001 | Mobile Device Landing Page (Light Mode) | About us | Verify if the full title is properly displayed on mobile screen without cutting off words | User is on a mobile device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Tap on the "About Us" section from the menu | N/A | The title "Dedicated to Simplifying the VALR Process for Veterans" should be fully visible without being cut off | The title appears cut off and some words are not fully visible | Fail | Medium | https://jam.dev/c/7a23cefc-0c89-4e8f-9d90-cdcadb484b4f | Adjust mobile CSS styling (e.g., font size, line height, padding) or use responsive design to ensure full title fits on screen | Solved
TC-002 | Mobile Device Authentication (Dark Mode) | About us | Verify visibility of white text over light background in abox | User is on a mobile device (dark mode) and navigates to the About Us section | 1. Open https://valrpro.com/ on a mobile browser 2. Go to the About Us section 3. Locate the box with the text "THIS IS TRUST" | N/A | Text "THIS IS TRUST" should be clearly visible with sufficient contrast against the background | Text is barely visible due to white color on a light background | Fail | Medium | https://jam.dev/c/f7e14b0e-6393-4743-bb26-202988c77a4c | Change text color to a darker shade or adjust background to ensure sufficient contrast and readability | Solved
TC-003 | PC (Brouser Dark Mode) Landing Page | About us | Verify visibility of white text over light background in abox | User is on a PC device (dark mode) and navigates to the About Us section | 1. Open https://valrpro.com/ on a mobile browser 2. Go to the About Us section 3. Locate the box with the text "THIS IS TRUST" | N/A | Text "THIS IS TRUST" should be clearly visible with sufficient contrast against the background | Text is barely visible due to white color on a light background | Fail | Medium | https://jam.dev/c/0144f3e4-3fc6-4d46-95a9-c5d6e2d3b272 | Change text color to a darker shade or adjust background to ensure sufficient contrast and readability | Solved
TC-004 | VA Form | ai_narrative | Alignment issue on AI narrative page. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | Proper page alignment should always be maintained. | An issue with alignment breakdown has been identified. | Fail | Low | https://jam.dev/c/8a75fd38-40a6-4076-9a75-206f6dcc8402 |  | Solved
TC-005 | VA Form | ai_narrative | AI narration modifies data. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | The Vietnam War, which took place from 1955 to 1975, should have its data accurately updated and presented in a narrative form. | Neck and shoulder conditions occurred during the Vietnam War timeline, which ended in 1975, while leg and arm conditions happened after 1975 and were not related to the Vietnam War period. | Fail | High | https://jam.dev/c/cdc6f837-e92a-4ab0-80e7-06bb578c52c5 |  | Solved
TC-006 | VA Form | ai_narrative | AI narration modifies data. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | Accurate health issues should be displayed or narrated in an AI narrative. | PTSD was not selected as a health issue, but it was mentioned in the AI narrative. | Fail | Medium | https://jam.dev/c/562a0661-00db-4406-9b80-91a1e3b22baa |  | Solved
TC-007 | Mobile Device Landing Page (Light Mode) | Calculator | Verify that both disability type and percentage selections are highlighted consistently | User is on the Physical Disability Calculator section on a mobile device | 1. Open https://valrpro.com/ on a mobile browser 2. Navigate to the Physical Disability Calculator 3. Select a physical disability type 4. Select a percentage value | N/A | Both selected disability type and selected percentage should be visually highlighted to indicate selection | Only the disability type is highlighted; percentage selection has no visual indication | Fail | Low | https://jam.dev/c/a7618719-d759-477c-8f92-3bc19a277051 | Apply consistent styling to percentage selection (e.g., background color or border) to visually confirm selection | Solved
TC-008 | Home | Contact us | Input box design and fields changed based on client requirements. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | Contact us form should as same as client requirement | A phone box was added that was not part of the client requirements, and the layout differs from what was specified in the requirements. | Fail | Medium | https://jam.dev/c/274e93b2-8c31-4a53-84c8-0721d951a951 |  | Solved
TC-009 | Home | Contact us | Image corners are not the same as in Figma. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | Based on the Figma design, the image corners should be angled. | Two curved and two angled corners are shown, which is asymmetrical and does not align with the client's requirements. | Fail | Low | https://jam.dev/c/bf359085-b448-4604-822f-bcc5a7ae50d4 |  | Solved
TC-010 | Home | Contact us | Handle incorrect input in input fields. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Goto Contact Us | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The form should be designed to accept specific data types, such as numbers in the phone input field and characters in the name fields. | Phone number fields accept character input, and name fields allow numeric values, leading to an input validation mismatch. | Fail | High | https://jam.dev/c/5aaba718-3a6c-4865-9743-0b788bbf1907 |  | Unsolved
TC-011 | Home | FAQ | FQA layout update using Figma design. | User should be able to be in browser | 1. Open VALR 2. Scroll down to FQA Section |  | Content layout should be similar to the client's requirements. | A different layout design has been observed in the FAQ section. | Fail | Low | https://jam.dev/c/1a16a164-3926-488d-b4c5-a8eb3a4a269d |  | Solved
TC-012 | Home | Footer | Update the footer message as per the design and include a social media link that is not connected to VALR's social media accounts. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | The footer section details and alignment should match the client's requirements. | The layout design differs from the client's requirements, and while social media is beneficial, the link connected to VALR's official social media is inaccurate. | Fail | High | https://jam.dev/c/c0b840df-8d99-4bf8-ba90-99631091e4ee |  | Solved
TC-013 | VA Form | gulf_war_location | Missing war location in chart | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 9th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Accurate locations of U.S. involvement in wars need to be displayed for veterans to choose their fighting regions. | The United States has conflicts with various countries, but Gulf War-related risk locations are the only ones highlighted, potentially causing veterans to miss out on VA benefits. | Fail | High | https://jam.dev/c/0a02aaf8-8e4e-407a-9ead-21cf454d357e |  | Solved
TC-014 | PC (Brouser Dark Mode) Landing Page | Home | Verify that homepage paragraph text is readable over dark background | User is on a PC device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the section with the text: "Tired of delays, paperwork, and confusion? VALR makes filing your VA claim fast and stress-free..." 3. Observe the text color against the background | N/A | Text should be easily readable with enough contrast even in dark-themed sections | Text appears dark over a dark background, making it difficult to read | Fail | Medium | https://jam.dev/c/215db53b-812b-4c4e-93a7-03b48bf2ff67 | Update text color to a lighter shade or adjust background opacity to ensure sufficient contrast and readability | Solved
TC-015 | Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Top of the home page 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Low | https://jam.dev/c/1f06cefb-bd1f-42b9-9bc5-736604e888e0 |  | Solved
TC-016 | Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the get in touch today section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/2968f160-9630-4c6f-bba9-5b0e76c9663d |  | Solved
TC-017 | Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the Frequently Asked Questions section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/debe4d04-3b2c-47d2-accd-2810beda0e9b |  | Solved | explain
TC-018 | Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the THROUGH EDUCATION section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/6c2f0795-5a52-4b4c-9b68-f30e6b436e7b |  | Solved | explain
TC-019 | PC (Brouser Dark + light Mode) Landing Page | Home | Verify that there is no unnecessary blank space above the Services section | User is on a PC device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll down to the Services section 3. Observe the spacing above the section | N/A | Spacing above Services section should be consistent and free of large empty gaps | There is an unusual blank space above the Services section | Fail | Low | https://jam.dev/c/72bb2f2e-40cc-41cd-a0e6-9dac05197357 | Review and adjust CSS layout/margins to eliminate unnecessary whitespace and maintain visual consistency | Solved
TC-020 | Home | Home page | Profile icon use in VAFORM section | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | An icon should make sense. | VAFORM is documented in the Profile icon | Fail | Medium | https://jam.dev/c/19b28142-f8ca-4af4-90c1-7dd7e98e9fc6 |  | Solved | when user have subcription plan whole section will be changed to another
TC-021 | Home | Home Page | Different video content is displayed when users log in to the system. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | Video content should remain consistent on the page for user information. | A different video is displayed, which can lead to misinformation issues. | Fail | High | https://jam.dev/c/5c75a6c3-df26-4cb1-abce-bba7051c7aea |  | Solved
TC-022 | Home | Home Page | The video lacks shading, and the corners are not symmetrical. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | Proper design should align with the requirements. | Different designs and web apps are displayed. | Fail | Medium | https://jam.dev/c/74a4e051-7867-4d6a-ada6-a0130384d075 |  | Solved
TC-023 | Home | Home Page | An alignment issue has been observed. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The alignment should match the client's requirements. | An alignment issue has been detected, which can sometimes result in user dissatisfaction. | Fail | Medium | https://jam.dev/c/584df2cc-d534-4559-9c20-0c74bb4326e1 |  | Solved | navbar holds the key section of the website. that why i skip this from the navbar
TC-024 | Home | Home Page | The claim layout differs from the client's requirements. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The claim page layout should match the client's requirements. | Different user interface, different image displayed. Also video added which was not in design | Fail | Medium | https://jam.dev/c/d49e5e4e-7252-4a2b-b250-63483159d613 |  | Solved |  | services
TC-025 | Home | Home Page | A line is visible when used in night mode. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The line beneath the icon should not be visible in the web app. | The line beneath the icon is noticeable in night mode. | Fail | Low | https://jam.dev/c/80518c60-dcee-4c92-8179-27abe13342e5 |  | Solved | discussed with the client and he suggested me to do so
TC-026 | Home | Landing Page | A significant gap has been noticed. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | The gap between contents should be determined user requirements. | Noticed a significant gap. | Fail | Low | https://jam.dev/c/1636caed-a178-46a7-aef8-4afdd970d596 |  | Solved
TC-027 | Home | Landing Page | The landing page is missing a contact option. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | The contact option should be prominently displayed at the top of user engagement. | Missing content buttons shows which sometimes lead to user dissatisfaction. | Fail | Medium | https://jam.dev/c/88966c97-c8c8-4db9-9faa-609432f036a7 |  | Solved | explain
TC-028 | Home | Landing Page | An alignment issue has been identified that does not match the client's requirements. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | Alignment should match user requirements to ensure satisfaction. | An alignment issue was found that could result in user dissatisfaction. | Fail | Low | https://jam.dev/c/732f8fb6-55db-42c9-bca1-1d23789db6f5 |  | Solved
TC-029 | Home | Landing Page | The payment section differs from the Figma design. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The layout should match the client's requirements. | A different layout has been observed. | Fail | Low | https://jam.dev/c/e35cc884-0b6e-4d9f-9651-b9b6862d98c9 |  | Solved | discussed with the client and he suggested me to do so
TC-030 | Home | Landing Page | The video corner is not the same as other corners. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | All corners of video file should be same | Three curved corners and one angled corner have been noticed, which makes it asymmetrical. | Fail | Medium | https://jam.dev/c/123734b1-0747-4619-8fb8-c1806768912a |  | Solved | need to check after published
TC-031 | Home | Landing Page | The video border shade is not implemented in the web app. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The video shade should match the client's requirements. | A mismatch has been identified between the client's requirements and the developed app. | Fail | Medium | https://jam.dev/c/535e6bd5-25ab-4c07-a109-aff9aa5fb5a4 |  | Solved | from my site i can't see any overlaps.
TC-032 | Home | Landing Page | An alignment issue has been observed on the landing page. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | Allignment should be match with client requirement | A mismatch in alignment with client requirements can result in dissatisfaction. | Fail | Low | https://jam.dev/c/eb37c560-e234-415b-95a6-f58bdb594cf8 |  | Solved
TC-033 | Home | Landing Page | The "Read More" option for the content under the banner is missing. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The stories banner should include a "Read More" option to allow users to view the full history. | Missing a "Read More" option in a story banner can make users believe the story is fake or created solely for publicity. | Fail | High | https://jam.dev/c/421d8638-3a23-4a6c-b704-5362ff64b5dc |  | Solved | need to check after published
TC-034 | Mobile Device Authentication (Dark Mode) | Login | Verify password field text color in dark mode is clearly visible | User's phone is in dark mode and user is on the login screen of the site | 1. Open https://valrpro.com/ on a mobile browser 2. Ensure the phone is set to dark mode 3. Go to the login screen 4. Tap on the password field and type any text | N/A | The typed password should be clearly visible (e.g., light-colored text on dark background) | Password text appears black on a dark background, making it hard to see | Fail | High | https://jam.dev/c/cca7d6de-4a27-4053-8108-3b660e26d30b | Update input field CSS to ensure sufficient color contrast for dark mode (e.g., use light-colored text) |  | in figma no otp validation when creating new account
TC-035 | SignIn | Login | The password hide icon overlaps when the user attempts to log in or signup | User should be able to be in browser | 1. Open VALR 2.Goto Signin or signup |  | The visible and hide option icon for the password should remain consistent. | The icon overlaps when a user enters input in the password section. | Fail | Medium | https://jam.dev/c/fec0b683-8105-450a-a86a-978e8e88eb6f |  | Unsolved
TC-036 | SignIn | Login | When an unregistered user tries to log in, the prompt doesn't display "Invalid email and password." | User should be able to be in browser | 1. Open VALR 2.Goto Signin or signup |  | When an unregistered user attempts to log in to the system, the prompt should display a message indicating that the email is not registered in the system. | The prompt displays "Something went wrong," but it doesn't clarify whether the issue is on the client side or due to a system error. | Fail | High | https://jam.dev/c/cebc8fcb-dd8e-43f7-a85e-b01e72f91582 |  | Unsolved
TC-037 | PC (Brouser Dark Mode) Authentication | Login | Verify password field text color in dark mode is clearly visible | User's phone is in dark mode and user is on the login screen of the site | 1. Open https://valrpro.com/ on a mobile browser 2. Ensure the phone is set to dark mode 3. Go to the login screen 4. Tap on the password field and type any text | N/A | The typed password should be clearly visible (e.g., light-colored text on dark background) | Password text appears black on a dark background, making it hard to see | Fail | High | https://jam.dev/c/d764618c-0455-4d4c-b1d0-2edb1a0f4428 | Update input field CSS to ensure sufficient color contrast for dark mode (e.g., use light-colored text) | Solved | need to check after published
TC-038 | VA Form | mental_health_details | An alignment issue has been observed. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 12th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Proper page alignment should always be maintained. | An issue with alignment breakdown has been identified. | Fail | Low | https://jam.dev/c/1b388bd9-a49f-4563-8345-8671539786f6
TC-039 | VA Form | mental_health_info | Work period time is not clearly specified as per day or total service hours. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 12th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Veterans' work period should be clearly specified as either daily hours or total service hours. | The lack of proper information has been noticed, which can sometimes lead to confusion for some veterans. | Fail | High | https://jam.dev/c/4fedc7b2-3f23-42bf-b95c-8315a5122b20
TC-040 | SignUp | SignUp | Verifying user with an OTP has not been included for authentication. | User should be able to be in browser | 1. Open VALR 2.Goto Signup | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | After signing up, users should receive an OTP to ensure proper authentication for valid accounts. | The app is missing OTP authentication. | Fail | High
TC-041 | VAFORM | VA Form PDFs | Verify that the "VA Form PDFs" text is fully visible without being cut off | User is on a mobile device and navigates to the VA Form section | 1. Open https://valrpro.com/ on a mobile browser 2. Click to the VA Form section 3. Locate the text "VA Form PDFs" 4. Observe whether the full text is visible without being cut off | N/A | Text "VA Form PDFs" should be completely visible and properly aligned | Text appears partially cut off or clipped on mobile screen | Fail | Medium | https://jam.dev/c/04f6f0b1-1689-405a-9282-da51b68e4f80 | Adjust responsive layout or padding to ensure full visibility of header text on all screen sizes
TC-042 | Home | Video | Video file corner are not same | User should be able to be in browser | 1. Open VALR |  | Corner of video file should be same | Three corners are curved, but one is angled, leading to an unsatisfactory appearance. | Fail | Low | https://jam.dev/c/444699fc-345e-411f-a7c2-a455224996d7
TC-043 | Home | Video | The border of the video file doesn't align with the Figma design. | User should be able to be in browser | 1. Open VALR 2. Goto about VARL video |  | The video shade design should match the client's requirements exactly. | A deviation from the client's requirements has been observed. | Fail | Low | https://jam.dev/c/842807bd-0b79-48a9-b2ce-d1be28607e80
TC-044
TC-045
TC-046
TC-047
TC-048
TC-049
TC-050
TC-051
TC-052
TC-053
TC-054
TC-055
TC-056
TC-057
TC-058
TC-059
TC-060
TC-061
TC-062
TC-063
TC-064
TC-065
TC-066
TC-067
TC-068
TC-069
TC-070
TC-071
TC-072
TC-073
TC-074
TC-075
TC-076
TC-077
TC-078
TC-079

## Tahsin (Mobile Phone User)
Tester : | Tahsin Ahmmed |  | Severity | Issues
Project Name: | ValrPro |  | High | 10
Project URL: | https://valrpro.com/ |  | Medium | 12
Developer: |  |  | Low | 12
OS:
Environment |  |  | Total Test Cases: | 34
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
| Mobile Device Landing Page (Light Mode) | About us | Verify if the full title is properly displayed on mobile screen without cutting off words | User is on a mobile device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Tap on the "About Us" section from the menu | N/A | The title "Dedicated to Simplifying the VALR Process for Veterans" should be fully visible without being cut off | The title appears cut off and some words are not fully visible | Fail | Medium | https://jam.dev/c/7a23cefc-0c89-4e8f-9d90-cdcadb484b4f | Adjust mobile CSS styling (e.g., font size, line height, padding) or use responsive design to ensure full title fits on screen
| Mobile Device Authentication (Dark Mode) | About us | Verify visibility of white text over light background in abox | User is on a mobile device (dark mode) and navigates to the About Us section | 1. Open https://valrpro.com/ on a mobile browser 2. Go to the About Us section 3. Locate the box with the text "THIS IS TRUST" | N/A | Text "THIS IS TRUST" should be clearly visible with sufficient contrast against the background | Text is barely visible due to white color on a light background | Fail | Medium | https://jam.dev/c/f7e14b0e-6393-4743-bb26-202988c77a4c | Change text color to a darker shade or adjust background to ensure sufficient contrast and readability
| Mobile Device Landing Page (Light Mode) | Calculator | Verify that both disability type and percentage selections are highlighted consistently | User is on the Physical Disability Calculator section on a mobile device | 1. Open https://valrpro.com/ on a mobile browser 2. Navigate to the Physical Disability Calculator 3. Select a physical disability type 4. Select a percentage value | N/A | Both selected disability type and selected percentage should be visually highlighted to indicate selection | Only the disability type is highlighted; percentage selection has no visual indication | Fail | Low | https://jam.dev/c/a7618719-d759-477c-8f92-3bc19a277051 | Apply consistent styling to percentage selection (e.g., background color or border) to visually confirm selection
| Mobile Device Authentication (Dark Mode) | Login | Verify password field text color in dark mode is clearly visible | User's phone is in dark mode and user is on the login screen of the site | 1. Open https://valrpro.com/ on a mobile browser 2. Ensure the phone is set to dark mode 3. Go to the login screen 4. Tap on the password field and type any text | N/A | The typed password should be clearly visible (e.g., light-colored text on dark background) | Password text appears black on a dark background, making it hard to see | Fail | High | https://jam.dev/c/cca7d6de-4a27-4053-8108-3b660e26d30b | Update input field CSS to ensure sufficient color contrast for dark mode (e.g., use light-colored text)

## Tahsin (PC User)
Tester : | Tahsin Ahmmed |  | Severity | Issues
Project Name: | ValrPro |  | High | 10
Project URL: | https://valrpro.com/ |  | Medium | 16
Developer: |  |  | Low | 13
OS:
Environment |  |  | Total Test Cases: | 39
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
| PC (Brouser Dark Mode) Landing Page | Home | Verify that homepage paragraph text is readable over dark background | User is on a PC device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the section with the text: "Tired of delays, paperwork, and confusion? VALR makes filing your VA claim fast and stress-free..." 3. Observe the text color against the background | N/A | Text should be easily readable with enough contrast even in dark-themed sections | Text appears dark over a dark background, making it difficult to read | Fail | Medium | https://jam.dev/c/215db53b-812b-4c4e-93a7-03b48bf2ff67 | Update text color to a lighter shade or adjust background opacity to ensure sufficient contrast and readability
| Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Top of the home page 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Low | https://jam.dev/c/1f06cefb-bd1f-42b9-9bc5-736604e888e0
| Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the get in touch today section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/2968f160-9630-4c6f-bba9-5b0e76c9663d
| Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the Frequently Asked Questions section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/debe4d04-3b2c-47d2-accd-2810beda0e9b
| Landing Page PC | Home | Verify that homepage UI is correct | User is on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll to the THROUGH EDUCATION section 3. Observe the layout | N/A | UI should match with the client requirements | Not matched with the client requirement | Fail | Medium | https://jam.dev/c/6c2f0795-5a52-4b4c-9b68-f30e6b436e7b
| PC (Brouser Dark + light Mode) Landing Page | Home | Verify that there is no unnecessary blank space above the Services section | User is on a PC device and on the homepage | 1. Open https://valrpro.com/ on a mobile browser 2. Scroll down to the Services section 3. Observe the spacing above the section | N/A | Spacing above Services section should be consistent and free of large empty gaps | There is an unusual blank space above the Services section | Fail | Low | https://jam.dev/c/72bb2f2e-40cc-41cd-a0e6-9dac05197357 | Review and adjust CSS layout/margins to eliminate unnecessary whitespace and maintain visual consistency
| PC (Brouser Dark Mode) Landing Page | About us | Verify visibility of white text over light background in abox | User is on a PC device (dark mode) and navigates to the About Us section | 1. Open https://valrpro.com/ on a mobile browser 2. Go to the About Us section 3. Locate the box with the text "THIS IS TRUST" | N/A | Text "THIS IS TRUST" should be clearly visible with sufficient contrast against the background | Text is barely visible due to white color on a light background | Fail | Medium | https://jam.dev/c/0144f3e4-3fc6-4d46-95a9-c5d6e2d3b272 | Change text color to a darker shade or adjust background to ensure sufficient contrast and readability
| PC (Brouser Dark Mode) Authentication | Login | Verify password field text color in dark mode is clearly visible | User's phone is in dark mode and user is on the login screen of the site | 1. Open https://valrpro.com/ on a mobile browser 2. Ensure the phone is set to dark mode 3. Go to the login screen 4. Tap on the password field and type any text | N/A | The typed password should be clearly visible (e.g., light-colored text on dark background) | Password text appears black on a dark background, making it hard to see | Fail | High | https://jam.dev/c/d764618c-0455-4d4c-b1d0-2edb1a0f4428 | Update input field CSS to ensure sufficient color contrast for dark mode (e.g., use light-colored text)
| VAFORM | VA Form PDFs | Verify that the "VA Form PDFs" text is fully visible without being cut off | User is on a mobile device and navigates to the VA Form section | 1. Open https://valrpro.com/ on a mobile browser 2. Click to the VA Form section 3. Locate the text "VA Form PDFs" 4. Observe whether the full text is visible without being cut off | N/A | Text "VA Form PDFs" should be completely visible and properly aligned | Text appears partially cut off or clipped on mobile screen | Fail | Medium | https://jam.dev/c/04f6f0b1-1689-405a-9282-da51b68e4f80 | Adjust responsive layout or padding to ensure full visibility of header text on all screen sizes

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name: | ValrPro
Developer:
OS: | Windows (x86) 11
Environment | Edge 138.0.7204.158
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
TC-001 | Home | Video | Video file corner are not same | User should be able to be in browser | 1. Open VALR |  | Corner of video file should be same | Three corners are curved, but one is angled, leading to an unsatisfactory appearance. | Fail | Low | https://jam.dev/c/444699fc-345e-411f-a7c2-a455224996d7
TC-002 | Home | Video | The border of the video file doesn't align with the Figma design. | User should be able to be in browser | 1. Open VALR 2. Goto about VARL video |  | The video shade design should match the client's requirements exactly. | A deviation from the client's requirements has been observed. | Fail | Low | https://jam.dev/c/842807bd-0b79-48a9-b2ce-d1be28607e80
TC-003 | Home | Landing Page | A significant gap has been noticed. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | The gap between contents should be determined user requirements. | Noticed a significant gap. | Fail | Low | https://jam.dev/c/1636caed-a178-46a7-aef8-4afdd970d596
TC-004 | Home | Landing Page | The landing page is missing a contact option. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | The contact option should be prominently displayed at the top of user engagement. | Missing content buttons shows which sometimes lead to user dissatisfaction. | Fail | Medium | https://jam.dev/c/88966c97-c8c8-4db9-9faa-609432f036a7
TC-005 | Home | Landing Page | An alignment issue has been identified that does not match the client's requirements. | User should be able to be in browser | 1. Open VALR 2. Scroll down to first video |  | Alignment should match user requirements to ensure satisfaction. | An alignment issue was found that could result in user dissatisfaction. | Fail | Low | https://jam.dev/c/732f8fb6-55db-42c9-bca1-1d23789db6f5
TC-006 | Home | Landing Page | The payment section differs from the Figma design. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The layout should match the client's requirements. | A different layout has been observed. | Fail | Low | https://jam.dev/c/e35cc884-0b6e-4d9f-9651-b9b6862d98c9
TC-007 | Home | Landing Page | The video corner is not the same as other corners. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | All corners of video file should be same | Three curved corners and one angled corner have been noticed, which makes it asymmetrical. | Fail | Medium | https://jam.dev/c/123734b1-0747-4619-8fb8-c1806768912a
TC-008 | Home | Landing Page | The video border shade is not implemented in the web app. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The video shade should match the client's requirements. | A mismatch has been identified between the client's requirements and the developed app. | Fail | Medium | https://jam.dev/c/535e6bd5-25ab-4c07-a109-aff9aa5fb5a4
TC-009 | Home | Landing Page | An alignment issue has been observed on the landing page. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | Allignment should be match with client requirement | A mismatch in alignment with client requirements can result in dissatisfaction. | Fail | Low | https://jam.dev/c/eb37c560-e234-415b-95a6-f58bdb594cf8
TC-010 | Home | Landing Page | The "Read More" option for the content under the banner is missing. | User should be able to be in browser | 1. Open VALR 2. Scroll down to 2nd video |  | The stories banner should include a "Read More" option to allow users to view the full history. | Missing a "Read More" option in a story banner can make users believe the story is fake or created solely for publicity. | Fail | High | https://jam.dev/c/421d8638-3a23-4a6c-b704-5362ff64b5dc
TC-011 | Home | FAQ | FQA layout update using Figma design. | User should be able to be in browser | 1. Open VALR 2. Scroll down to FQA Section |  | Content layout should be similar to the client's requirements. | A different layout design has been observed in the FAQ section. | Fail | Low | https://jam.dev/c/1a16a164-3926-488d-b4c5-a8eb3a4a269d
TC-012 | Home | Contact us | Input box design and fields changed based on client requirements. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | Contact us form should as same as client requirement | A phone box was added that was not part of the client requirements, and the layout differs from what was specified in the requirements. | Fail | Medium | https://jam.dev/c/274e93b2-8c31-4a53-84c8-0721d951a951
TC-013 | Home | Contact us | Image corners are not the same as in Figma. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | Based on the Figma design, the image corners should be angled. | Two curved and two angled corners are shown, which is asymmetrical and does not align with the client's requirements. | Fail | Low | https://jam.dev/c/bf359085-b448-4604-822f-bcc5a7ae50d4
TC-014 | Home | Footer | Update the footer message as per the design and include a social media link that is not connected to VALR's social media accounts. | User should be able to be in browser | 1. Open VALR 2.Scroll down to contact us section |  | The footer section details and alignment should match the client's requirements. | The layout design differs from the client's requirements, and while social media is beneficial, the link connected to VALR's official social media is inaccurate. | Fail | High | https://jam.dev/c/c0b840df-8d99-4bf8-ba90-99631091e4ee
TC-015 | SignIn | Login | The password hide icon overlaps when the user attempts to log in or signup | User should be able to be in browser | 1. Open VALR 2.Goto Signin or signup |  | The visible and hide option icon for the password should remain consistent. | The icon overlaps when a user enters input in the password section. | Fail | Medium | https://jam.dev/c/fec0b683-8105-450a-a86a-978e8e88eb6f
TC-016 | SignIn | Login | When an unregistered user tries to log in, the prompt doesn't display "Invalid email and password." | User should be able to be in browser | 1. Open VALR 2.Goto Signin or signup |  | When an unregistered user attempts to log in to the system, the prompt should display a message indicating that the email is not registered in the system. | The prompt displays "Something went wrong," but it doesn't clarify whether the issue is on the client side or due to a system error. | Fail | High | https://jam.dev/c/cebc8fcb-dd8e-43f7-a85e-b01e72f91582
TC-017 | SignUp | SignUp | Verifying user with an OTP has not been included for authentication. | User should be able to be in browser | 1. Open VALR 2.Goto Signup | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | After signing up, users should receive an OTP to ensure proper authentication for valid accounts. | The app is missing OTP authentication. | Fail | High
TC-018 | Home | Home page | Profile icon use in VAFORM section | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | An icon should make sense. | VAFORM is documented in the Profile icon | Fail | Medium | https://jam.dev/c/19b28142-f8ca-4af4-90c1-7dd7e98e9fc6
TC-019 | Home | Home Page | Different video content is displayed when users log in to the system. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | Video content should remain consistent on the page for user information. | A different video is displayed, which can lead to misinformation issues. | Fail | High | https://jam.dev/c/5c75a6c3-df26-4cb1-abce-bba7051c7aea
TC-020 | Home | Home Page | The video lacks shading, and the corners are not symmetrical. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | Proper design should align with the requirements. | Different designs and web apps are displayed. | Fail | Medium | https://jam.dev/c/74a4e051-7867-4d6a-ada6-a0130384d075
TC-021 | Home | Home Page | An alignment issue has been observed. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The alignment should match the client's requirements. | An alignment issue has been detected, which can sometimes result in user dissatisfaction. | Fail | Medium | https://jam.dev/c/584df2cc-d534-4559-9c20-0c74bb4326e1
TC-022 | Home | Home Page | The claim layout differs from the client's requirements. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The claim page layout should match the client's requirements. | Different user interface, different image displayed. Also video added which was not in design | Fail | Medium | https://jam.dev/c/d49e5e4e-7252-4a2b-b250-63483159d613
TC-023 | Home | Home Page | A line is visible when used in night mode. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The line beneath the icon should not be visible in the web app. | The line beneath the icon is noticeable in night mode. | Fail | Low | https://jam.dev/c/80518c60-dcee-4c92-8179-27abe13342e5
TC-024 | Home | Contact us | Handle incorrect input in input fields. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Goto Contact Us | Email : tbfdmiyygildwxwqyp@nespf.com Pass : 12345678 | The form should be designed to accept specific data types, such as numbers in the phone input field and characters in the name fields. | Phone number fields accept character input, and name fields allow numeric values, leading to an input validation mismatch. | Fail | High | https://jam.dev/c/5aaba718-3a6c-4865-9743-0b788bbf1907
TC-025 | VA Form | gulf_war_location | Missing war location in chart | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 9th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Accurate locations of U.S. involvement in wars need to be displayed for veterans to choose their fighting regions. | The United States has conflicts with various countries, but Gulf War-related risk locations are the only ones highlighted, potentially causing veterans to miss out on VA benefits. | Fail | High | https://jam.dev/c/0a02aaf8-8e4e-407a-9ead-21cf454d357e |  | Unsolve
TC-026 | VA Form | mental_health_info | Work period time is not clearly specified as per day or total service hours. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 12th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Veterans' work period should be clearly specified as either daily hours or total service hours. | The lack of proper information has been noticed, which can sometimes lead to confusion for some veterans. | Fail | High | https://jam.dev/c/4fedc7b2-3f23-42bf-b95c-8315a5122b20 |  | Unsolve
TC-027 | VA Form | mental_health_details | An alignment issue has been observed. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and filled up to 12th steps | Email : bijoymamud.09@gmail.com Pass : 12345678 | Proper page alignment should always be maintained. | An issue with alignment breakdown has been identified. | Fail | Low | https://jam.dev/c/1b388bd9-a49f-4563-8345-8671539786f6 |  | Unsolve
TC-028 | VA Form | ai_narrative | Alignment issue on AI narrative page. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | Proper page alignment should always be maintained. | An issue with alignment breakdown has been identified. | Fail | Low | https://jam.dev/c/8a75fd38-40a6-4076-9a75-206f6dcc8402 |  | Unsolve
TC-029 | VA Form | ai_narrative | AI narration modifies data. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | The Vietnam War, which took place from 1955 to 1975, should have its data accurately updated and presented in a narrative form. | Neck and shoulder conditions occurred during the Vietnam War timeline, which ended in 1975, while leg and arm conditions happened after 1975 and were not related to the Vietnam War period. | Fail | High | https://jam.dev/c/cdc6f837-e92a-4ab0-80e7-06bb578c52c5 |  | Unsolve
TC-030 | VA Form | ai_narrative | AI narration modifies data. | User should be able to be in browser | 1. Open VALR. 2. Sign in using valid credentials. 3. Click on VA form and goto AI Narrative | Email : bijoymamud.09@gmail.com Pass : 12345678 | Accurate health issues should be displayed or narrated in an AI narrative. | PTSD was not selected as a health issue, but it was mentioned in the AI narrative. | Fail | Medium | https://jam.dev/c/562a0661-00db-4406-9b80-91a1e3b22baa |  | Unsolve