## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Fahad
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 22 |  | https://www.google.com/url?q=https://drive.google.com/drive/folders/1FRBcKQaBHzPnXLwXsJ50fxP5fJZiGNoG&sa=D&source=editors&ust=1777270765470635&usg=AOvVaw1xT38euCF2HCZ8KvY8sS0Y
Developer: |  |  | Medium | 11
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946 |  | Low | 1
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127 | [12 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
|  |  | Total Test Cases: | 34
|  |  | Test Case Solved : | 14
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback | Feedback | Stack | Comment
BR_001 | Splash Screen | Splash Screen | Splash flow missing | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | All flash screens should be positioned accurately according to the Figma design. | Missing flash screen on selecting gender | Fail | Medium | 001.MP4 | 001.1.png |  | Unsolved | App | I solve the issue
BR_002 | Splash Screen | Splash Screen | Splash image missing | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | The image on the splash screen should be positioned precisely. | Image missing in splash screen | Fail | Medium | 002.png |  |  | Solved | App | I fix the issue
BR_003 | Splash Screen | Splash Screen | The buttons are shifting along with the splash screen. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | Only the image should be scrollable, not the options. | Buttons are also moving with the picture. | Fail | Medium | 003.MP4 |  |  | Unsolved | App | Button also change able because last button is Let get started
BR_004 | Login | Login | The login page doesn’t include links to the terms of service or privacy policy. | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | Privacy policies should be properly linked on the screen. | The Privacy policy aren’t connected. | Fail | High | 004.png |  |  | Unsolved | App | Not in design It is on account section
BR_005 | Achievement | Achievement | Beginner profile is set to level one, but it requires 200 steps to unlock that level. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings | User credentials | The beginner profile level should start at zero, and after completing 200 steps, it will unlock level one. | The level starts at one, and the achievement also locks at level one. | Fail | Medium | 005.png |  |  | Solved | Back-End
BR_006 | Profile | Profile | A profile input validation issue has been detected. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select Profile | User credentials | Proper maintenance of input field validation is essential. | Input validation missing in app | Fail | High | 006.png |  |  | Unsolved | App | I fix the issue
BR_007 | Password | Password | The password update error toast message is showing with the success toast message color. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select Update password | User credentials | Error toast message should be displayed properly | The error toast message color is set to the same as the success toast message. | Fail | Low | 007.png |  |  | Unsolved | App | I fix the issue
BR_008 | Weight tracker | BMI | BMI calculation error | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | BMI calculation in app should be accurate | Error in BMI calculation | Fail | High | 008.png |  |  | Solved | Back-End
BR_009 | Login | Login | Faced error in login | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | User should not face any issue in login | Faced bad request on login time | Fail | High | 009.png |  |  | Solved | Back-End
BR_010 | Challenge | Challenge | Progress count issue | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges 4. Click on current challenge | User credentials | Progress calculations need to be precise. | Mismatch in progress calculation | Fail | High | 010.MP4 |  |  | Unsolved | App | I fix the issue
BR_011 | Achievement | Achievement | Unlocked the 7th achievement instead of the 6th one. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings | User credentials | Achievements should be unlocked in ascending order. | 7th achievement unlocked instead of the 6th | Fail | High | 011.png |  |  | Solved | Back-End | I fix the issue
BR_012 | Challenge | Challenge | The "Continue Steps" button isn’t working, making it nonfunctional. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges | User credentials | All buttons should work accurately. | button not working | Fail | High | 012.mov |  |  | Solved | App | I solved the issue
BR_013 | Challenge | Challenge | Miss calculations in challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges | User credentials | All challenge data should function smoothly. | A data mismatch has been detected. | Fail | High | 013.MP4 |  |  | Solved | Back-End | I fix the issue
BR_014 | OTP | OTP | Double OTP page is displayed | User need to download the app on their IOS device | 1. Open app 2. goto Login page 3. Click on forget password 4. Enter mail and goto OTP page | User credentials | OTP page should displayed single time | OTP page shows twice | Fail | Medium | 014.PNG |  |  | Unsolved | App | It is not issue if you double click on otp then it show double otp. It check it on my end
BR_015 | Home | Home | Save the data from the previous account and show it in the new account. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Home | User credentials | Data from a deleted account should not be stored. | Showed deleted account data on the new account | Fail | High | 015.PNG
BR_016 | Challenge | Challenge | Failed to join public challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges | User credentials | Usere should be able to join public created challenges | Failed to join in public created challenges | Fail | High | 016.png |  |  | Solved | App | I fix the issue
BR_017 | Help & Support | Contact Support | The social media and website links aren’t integrated. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Help & Support 4. Click on contact support | User credentials | Social media accounts and the website should be properly connected to ensure authenticity. | Missing social media and website links | Fail | Medium | 017.png |  |  |  | App | Client not provide.Only showing the static data
BR_018 | Privacy Policy | Privacy Policy | Missing privacy policy content in app | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Privacy Policy | User credentials | The privacy policy should be clearly displayed in the app to ensure authenticity. | Privacy policy content is missing. | Fail | Medium | 018.png |  |  | Unsolved | App | It is comming from backend. If dashboard upload privacy policy then it show
BR_019 | Terms of service | Terms of service | Missing terms of service content in app | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Terms of service | User credentials | The terms of service should be clearly displayed in the app to ensure authenticity. | Terms of service content is missing. | Fail | Medium | 019.png |  |  | Solved | App | It is comming from backend. If dashboard upload Terms of Service then it show
BR_020 | Challenge | Challenge | The step count for the public challenge isn’t working as it should. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | Steps should be counted accurately in public challenges. | Facing calculation error and steps are not counting in public challenges | Fail | High | 020.png |  |  | Solved | Back-End
BR_021 | Challenge | Challenge | Missmatch calculation in created challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | Calclations should be accurate | Miss calculation has been noticed | Fail | High | 021.png |  |  | Solved | Back-End
BR_022 | Delete Account | Delete Account | Failed to redirect to the signup page after deleting the account. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Settings 4. Click on delete account | User credentials | After deleting an account, the user should be redirected to the signup page. | Unable to redirect the user to the signup page. | Fail | High | 022.MP4 |  |  | Solved | App | I fix the issue
BR_023 | Forget Password | Forget Password | User is able to reset password for deleted account | User need to download the app on their IOS device | 1. Open app 2. Goto login page 3. Click on forget password | User credentials | Only registered email should receive OTP | Normal mail also can receive OTP | Fail | High | 023.mov |  |  | Solved | App | I fix the issue
BR_024 | Challenge | Challenge | The challenge lasts for two timelines, one measured in weeks and the other in days. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | It should only take one time | It takes two time inputs, one in weeks and the other with a start and end date, which makes it a bit confusing. | Fail | Medium | 024.png |  |  | Solved | App | It is previously designed.For this reason. Here user have to calculate start date and end date of challenge and based on week input
BR_025 | Daily Task | Daily Task | Multiple task completion screen appeared after the user finished their daily task. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Complete daily task | User credentials | After completing daily task, completion screen should appear only one time | Multiple completion screen has been seen in app | Fail | Medium | 025.MP4 |  |  | Unsolved | App | I fix the issue
BR_026 | Progress | Progress | Work progress calculation and daily target calculation are different. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Complete daily task | User credentials | The daily target goal calculation needs to be accurate and clearly displayed. | Progress calculation error | Fail | High | 026.png
BR_027 | Weight tracker | BMI | The weight can be changed, but you need to close and relaunch the app. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | The weight should update dynamically without needing to close or relaunch the app. | Unable to update weight in real time | Fail | High | 027.mov
BR_028 | Report | Report | Missing Statistic on report page | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click report | User credentials | The design and alignment should be as perfect as in Figma. | Statistic missing in the frontend | Fail | High | 028.png
BR_029 | Home | Home | Failed to display progress in proper week | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Home | User credentials | The filter on the calendar should display correctly in either week or month view. | Unable to display the progress for the day in the week. | Fail | High | 029.png
BR_030 | Report | Report | Failed to display accurate calender in report page | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click report | User credentials | The calendar should be displayed accurately in the app. | Unable to display the correct calendar in the app. | Fail | High | 030.png
BR_031 | Splash Screen | Splash Screen | Failed to proceed with default steps | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | If steps is not manually selected by user, then the default steps (1000 steps) should be used to procced | The user cannot proceed to the next page without manually selecting the steps. | Fail | High | 031.png
BR_032 | Login | Login | Failed to sigin | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | User should be able to signin without facing any issue | Failed to signin properly | Fail | High | 032.png
BR_033 | Preferences | Preferences | The frontend is missing the daily reminder feature. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto settings 4. Click on Preferences | User credentials | Design and functions should be same as figma | Missing daily remainder in frontend | Fail | High | 033.png
BR_034 | Weight tracker | BMI | Alignment issue in weight graph | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | Alignment and design should be accurate as figma | Alignment issue has been noticed | Fail | Medium | 034.png

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Achievement | Achievement | BR-001, BR-002 | 2 | 5.88% | High: 1 Medium: 1 Low: 0
Challenge | Challenge | BR-003, BR-004, BR-005, BR-006, BR-007, BR-008, BR-009 | 7 | 20.59% | High: 6 Medium: 1 Low: 0
Daily Task | Daily Task | BR-010 | 1 | 2.94% | High: 0 Medium: 1 Low: 0
Delete Account | Delete Account | BR-011 | 1 | 2.94% | High: 1 Medium: 0 Low: 0
Forget Password | Forget Password | BR-012 | 1 | 2.94% | High: 1 Medium: 0 Low: 0
Help & Support | Contact Support | BR-013 | 1 | 2.94% | High: 0 Medium: 1 Low: 0
Home | Home | BR-014, BR-015 | 2 | 5.88% | High: 2 Medium: 0 Low: 0
Login | Login | BR-016, BR-017, BR-018 | 3 | 8.82% | High: 3 Medium: 0 Low: 0
OTP | OTP | BR-019 | 1 | 2.94% | High: 0 Medium: 1 Low: 0
Password | Password | BR-020 | 1 | 2.94% | High: 0 Medium: 0 Low: 1
Preferences | Preferences | BR-021 | 1 | 2.94% | High: 1 Medium: 0 Low: 0
Privacy Policy | Privacy Policy | BR-022 | 1 | 2.94% | High: 0 Medium: 1 Low: 0
Profile | Profile | BR-023 | 1 | 2.94% | High: 1 Medium: 0 Low: 0
Progress | Progress | BR-024 | 1 | 2.94% | High: 1 Medium: 0 Low: 0
Report | Report | BR-025, BR-026 | 2 | 5.88% | High: 2 Medium: 0 Low: 0
Splash Screen | Splash Screen | BR-027, BR-028, BR-029, BR-030 | 4 | 11.76% | High: 1 Medium: 3 Low: 0
Terms of service | Terms of service | BR-031 | 1 | 2.94% | High: 0 Medium: 1 Low: 0
Weight tracker | BMI | BR-032, BR-033, BR-034 | 3 | 8.82% | High: 2 Medium: 1 Low: 0

## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 22
Project URL: |  |  | Medium | 11
Developer: |  |  | Low | 1
OS:
Environment |  |  | Total Test Cases: | 34 | [9 empty] | Place solve if the issue resolves ¦ \/ | Mention which Stack solved the issue ¦ \/
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Stack | Comment
BR-001 | Achievement | Achievement | Beginner profile is set to level one, but it requires 200 steps to unlock that level. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings | User credentials | The beginner profile level should start at zero, and after completing 200 steps, it will unlock level one. | The level starts at one, and the achievement also locks at level one. | Fail | Medium | 005.png |  | Fahad
BR-002 | Achievement | Achievement | Unlocked the 7th achievement instead of the 6th one. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings | User credentials | Achievements should be unlocked in ascending order. | 7th achievement unlocked instead of the 6th | Fail | High | 011.png |  | Fahad
BR-003 | Challenge | Challenge | Progress count issue | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges 4. Click on current challenge | User credentials | Progress calculations need to be precise. | Mismatch in progress calculation | Fail | High | 010.MP4 |  | Fahad
BR-004 | Challenge | Challenge | The "Continue Steps" button isn’t working, making it nonfunctional. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges | User credentials | All buttons should work accurately. | button not working | Fail | High | 012.mov |  | Fahad
BR-005 | Challenge | Challenge | Miss calculations in challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto challenges | User credentials | All challenge data should function smoothly. | A data mismatch has been detected. | Fail | High | 013.MP4 |  | Fahad
BR-006 | Challenge | Challenge | Failed to join public challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges | User credentials | Usere should be able to join public created challenges | Failed to join in public created challenges | Fail | High | 016.png |  | Fahad
BR-007 | Challenge | Challenge | The step count for the public challenge isn’t working as it should. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | Steps should be counted accurately in public challenges. | Facing calculation error and steps are not counting in public challenges | Fail | High | 020.png |  | Fahad
BR-008 | Challenge | Challenge | Missmatch calculation in created challenges | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | Calclations should be accurate | Miss calculation has been noticed | Fail | High | 021.png |  | Fahad
BR-009 | Challenge | Challenge | The challenge lasts for two timelines, one measured in weeks and the other in days. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Public challenges 4. Join in public challenges | User credentials | It should only take one time | It takes two time inputs, one in weeks and the other with a start and end date, which makes it a bit confusing. | Fail | Medium | 024.png |  | Fahad
BR-010 | Daily Task | Daily Task | Multiple task completion screen appeared after the user finished their daily task. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Complete daily task | User credentials | After completing daily task, completion screen should appear only one time | Multiple completion screen has been seen in app | Fail | Medium | 025.MP4 |  | Fahad
BR-011 | Delete Account | Delete Account | Failed to redirect to the signup page after deleting the account. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Settings 4. Click on delete account | User credentials | After deleting an account, the user should be redirected to the signup page. | Unable to redirect the user to the signup page. | Fail | High | 022.MP4 |  | Fahad
BR-012 | Forget Password | Forget Password | User is able to reset password for deleted account | User need to download the app on their IOS device | 1. Open app 2. Goto login page 3. Click on forget password | User credentials | Only registered email should receive OTP | Normal mail also can receive OTP | Fail | High | 023.mov |  | Fahad
BR-013 | Help & Support | Contact Support | The social media and website links aren’t integrated. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Help & Support 4. Click on contact support | User credentials | Social media accounts and the website should be properly connected to ensure authenticity. | Missing social media and website links | Fail | Medium | 017.png |  | Fahad
BR-014 | Home | Home | Save the data from the previous account and show it in the new account. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Home | User credentials | Data from a deleted account should not be stored. | Showed deleted account data on the new account | Fail | High | 015.PNG |  | Fahad
BR-015 | Home | Home | Failed to display progress in proper week | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Home | User credentials | The filter on the calendar should display correctly in either week or month view. | Unable to display the progress for the day in the week. | Fail | High | 029.png |  | Fahad
BR-016 | Login | Login | The login page doesn’t include links to the terms of service or privacy policy. | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | Privacy policies should be properly linked on the screen. | The Privacy policy aren’t connected. | Fail | High | 004.png |  | Fahad
BR-017 | Login | Login | Faced error in login | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | User should not face any issue in login | Faced bad request on login time | Fail | High | 009.png |  | Fahad
BR-018 | Login | Login | Failed to sigin | User need to download the app on their IOS device | 1. Open app 2. Goto login page | User credentials | User should be able to signin without facing any issue | Failed to signin properly | Fail | High | 032.png |  | Fahad
BR-019 | OTP | OTP | Double OTP page is displayed | User need to download the app on their IOS device | 1. Open app 2. goto Login page 3. Click on forget password 4. Enter mail and goto OTP page | User credentials | OTP page should displayed single time | OTP page shows twice | Fail | Medium | 014.PNG |  | Fahad
BR-020 | Password | Password | The password update error toast message is showing with the success toast message color. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select Update password | User credentials | Error toast message should be displayed properly | The error toast message color is set to the same as the success toast message. | Fail | Low | 007.png |  | Fahad
BR-021 | Preferences | Preferences | The frontend is missing the daily reminder feature. | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto settings 4. Click on Preferences | User credentials | Design and functions should be same as figma | Missing daily remainder in frontend | Fail | High | 033.png |  | Fahad
BR-022 | Privacy Policy | Privacy Policy | Missing privacy policy content in app | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Privacy Policy | User credentials | The privacy policy should be clearly displayed in the app to ensure authenticity. | Privacy policy content is missing. | Fail | Medium | 018.png |  | Fahad
BR-023 | Profile | Profile | A profile input validation issue has been detected. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select Profile | User credentials | Proper maintenance of input field validation is essential. | Input validation missing in app | Fail | High | 006.png |  | Fahad
BR-024 | Progress | Progress | Work progress calculation and daily target calculation are different. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Complete daily task | User credentials | The daily target goal calculation needs to be accurate and clearly displayed. | Progress calculation error | Fail | High | 026.png |  | Fahad
BR-025 | Report | Report | Missing Statistic on report page | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click report | User credentials | The design and alignment should be as perfect as in Figma. | Statistic missing in the frontend | Fail | High | 028.png |  | Fahad
BR-026 | Report | Report | Failed to display accurate calender in report page | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click report | User credentials | The calendar should be displayed accurately in the app. | Unable to display the correct calendar in the app. | Fail | High | 030.png |  | Fahad
BR-027 | Splash Screen | Splash Screen | Splash flow missing | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | All flash screens should be positioned accurately according to the Figma design. | Missing flash screen on selecting gender | Fail | Medium | 001.MP4 | 001.1.png | Fahad
BR-028 | Splash Screen | Splash Screen | Splash image missing | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | The image on the splash screen should be positioned precisely. | Image missing in splash screen | Fail | Medium | 002.png |  | Fahad
BR-029 | Splash Screen | Splash Screen | The buttons are shifting along with the splash screen. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | Only the image should be scrollable, not the options. | Buttons are also moving with the picture. | Fail | Medium | 003.MP4 |  | Fahad
BR-030 | Splash Screen | Splash Screen | Failed to proceed with default steps | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials | User credentials | If steps is not manually selected by user, then the default steps (1000 steps) should be used to procced | The user cannot proceed to the next page without manually selecting the steps. | Fail | High | 031.png |  | Fahad
BR-031 | Terms of service | Terms of service | Missing terms of service content in app | User need to download the app on their IOS device | 1. Open app 2. Login using valid credentials 3. Goto Terms of service | User credentials | The terms of service should be clearly displayed in the app to ensure authenticity. | Terms of service content is missing. | Fail | Medium | 019.png |  | Fahad
BR-032 | Weight tracker | BMI | BMI calculation error | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | BMI calculation in app should be accurate | Error in BMI calculation | Fail | High | 008.png |  | Fahad
BR-033 | Weight tracker | BMI | The weight can be changed, but you need to close and relaunch the app. | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | The weight should update dynamically without needing to close or relaunch the app. | Unable to update weight in real time | Fail | High | 027.mov |  | Fahad
BR-034 | Weight tracker | BMI | Alignment issue in weight graph | User need to download the app on their IOS device | 1. Open app 2. Signup using valid credentials 3. Click on settings 4. Select weight tracker | User credentials | Alignment and design should be accurate as figma | Alignment issue has been noticed | Fail | Medium | 034.png |  | Fahad