## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: |  |  | High | 22
Project URL: |  |  | Medium | 17
Developer: |  |  | Low | 1
OS:
Environment |  |  | Total Test Cases: | 40 | [9 empty] | Place solve if the issue resolves I V | Mention which Stack solved the issue I V
|  |  | Test Case Solved : | 0
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Stack | Comment
BR-001 | Account | Account | Different from UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 031.png |  | Fahad
BR-002 | Account | Account | Flow broken. Unable to add wallet card in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The flow should be accurate according to the Figma design. | The app is missing a feature that allows adding a wallet card to the driver profile. | Fail | High | 032.png |  | Fahad
BR-003 | Account | Account | Missing email input field in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The input field should be positioned precisely as shown in the Figma design. | Missing input field in app | Fail | High | 033.png |  | Fahad
BR-004 | Account | Account | Missing update password field in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 034.png |  | Fahad
BR-005 | Account | Account | Button is not functional | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 035.png |  | Fahad
BR-006 | Account | Account | Missing privacy and data | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Page data should be positioned perfectly. | Missing content on privacy and data | Fail | Low | 036.png |  | Fahad
BR-007 | Account | Account | About us page missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The feature and page should be positioned in the ideal spot. | Page missing also option missing in account | Fail | High | 037.png |  | Fahad
BR-008 | Account | Account | Vehicle update missing from account | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The feature and page should be positioned in the ideal spot. | Page missing also option missing in account | Fail | High | 038.png |  | Fahad
BR-009 | Forget Password | Forget Password | Wrong error in wrong place | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password | User Credential | Error should be displayed in right place | wrong error in wrong place | Fail | Medium | 005.png |  | Fahad
BR-010 | History | History | Different from UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role 4. Click on History | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 040.png |  | Fahad
BR-011 | Home | Quick Booking | Feature missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 019.png |  | Fahad
BR-012 | Home | Quick Booking | Missing option to set location on the map | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 020.png |  | Fahad
BR-013 | Home | Quick Booking | The map on the top bar is missing in the app. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 021.png |  | Fahad
BR-014 | Home | Quick Booking | The multi-stop feature hasn’t been added to the app yet. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 022.png |  | Fahad
BR-015 | Home | Quick Booking | The app doesn’t have a feature to set pickup and drop-off times. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 023.png |  | Fahad
BR-016 | Home | Quick Booking | User profile icon set as default | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | Medium | 024.png |  | Fahad
BR-017 | Home | Quick Booking | View current location feature missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The map should include a show current location feature because it’s a basic necessity. | Current location view is missing in app | Fail | High | 025.png |  | Fahad
BR-018 | Home | Quick Booking | Car list displayed at the pickup spot | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 026.png |  | Fahad
BR-019 | Landing screen | Home | The UI was implemented in a different way. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | High | 015.png |  | Fahad
BR-020 | Landing screen | Home | Figma set as 3D but implemented as 2D | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 016.png |  | Fahad
BR-021 | Landing screen | Home | The app has a top-notch blend in its design, but within the app itself, it doesn’t quite blend in. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 017.png |  | Fahad
BR-022 | Landing screen | Home | The UI and implementation are different. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 018.png |  | Fahad
BR-023 | Landing screen | Home | The profile name doesn’t update automatically. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The profile should automatically update after switching roles. | The profile does not update dynamically. | Fail | Medium | 028.mp4 |  | Fahad
BR-024 | Landing screen | Home | Clicking on the profile doesn’t navigate the user to the profile screen. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 029.png |  | Fahad
BR-025 | Landing screen | Home | Not functional | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 030.png |  | Fahad
BR-026 | Landing screen | Home | Users UI set as Drivers UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | The UI should be designed to adapt to different user roles. | Users UI is integrated in drivers UI | Fail | Medium | 039.png |  | Fahad
BR-027 | OTP | OTP | Failed to receive OTP in the entered email. | User need to install the app in their android device | 1. Open app 2. Click on sign-up | User Credential | The user should get an OTP for email verification. | Did not receive the OTP in the registered email address. | Fail | High | 003.png |  | Fahad
BR-028 | OTP | OTP | The app name in the OTP is incorrect. | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | The app name in the OTP should be correct. | The mail title shows the wrong app name. | Fail | Medium | 006.png |  | Fahad
BR-029 | OTP | OTP | support mail is not aligned with app name | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | The support email should match the app name. | Noticed difference of app name and support mail | Fail | Medium | 007.png |  | Fahad
BR-030 | OTP | OTP | The OTP code in the email body is missing. | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | Email body should contain User name , OTP code, time and date | Blank email body has been noticed | Fail | High | 008.png |  | Fahad
BR-031 | Sign-up | Sign-up | Failed to create account | User need to install the app in their android device | 1. Open app 2. Click on sign-up | N/A | Users should be able to sign up without encountering any problems. | Failed to signup | Fail | High | 001.png |  | Fahad
BR-032 | Sign-up | Sign-up | Failed to create account | User need to install the app in their android device | 1. Open app 2. Click on sign-up | N/A | Users should be able to sign up without encountering any problems. | Failed to signup | Fail | High | 002.png |  | Fahad
BR-033 | Sign-up | Sign-up | The "Remember Me" button isn’t working. | User need to install the app in their android device | 1. Open app 2. Click on sign-up | User Credential | Remember button should be functional | Not working button. Unable to click | Fail | Medium | 004.png |  | Fahad
BR-034 | Sign-up | Sign-up | Sign-in page error display in sign-up page | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | An error message for a specific page should only appear on that page. | An error from another page is appearing on a different page. | Fail | Medium | 013.png |  | Fahad
BR-035 | Vehicle Information | Vehicle Information | Design Alignment issue | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Alignment and design should be as same as figma | Different design has been noticed | Fail | Medium | 009.png |  | Fahad
BR-036 | Vehicle Information | Vehicle Information | Different UI has been noticed | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Alignment and design should be as same as figma | Different design has been noticed | Fail | Medium | 010.png |  | Fahad
BR-037 | Vehicle Information | Vehicle Information | The error toast still shows up even after all input fields are filled. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Error should only be visible when it's required | The error keeps appearing even when it’s not needed. | Fail | Medium | 011.png |  | Fahad
BR-038 | Vehicle Information | Vehicle Information | Submission failed after loading time | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Vehicle information submission should be completed smoothly and without any problems. | The submission failed after loading for 2 minutes. | Fail | High | 012.png |  | Fahad
BR-039 | Vehicle Information | Vehicle Information | Flow broken | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | The driver should be able to register without experiencing any timeout issues. | Failed to register driver | Fail | High | 014.png |  | Fahad
BR-040 | Vehicle Information | Vehicle Information | Age verification missing. Driver must be 18 or more years old | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Driver age verification feature missing in app | No filter add in driver age field. It's required to be 18 or more years old to be driver | Fail | High | 027.png |  | Fahad

## Fahad
Tester : | Mohammed Fahad Faisal |  |  |  | Email | user@gmail.com | driver@gmail.com
Project Name: | Ryde Islands |  |  |  | Pass | user*user* | driver*driver*
Developer: | AI Thunder
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | realme C63 model : RMX3939 Android Version : 15 Dimention : (6.59 x 3.02 x 0.30)in
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
BR_001 | Sign-up | Sign-up | Failed to create account | User need to install the app in their android device | 1. Open app 2. Click on sign-up | N/A | Users should be able to sign up without encountering any problems. | Failed to signup | Fail | High | 001.png
BR_002 | Sign-up | Sign-up | Failed to create account | User need to install the app in their android device | 1. Open app 2. Click on sign-up | N/A | Users should be able to sign up without encountering any problems. | Failed to signup | Fail | High | 002.png
BR_003 | OTP | OTP | Failed to receive OTP in the entered email. | User need to install the app in their android device | 1. Open app 2. Click on sign-up | User Credential | The user should get an OTP for email verification. | Did not receive the OTP in the registered email address. | Fail | High | 003.png
BR_004 | Sign-up | Sign-up | The "Remember Me" button isn’t working. | User need to install the app in their android device | 1. Open app 2. Click on sign-up | User Credential | Remember button should be functional | Not working button. Unable to click | Fail | Medium | 004.png
BR_005 | Forget Password | Forget Password | Wrong error in wrong place | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password | User Credential | Error should be displayed in right place | wrong error in wrong place | Fail | Medium | 005.png
BR_006 | OTP | OTP | The app name in the OTP is incorrect. | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | The app name in the OTP should be correct. | The mail title shows the wrong app name. | Fail | Medium | 006.png
BR_007 | OTP | OTP | support mail is not aligned with app name | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | The support email should match the app name. | Noticed difference of app name and support mail | Fail | Medium | 007.png
BR_008 | OTP | OTP | The OTP code in the email body is missing. | User need to install the app in their android device | 1. Open app 2. Click on sign-in 3. Click on Forget Password 4. Open mail | User Credential | Email body should contain User name , OTP code, time and date | Blank email body has been noticed | Fail | High | 008.png
BR_009 | Vehicle Information | Vehicle Information | Design Alignment issue | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Alignment and design should be as same as figma | Different design has been noticed | Fail | Medium | 009.png
BR_010 | Vehicle Information | Vehicle Information | Different UI has been noticed | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Alignment and design should be as same as figma | Different design has been noticed | Fail | Medium | 010.png
BR_011 | Vehicle Information | Vehicle Information | The error toast still shows up even after all input fields are filled. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Error should only be visible when it's required | The error keeps appearing even when it’s not needed. | Fail | Medium | 011.png
BR_012 | Vehicle Information | Vehicle Information | Submission failed after loading time | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Vehicle information submission should be completed smoothly and without any problems. | The submission failed after loading for 2 minutes. | Fail | High | 012.png
BR_013 | Sign-up | Sign-up | Sign-in page error display in sign-up page | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | An error message for a specific page should only appear on that page. | An error from another page is appearing on a different page. | Fail | Medium | 013.png
BR_014 | Vehicle Information | Vehicle Information | Flow broken | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | The driver should be able to register without experiencing any timeout issues. | Failed to register driver | Fail | High | 014.png
BR_015 | Landing screen | Home | The UI was implemented in a different way. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | High | 015.png
BR_016 | Landing screen | Home | Figma set as 3D but implemented as 2D | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 016.png
BR_017 | Landing screen | Home | The app has a top-notch blend in its design, but within the app itself, it doesn’t quite blend in. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 017.png
BR_018 | Landing screen | Home | The UI and implementation are different. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 018.png
BR_019 | Home | Quick Booking | Feature missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 019.png
BR_020 | Home | Quick Booking | Missing option to set location on the map | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 020.png
BR_021 | Home | Quick Booking | The map on the top bar is missing in the app. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 021.png
BR_022 | Home | Quick Booking | The multi-stop feature hasn’t been added to the app yet. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 022.png
BR_023 | Home | Quick Booking | The app doesn’t have a feature to set pickup and drop-off times. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 023.png
BR_024 | Home | Quick Booking | User profile icon set as default | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | Medium | 024.png
BR_025 | Home | Quick Booking | View current location feature missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The map should include a show current location feature because it’s a basic necessity. | Current location view is missing in app | Fail | High | 025.png
BR_026 | Home | Quick Booking | Car list displayed at the pickup spot | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 026.png
BR_027 | Vehicle Information | Vehicle Information | Age verification missing. Driver must be 18 or more years old | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | Driver age verification feature missing in app | No filter add in driver age field. It's required to be 18 or more years old to be driver | Fail | High | 027.png
BR_028 | Landing screen | Home | The profile name doesn’t update automatically. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | The profile should automatically update after switching roles. | The profile does not update dynamically. | Fail | Medium | 028.mp4
BR_029 | Landing screen | Home | Clicking on the profile doesn’t navigate the user to the profile screen. | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 029.png
BR_030 | Landing screen | Home | Not functional | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role | User Credential | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 030.png
BR_031 | Account | Account | Different from UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 031.png
BR_032 | Account | Account | Flow broken. Unable to add wallet card in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The flow should be accurate according to the Figma design. | The app is missing a feature that allows adding a wallet card to the driver profile. | Fail | High | 032.png
BR_033 | Account | Account | Missing email input field in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The input field should be positioned precisely as shown in the Figma design. | Missing input field in app | Fail | High | 033.png
BR_034 | Account | Account | Missing update password field in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 034.png
BR_035 | Account | Account | Button is not functional | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Features and functionalities should be implemented correctly. | Missing feature noticed | Fail | High | 035.png
BR_036 | Account | Account | Missing privacy and data | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | Page data should be positioned perfectly. | Missing content on privacy and data | Fail | Low | 036.png
BR_037 | Account | Account | About us page missing in app | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The feature and page should be positioned in the ideal spot. | Page missing also option missing in account | Fail | High | 037.png
BR_038 | Account | Account | Vehicle update missing from account | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role 4. Click on Account | Driver Credentials | The feature and page should be positioned in the ideal spot. | Page missing also option missing in account | Fail | High | 038.png
BR_039 | Landing screen | Home | Users UI set as Drivers UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select driver role | Driver Credentials | The UI should be designed to adapt to different user roles. | Users UI is integrated in drivers UI | Fail | Medium | 039.png
BR_040 | History | History | Different from UI | User need to install the app in their android device | 1. Open app 2. Sign-in using valid credential 3. Select user role 4. Click on History | User Credential | The design and alignments should be as accurate as in Figma. | Noticed a different design implementation in the app. | Fail | Medium | 040.png
BR_041
BR_042
BR_043
BR_044
BR_045
BR_046
BR_047
BR_048
BR_049
BR_050

## Tahsin (hidden)
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
Account | Account | BR-001, BR-002, BR-003, BR-004, BR-005, BR-006, BR-007, BR-008 | 8 | 20.00% | High: 6 Medium: 1 Low: 1
Forget Password | Forget Password | BR-009 | 1 | 2.50% | High: 0 Medium: 1 Low: 0
History | History | BR-010 | 1 | 2.50% | High: 0 Medium: 1 Low: 0
Home | Quick Booking | BR-011, BR-012, BR-013, BR-014, BR-015, BR-016, BR-017, BR-018 | 8 | 20.00% | High: 6 Medium: 2 Low: 0
Landing screen | Home | BR-019, BR-020, BR-021, BR-022, BR-023, BR-024, BR-025, BR-026 | 8 | 20.00% | High: 3 Medium: 5 Low: 0
OTP | OTP | BR-027, BR-028, BR-029, BR-030 | 4 | 10.00% | High: 2 Medium: 2 Low: 0
Sign-up | Sign-up | BR-031, BR-032, BR-033, BR-034 | 4 | 10.00% | High: 2 Medium: 2 Low: 0
Vehicle Information | Vehicle Information | BR-035, BR-036, BR-037, BR-038, BR-039, BR-040 | 6 | 15.00% | High: 3 Medium: 3 Low: 0