## Main Report
Tester : | Mohammed Fahad Faisal Tahsin Ahmmed |  | Severity | Issues
Project Name: | OUI Impact |  | High | 16
Project URL: | https://drive.google.com/drive/u/1/folders/1jHCOJ4-cf7QP2AvdXMWOEKl_jTwM89qz |  | Medium | 6
Developer: | AI Strix |  | Low | 11
OS:
Environment |  |  | Total Test Cases: | 33
|  |  | Test Case Solved : | 29
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Tester | Feedback | Comment
BR-001 | App | App | App icon alignment issue | User need to download the app on their devices | Download the app | N/A | Icon placement should be accurate | Icon alignment is not perfect | Fail | Low | https://drive.google.com/file/d/1fbwvfqBw7AL31Bh3zYq1e42PzlvHhUoD/view?usp=drive_link |  | Fahad | Solved | Aproved by Client
BR-002 | App | No Chat | Button Missing | User need to download the app on their devices | 1. Open app | N/A | All button should be placed perfectly | Missing button has been noticed | Fail | High | https://drive.google.com/file/d/1-852cYEyh-8sp6XZS1gVg0TkJzw1HNr9/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-003 | App | No Reward | Button Missing | User need to download the app on their devices | 1. Open app | N/A | All button should be placed perfectly | Missing button has been noticed | Fail | High | https://drive.google.com/file/d/18Tz-fIQy92qBBiFGeCLA4stx0N8GekmQ/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-004 | Home | Home | Limit section missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1McV5tHkr2PlRgz5mWn1LG-Po4x4Wyecx/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-005 | Home | Home | Notification bar missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1U2u1kdUfJzOPPsFABPsrEDrwbG9f784X/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-006 | Home | Home | conversation and personal field section missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/12f-xDnuy7Jt811l5hzla7s_K09kJMJj1/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-007 | Leader Board | Leader Board | Pic background should be white but it is in transparent | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section 4 Click on redemption point | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1eEz2XIAkYqc4ydtjqzFjTs5077zfGLOt/view?usp=sharing |  | Fahad |  | The placeholder image background looks like transparent image. It has white background
BR-008 | Login | Login | Different design has been noticed | User need to download the app on their devices | 1. Open app 2. Click on Login | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1OiAZx95iqY8d8BbCUXXY0rLHPiZwxLnL/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-009 | Login | Login | Failed to login using google , apple and facebook id | User need to download the app on their devices | 1. Open app 2. Click on Login | N/A | User should be able to login using their google , facebook and apple id | failed to login using different method | Fail | High | https://drive.google.com/file/d/1SkvgL9gbh9Sp4h2yr8CCREpA_ileAZHC/view?usp=sharing |  | Fahad |  | Will be implemented in backend phase
BR-010 | Login | Login | The login operation failed by entering of valid credentials. | User need to download the app on their devices | 1. Open app 2. Login | Email : weseha6766@idwager.com pass : 1234abcdEF | User should be able to login by providing valid credentials | Failed to login by giving valid credentials | Fail | High | https://drive.google.com/file/d/1FSwlhhPF_Jz-DH1dxqEcwKc2qnmA96Jq/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-011 | Login | Login | Should be placed as title not as placeholder | User need to download the app on their devices | 1. Open app 2. Login | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1pRCQJNNXPghiuWmUD4wbM69TCPceErJS/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-012 | OTP | OTP | Alignment issue | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1NrM_g37-1Og3Ux3xmjbs6Ph2E8iUJjvL/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-013 | OTP | OTP | Design issue | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1lQ7gVJzWUHYOPhzRRB-1AkOKrdH2jfH4/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-014 | OTP | OTP | Failed to receive OTP via mail | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register 4. Goto OTP page | Email : weseha6766@idwager.com pass : 1234abcdEF | User should be able to receive their OTP via mail after registering | failed to receive OTP in the registered mail | Fail | High | https://drive.google.com/file/d/1rbwTLHV73bgf_iiWO7xzR7g__yLvqXxv/view?usp=sharing |  | Fahad |  | Will be implemented in backend phase
BR-015 | Panel | Panel | Design issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on top right icon to open panel | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/12lo_mJIIEyA6VF8Kt0P7nrHrAe0AcenW/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-016 | Profile | Profile | Profile page appears after register | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register 4. Goto OTP page | Email : weseha6766@idwager.com pass : 1234abcdEF | Profile page should be appear when user login to the page wih register credentials | Page apear after register | Fail | High | https://drive.google.com/file/d/12WFq9F46mN9-_uFjJ-k-1tJ9T4fvBdi0/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-017 | Profile | Profile | Failed to update user profile | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on profile | Email : weseha6766@idwager.com pass : 1234abcdEF | Users should have the ability to update their profile information following a successful login. | Failed to update user profile | Fail | High | https://drive.google.com/file/d/1DoTYThx1hUohmHpA-C2ye12Y3pHehJRj/view?usp=sharing |  | Fahad |  | Will be implemented in backend phase
BR-018 | Redeem | Redeem | Different title name placed | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1s_9QJhkv7-aTVaVlTOOJQRG6jrpTmZ2F/view?usp=sharing |  | Fahad | Solved
BR-019 | Redeem | Redeem | Page name should be Reward but displayed as Redeem | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/13HyM3KpuRmgHdOCmeiuUJlj0zKSJkJJZ/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-020 | Redeem | Redeem | refer list missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1RgajnTmk5Jhexv8U3sgwS46pIoOIXGao/view?usp=sharing |  | Fahad | Solved
BR-021 | Redeem | Redeem | Leader board name as redemption point | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1VCLSMYa9fPqkA15QHwn1pKjL3dkmvIY3/view?usp=sharing |  | Fahad | Solved
BR-022 | Register | Register | Tic box button should be placed according to design | User need to download the app on their devices | 1. Open app 2. Click on register | N/A | Square tic box button should be placed | Radio button placed in the square button field | Fail | Low | https://drive.google.com/file/d/1vrcqUYkOIs-IjqQV4JCIu5sXsfekn7is/view?usp=sharing |  | Fahad | Solved
BR-023 | Register | Register | Terms and condition and privacy policy page missing | User need to download the app on their devices | 1. Open app 2. Click on register | N/A | Terms and condition and privacy policy page should be placed in the register page | Plain text found insted of linked pages of terms and condition and privacy policy | Fail | High | https://drive.google.com/file/d/1vrcqUYkOIs-IjqQV4JCIu5sXsfekn7is/view?usp=sharing |  | Fahad | Solved
BR-024 | Reset password | Reset password | Page flow missing | User need to download the app on their devices | 1. Open app 2. Login 3. Click on forget password | Email : weseha6766@idwager.com pass : 1234abcdEF | Page flow should be accurate and match with client requirement | Page missing | Fail | High | https://drive.google.com/file/d/1ffAglhyI3-LkTIx2ds-f9nnf9aRP9M2E/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-025 | Terms and condition | Terms and condition | Page missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1xU6QEM94SsUBvZwrpf3L7YDTyxcMkRkU/view?usp=sharing |  | Fahad | Solved
BR-026 | Watch and earn | Watch and earn | redeem description missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1yj8i6GlOjorpnWzljgfzoDM8rgYHVD6x/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-027 | Welcome | On Boarding 1 | Alignment issue | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1Kc2G4sSMzxdd1Migyq_L8pZHRUuWBuMD/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-028 | Welcome | On Boarding 2 | Alignment issue | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1rGnFUgLJ8lp-_NPEG5-Zo9sa2GCXDW-G/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-029 | Welcome | On Boarding 4 | Heading name different | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1iNFkp4bQO5MbHRFAjQ6-bUd0_4tK757G/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-030 | Welcome | Welcome | Different app name | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/19EQs3W-3H3cmenWeIjnsjO74TVUYdiqR/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-031 | Your Impact | Your Impact | Alignment and format issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section 4 Click on redemption point | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/14thBFFXTawrFH-6XlHduLG9OTVscazid/view?usp=sharing |  | Fahad | Solved
BR-032 | Your Impact | Your Impact | Design issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1R9OZU1lVTDsIsWbZmYoIXjjJ4EVwZ8Eq/view?usp=sharing |  | Fahad | Solved | Aproved by Client
BR-033 | Your Impact | Your Impact | Description missing in the upgrade to premium banner | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1VTB8ezTRtQoysQH1s4NswcgVEarx7H80/view?usp=sharing |  | Fahad | Solved | Aproved by Client

## Fahad
Tester : | Mohammed Fahad Faisal
Project Name:
Developer:
OS: | Windows 11 Pro Version:24H2 OS build:26100.4946
Environment: | Brave 1.81.135 (Official Build) (64-bit) Chromium: 139.0.7258.127
Test ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback
TC_001 | App | App | App icon alignment issue | User need to download the app on their devices | Download the app | N/A | Icon placement should be accurate | Icon alignment is not perfect | Fail | Low | https://drive.google.com/file/d/1fbwvfqBw7AL31Bh3zYq1e42PzlvHhUoD/view?usp=drive_link
TC_002 | App | No Chat | Button Missing | User need to download the app on their devices | 1. Open app | N/A | All button should be placed perfectly | Missing button has been noticed | Fail | High | https://drive.google.com/file/d/1-852cYEyh-8sp6XZS1gVg0TkJzw1HNr9/view?usp=sharing
TC_003 | App | No Reward | Button Missing | User need to download the app on their devices | 1. Open app | N/A | All button should be placed perfectly | Missing button has been noticed | Fail | High | https://drive.google.com/file/d/18Tz-fIQy92qBBiFGeCLA4stx0N8GekmQ/view?usp=sharing
TC_004 | Welcome | On Boarding 1 | Alignment issue | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1Kc2G4sSMzxdd1Migyq_L8pZHRUuWBuMD/view?usp=sharing
TC_005 | Welcome | On Boarding 2 | Alignment issue | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1rGnFUgLJ8lp-_NPEG5-Zo9sa2GCXDW-G/view?usp=sharing
TC_006 | Welcome | On Boarding 4 | Heading name different | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1iNFkp4bQO5MbHRFAjQ6-bUd0_4tK757G/view?usp=sharing
TC_007 | Welcome | Welcome | Different app name | User need to download the app on their devices | 1. Open app | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/19EQs3W-3H3cmenWeIjnsjO74TVUYdiqR/view?usp=sharing
TC_008 | Login | Login | Different design has been noticed | User need to download the app on their devices | 1. Open app 2. Click on Login | N/A | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1OiAZx95iqY8d8BbCUXXY0rLHPiZwxLnL/view?usp=sharing
TC_009 | Login | Login | Failed to login using google , apple and facebook id | User need to download the app on their devices | 1. Open app 2. Click on Login | N/A | User should be able to login using their google , facebook and apple id | failed to login using different method | Fail | High | https://drive.google.com/file/d/1SkvgL9gbh9Sp4h2yr8CCREpA_ileAZHC/view?usp=sharing
TC_010 | Register | Register | Tic box button should be placed according to design | User need to download the app on their devices | 1. Open app 2. Click on register | N/A | Square tic box button should be placed | Radio button placed in the square button field | Fail | Low | https://drive.google.com/file/d/1vrcqUYkOIs-IjqQV4JCIu5sXsfekn7is/view?usp=sharing
TC_011 | Register | Register | Terms and condition and privacy policy page missing | User need to download the app on their devices | 1. Open app 2. Click on register | N/A | Terms and condition and privacy policy page should be placed in the register page | Plain text found insted of linked pages of terms and condition and privacy policy | Fail | High | https://drive.google.com/file/d/1vrcqUYkOIs-IjqQV4JCIu5sXsfekn7is/view?usp=sharing
TC_012 | OTP | OTP | Alignment issue | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1NrM_g37-1Og3Ux3xmjbs6Ph2E8iUJjvL/view?usp=sharing
TC_013 | OTP | OTP | Design issue | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1lQ7gVJzWUHYOPhzRRB-1AkOKrdH2jfH4/view?usp=sharing
TC_014 | OTP | OTP | Failed to receive OTP via mail | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register 4. Goto OTP page | Email : weseha6766@idwager.com pass : 1234abcdEF | User should be able to receive their OTP via mail after registering | failed to receive OTP in the registered mail | Fail | High | https://drive.google.com/file/d/1rbwTLHV73bgf_iiWO7xzR7g__yLvqXxv/view?usp=sharing
TC_015 | Profile | Profile | Profile page appears after register | User need to download the app on their devices | 1. Open app 2. Click on register 3. Provide data and click register 4. Goto OTP page | Email : weseha6766@idwager.com pass : 1234abcdEF | Profile page should be appear when user login to the page wih register credentials | Page apear after register | Fail | High | https://drive.google.com/file/d/12WFq9F46mN9-_uFjJ-k-1tJ9T4fvBdi0/view?usp=sharing
TC_016 | Profile | Profile | Failed to update user profile | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on profile | Email : weseha6766@idwager.com pass : 1234abcdEF | Users should have the ability to update their profile information following a successful login. | Failed to update user profile | Fail | High | https://drive.google.com/file/d/1DoTYThx1hUohmHpA-C2ye12Y3pHehJRj/view?usp=sharing
TC_017 | Login | Login | The login operation failed by entering of valid credentials. | User need to download the app on their devices | 1. Open app 2. Login | Email : weseha6766@idwager.com pass : 1234abcdEF | User should be able to login by providing valid credentials | Failed to login by giving valid credentials | Fail | High | https://drive.google.com/file/d/1FSwlhhPF_Jz-DH1dxqEcwKc2qnmA96Jq/view?usp=sharing
TC_018 | Login | Login | Should be placed as title not as placeholder | User need to download the app on their devices | 1. Open app 2. Login | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1pRCQJNNXPghiuWmUD4wbM69TCPceErJS/view?usp=sharing
TC_019 | Reset password | Reset password | Page flow missing | User need to download the app on their devices | 1. Open app 2. Login 3. Click on forget password | Email : weseha6766@idwager.com pass : 1234abcdEF | Page flow should be accurate and match with client requirement | Page missing | Fail | High | https://drive.google.com/file/d/1ffAglhyI3-LkTIx2ds-f9nnf9aRP9M2E/view?usp=sharing
TC_020 | Home | Home | Limit section missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1McV5tHkr2PlRgz5mWn1LG-Po4x4Wyecx/view?usp=sharing
TC_021 | Home | Home | Notification bar missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1U2u1kdUfJzOPPsFABPsrEDrwbG9f784X/view?usp=sharing
TC_022 | Home | Home | conversation and personal field section missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/12f-xDnuy7Jt811l5hzla7s_K09kJMJj1/view?usp=sharing
TC_023 | Panel | Panel | Design issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on top right icon to open panel | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/12lo_mJIIEyA6VF8Kt0P7nrHrAe0AcenW/view?usp=sharing
TC_024 | Redeem | Redeem | Different title name placed | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1s_9QJhkv7-aTVaVlTOOJQRG6jrpTmZ2F/view?usp=sharing
TC_025 | Redeem | Redeem | Page name should be Reward but displayed as Redeem | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/13HyM3KpuRmgHdOCmeiuUJlj0zKSJkJJZ/view?usp=sharing
TC_026 | Redeem | Redeem | refer list missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1RgajnTmk5Jhexv8U3sgwS46pIoOIXGao/view?usp=sharing
TC_027 | Watch and earn | Watch and earn | redeem description missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1yj8i6GlOjorpnWzljgfzoDM8rgYHVD6x/view?usp=sharing
TC_028 | Redeem | Redeem | Leader board name as redemption point | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1VCLSMYa9fPqkA15QHwn1pKjL3dkmvIY3/view?usp=sharing
TC_029 | Leader Board | Leader Board | Pic background should be white but it is in transparent | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section 4 Click on redemption point | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Low | https://drive.google.com/file/d/1eEz2XIAkYqc4ydtjqzFjTs5077zfGLOt/view?usp=sharing
TC_030 | Your Impact | Your Impact | Alignment and format issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on redeem section 4 Click on redemption point | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/14thBFFXTawrFH-6XlHduLG9OTVscazid/view?usp=sharing
TC_031 | Your Impact | Your Impact | Design issue | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1R9OZU1lVTDsIsWbZmYoIXjjJ4EVwZ8Eq/view?usp=sharing
TC_032 | Your Impact | Your Impact | Description missing in the upgrade to premium banner | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | Medium | https://drive.google.com/file/d/1VTB8ezTRtQoysQH1s4NswcgVEarx7H80/view?usp=sharing
TC_033 | Terms and condition | Terms and condition | Page missing | User need to download the app on their devices | 1. Open app 2. Login using valid credentials 3. Click on your impact | Email : weseha6766@idwager.com pass : 1234abcdEF | Alignment and design should be accurate as client expectation | Alignment issue has been observed | Fail | High | https://drive.google.com/file/d/1xU6QEM94SsUBvZwrpf3L7YDTyxcMkRkU/view?usp=sharing

## Tahsin
Tester : |  |  | Severity | Issues
Project Name: |  |  | High | 0
Project URL: |  |  | Medium | 0
Developer: |  |  | Low | 0
OS:
Environment |  |  | Total Test Cases: | 0
Test Case Solved :
Test Case ID | Module | Sub Module | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Screen Shots | Suggestion | Feedback

## Summary Report
Module | Sub Module | Test Case ID | Bug Count | Bug Rate % | Bug Severity
App | App | BR-001 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
App | No Chat | BR-002 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
App | No Reward | BR-003 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
Home | Home | BR-004, BR-005, BR-006 | 3 | 9.09% | High: 3 Medium: 0 Low: 0
Leader Board | Leader Board | BR-007 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Login | Login | BR-008, BR-009, BR-010, BR-011 | 4 | 12.12% | High: 2 Medium: 0 Low: 2
OTP | OTP | BR-012, BR-013, BR-014 | 3 | 9.09% | High: 1 Medium: 1 Low: 1
Panel | Panel | BR-015 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Profile | Profile | BR-016, BR-017 | 2 | 6.06% | High: 2 Medium: 0 Low: 0
Redeem | Redeem | BR-018, BR-019, BR-020, BR-021 | 4 | 12.12% | High: 2 Medium: 2 Low: 0
Register | Register | BR-022, BR-023 | 2 | 6.06% | High: 1 Medium: 0 Low: 1
Reset password | Reset password | BR-024 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
Terms and condition | Terms and condition | BR-025 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
Watch and earn | Watch and earn | BR-026 | 1 | 3.03% | High: 1 Medium: 0 Low: 0
Welcome | On Boarding 1 | BR-027 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Welcome | On Boarding 2 | BR-028 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Welcome | On Boarding 4 | BR-029 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Welcome | Welcome | BR-030 | 1 | 3.03% | High: 0 Medium: 0 Low: 1
Your Impact | Your Impact | BR-031, BR-032, BR-033 | 3 | 9.09% | High: 0 Medium: 3 Low: 0