## Main Report
Tester : | Mohammed Fahad Faisal |  | Severity | Issues
Project Name: | Tiktok-Dictionary |  | High | 8
Project: | Web App |  | Medium | 10 |  | Username : | test12#$#%
Developer: |  |  | Low | 1 |  | Password : | test
OS: |  |  | Total Test Cases: | 19
Enviroment: |  |  | Test Case Solved : | 19
Test ID | Module | Summary | Steps | Expected Result | Actual Result | Result | Severity | Screen Shots | Suggestion | Feedback | FrontEnd FeedBack
TC_001 | SignUp | Signup should contain email, username and password from client to register | 1. Open link | From register, it would take email , username and password from user | only taking username and password | Fail | Medium | https://drive.google.com/file/d/1__P9gdNkfB066_czhU48qsYvGa7vfLfr/view?usp=drive_link |  | Solved | do just done and remove email add captcha as per client correction
TC_002 | Home | "Most Agreed Definition" section missing in frontend | 1. Open link 2. Go after treanding right now segment | Design should be same as client requirement | Missing "Most Agreed Definition" section | Fail | High | https://drive.google.com/file/d/1034C93V05t-pTCr-8JJd8hcorSuBq8TK/view?usp=drive_link |  | Solved | In home page client only wants trending sections he tells me to remove all the section except trending words
TC_003 | Home | "Fresh Submission" section missing in frontend | 1. Open link 2. Go after treanding right now segment | Design should be same as client requirement | Missing "Fresh Submission" section | Fail | High | https://drive.google.com/file/d/1mc2Jb5qKX5bw4wV6Sa7B9sE2HcjP1SPk/view?usp=drive_link |  | Solved | In home page client only wants trending sections he tells me to remove all the section except trending words
TC_004 | Home | "Explore Catagories" section missing in frontend | 1. Open link 2. Go after treanding right now segment | Design should be same as client requirement | "Explore Catagories" section missing in frontend | Fail | High | https://drive.google.com/file/d/17aZMwHmI5MLESHwEHBBE9UyTWeqeQLfl/view?usp=drive_link |  | Solved | In home page client only wants trending sections he tells me to remove all the section except trending words
TC_005 | Home | section missing in frontend | 1. Open link 2. Go after treanding right now segment | Design should be same as client requirement | section missing in frontend | Fail | High | https://drive.google.com/file/d/1yDOtzugyAfvu-AVaJZubdzTf4V-nrTh0/view?usp=drive_link |  | Solved | dont know which section you are talking about
TC_006 | Footer | No hyperlink attatched | 1. Open link 2. Go after footer section | Social Media link should be attatched | Missing social media links | Fail | High | https://drive.google.com/file/d/1MvuPBwU2uhyMBuTP2IXTNtTMy8lj-nR8/view?usp=drive_link |  | Solved | client haven't provided the social media links yet so its only redirecting on social media only
TC_007 | Home | Word "Tiktok" fade away if the background is white | 1. Open link 2. Go to white background | Page name should be displayed under different pattern | Failed to display page name properly under white background | Fail | Medium | https://drive.google.com/file/d/1zx_uUU62Ncdw06AEVELkXtjH7qp5fqdf/view?usp=drive_link |  | Solved | It happens for the sticky effect on scrolling and yes its fadeway cause we dont know how to design but i just followed the figma if client was facing any problem if he let us know this issue we will try to fix this , [this is added by our own client didnt mentioned about it]
TC_008 | Word Detail Page | Different font use | 1. Open link 2. Click on words | Page alignment and design should be similar with the client requirement | Link, dislike and other words uses different font then figma | Fail | Medium | https://drive.google.com/file/d/19ci6Fuwr62WMdYwQZ12uwEFt7haJkHHu/view?usp=drive_link |  | Solved | we actually use the given font in figma inter and GRIFTER
TC_009 | Word Detail Page | Should display username not Email | 1. Open link 2. Click on words | It should display the user name of the person who add this word | Email address shown in username section instead of username | Fail | Medium | https://drive.google.com/file/d/1_yLY8H-QuZKhI4TYtuoSEHzffytpbiVq/view?usp=drive_link |  | Solved | the showing email is username user set the email as username
TC_010 | Word Detail Page | "Report" button missing in frontend | 1. Open link 2. Click on words | All button should be implemented which was in figma | Missing report button for word | Fail | High | https://drive.google.com/file/d/1posyT4HnxJkOce-mx_E2IujS8wl67hD0/view?usp=drive_link |  | Solved | this has not design ...which fields can be included in report
TC_011 | Submit a word | input title color should be black as in figma | 1. Open link 2. Click on Submit | Alignment and design should be similar with figma | Different design has been noticed | Fail | Medium | https://drive.google.com/file/d/1rgD-KNL0GP3U-vq-7iTu5G2kUgCWQxGw/view?usp=drive_link |  | Solved | yes this things is already corrected
TC_012 | Submit a word | Doesn't indicate which field are required | 1. Open link 2. Click on Submit | Required fields should marked | Required fields are not marked | Fail | Medium | https://drive.google.com/file/d/1v7PotWOzJYsrvP9kGmZ29BganVsh_r4E/view?usp=drive_link |  | Solved | client didnt tell me which field are required or mendatory and didn't even say a word how its gonna work
TC_013 | Submit a word | Failed to detect word existance | 1. Open link 2. Click on Submit | Should detect auto when user enter word | Failed to detect | Fail | High | https://drive.google.com/file/d/1Kwy5duZ_QDVp-G1YKyrTasZXvdiTcMDQ/view?usp=drive_link |  | Solved | we done this project as per the figma we tried to solve some inconsistencies in this project already to detect a word after submitting user need to search the word from the search bar
TC_014 | Submit a word | Failed to detect word existance | 1. Open link 2. Click on Submit | Should detect auto when user enter word | Failed to detect | Fail | High | https://drive.google.com/file/d/1-xYj77Q2BAPGR-lvIp9N6yPZriZY4vUH/view?usp=drive_link |  | Solved | we done this project as per the figma we tried to solve some inconsistencies in this project already to detect a word after submitting user need to search the word from the search bar
TC_015 | Discover | Page Icon blend with background color | 1. Open link 2. Click on Discover | Alignment and design should be similar with figma | Different design has been noticed | Fail | Low | https://drive.google.com/file/d/1imHDfNAXKMiZKwdsbAc0gUY-3eBQClOo/view?usp=drive_link |  | Solved | client didnt say things about this project for better experience we tried this as a developer we dont know which color client would like the most since client didnt even say anything
TC_016 | Discover | input title color should be black as in figma | 1. Open link 2. Click on Discover | Alignment and design should be similar with figma | Different design has been noticed | Fail | Medium | https://drive.google.com/file/d/11MmUB1C1rpxUJ4zncSHikdkDPUWHmnug/view?usp=drive_link |  | Solved | yes this things is already corrected
TC_017 | Discover | word suggestions failed | 1. Open link 2. Click on Discover | Alignment and design should be similar with figma | Different design has been noticed | Fail | Medium | https://drive.google.com/file/d/1BqpMWH9VPV8PkGLPnPFXq47PAR4e7eMR/view?usp=drive_link |  | Solved | we dont know actually the logic behid suggesting a word every functionality you see given from us as extra
TC_018 | Discover | word suggestions failed | 1. Open link 2. Click on Discover | Alignment and design should be similar with figma | Different design has been noticed | Fail | Medium | https://drive.google.com/file/d/1NkYj6lutTirzpjILNupyy9CIIHYVsomu/view?usp=drive_link |  | Solved | we dont know actually the logic behid suggesting a word every functionality you see given from us as extra
TC_019 | Discover | Words are listead in the catagory section | 1. Open link 2. Click on Discover | Alignment and design should be similar with figma | Different design has been noticed | Fail | Medium | https://drive.google.com/file/d/1gpeRwpf_ouTUERTIITRsqj-1Z1CE1t0s/view?usp=drive_link |  | Solved | we remove the category section as per client message
TC_020
TC_021
TC_022
TC_023
TC_024
TC_025
TC_026
TC_027
TC_028